## ABAP Objectr Tracker Template
SrNo | Module | Interface | Development Description | Scope | FRICE Category | Priority | PriorityType | Complexity | Functional Consultant | RGS |  |  |  | FS |  | ABAP Development |  |  |  | HBT Testing |  | CTM Testing |  | UAT Sign Off | Go-Live Planned Date (dd.mm.yyyy)
[10 empty] | Planned Preparation Start Date (dd.mm.yyyy) | Planned Preparation Finish Date (dd.mm.yyyy) | Planned Submission Date (dd.mm.yyyy) | Planned Approval Date (dd.mm.yyyy) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned ABAP Consultant | Duration (Days) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned Date (dd.mm.yyyy)
1 | SAP PS | open text | WBS, Network, Activity, Mileston Upload Program | SOW | Conversion | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
2 | SAP PS | open text | BPO Upload Program | SOW | Conversion | 1 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
3 | SAP PS | open text | Unit Cost Plan Upload Program | SOW | Conversion | 2 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
4 | SAP PS | open text | Budget Approval Procedure & document attachment compulsary | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
5 | SAP PS | open text | Milestone Confimation Mail Notification with completion Image & architect certificate attachement | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
6 | SAP PS | Smart app | Project & Work Breakdown Structure sync to smartapp | SOW | Integration | 1 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
7 | SAP PS | Smart app | WBS & Milestones (Payment milestones plans) sync to smartapp | SOW | Integration | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
8 | SAP PS | Smart app | Network Sync to Smartapp | SOW | Integration | 4 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
9 | SAP PS | Smart app | Activities Sync from Smartapp to SAP | SOW | Integration | 5 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
10 | SAP PS | Smart app | Link BOQ to WBS in SAP then sync to smartapp | SOW | Integration | 3 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
11 | SAP DMS | open text | All attached documents in SAP to view in Contentverse DMS | SOW | Integration | 1 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
12 | SAP FICO | open text | Vendor master upload | SOW | Conversion | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
13 | SAP FICO | open text | Asset Cutover upload Program | SOW | Conversion | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
14 | SAP FICO | open text | Cutover Template | SOW | Conversion | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
15 | SAP FICO | open text | GSTR1 | SOW | Report | 1 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
16 | SAP FICO | open text | GSTR2 | SOW | Report | 1 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
17 | SAP FICO | open text | Bank Reco Upload Program | SOW | Conversion | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
18 | SAP FICO | open text | Customer Tax Invoice (Interest) | SOW | Form | 2 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
19 | SAP FICO | open text | Customer Receipt Screen | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
20 | SAP FICO | open text | Customer Receipt List | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
21 | SAP FICO | open text | Project & Plants Mapping table | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
22 | SAP FICO | SFDC | Token Amount SFDC-SAP | SOW | Integration | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
23 | SAP FICO | SFDC | Customer Receipts (SFDC) | SOW | Integration | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
24 | SAP FICO | SFDC | Interest Waiver | SOW | Integration | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
25 | SAP FICO | Clear tax | Invoice wise Match & Mismatch Report showing Revenue as per in P&L & as per GST Outward Register | SOW | Integration | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
26 | SAP FICO | Clear tax | GSTR 1 | SOW | Integration | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
27 | SAP FICO | Clear tax | GSTR 2 | SOW | Integration | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
28 | SAP FICO | Clear tax | GSTN , Address & Pan Validation | SOW | Integration | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
29 | SAP FICO | open text | GSTN , Address & Pan Validation | SOW | Report | 1 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
30 | SAP FICO | open text | Expense Head wise TDS deduction required | SOW | Report | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
31 | SAP FICO | open text | ITC utilization project wise | SOW | Report | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
32 | SAP FICO | Report | Cash Flow Report | Additional | Report | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
33 | SAP FICO | open text | Invoice wise Match & Mismatch Report showing Revenue as per in P&L & as per GST Outward Register | Additional | Report | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
34 | SAP SD | open text | Unit Upload Program | SOW | Conversion | 2 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
35 | SAP SD | open text | Other Charges Upload Program | SOW | Conversion | 2 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
36 | SAP SD | open text | Customer creation Program | SOW | Conversion | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
37 | SAP SD | open text | Unit Status Auto Update | SOW | Enhancement | 1 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
38 | SAP SD | open text | Sales Order creation Program | SOW | Conversion | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
39 | SAP SD | open text | Mass Demand creation Program | SOW | Enhancement | 1 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
40 | SAP SD | open text | Auto Debit /Credit Note Program | Hold | Enhancement | 1 | Hold | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
41 | SAP SD | open text | Additional Custom tab in SO (Additional Field) | SOW | Enhancement | 2 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
42 | SAP SD | open text | Price custom routine 1(land abatment) for Unit | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
43 | SAP SD | open text | Price custom routine 2(Net of land abatment) for Unit | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
44 | SAP SD | open text | Price custom routine for discount calculation for Unit | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
45 | SAP SD | open text | Price custom routine for GST % After OC Receive for Unit | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
46 | SAP SD | open text | Price custom routine for GST % After OC Receive for other charges | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
47 | SAP SD | open text | Milestone wise demand report(Amout vs actual receipt amount)/MIS Sales | SOW | Report | 1 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
48 | SAP SD | open text | Booking Form | SOW | Form | 2 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
49 | SAP SD | open text | Reminder letter1 | SOW | Form | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
50 | SAP SD | open text | Reminder letter2 | SOW | Form | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
51 | SAP SD | open text | Termination Form | SOW | Form | 1 | Post Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
52 | SAP SD | open text | Demand form | SOW | Form | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
53 | SAP SD | open text | Unit Cancellation Process with workflow(Approval process) | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
54 | SAP SD | open text | Brokerage payout Process | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
55 | SAP SD | open text | Brokerage payout Report | SOW | Report | 1 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
56 | SAP SD | SFDC | Unit Master sync with SFDC | SOW | Integration | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
57 | SAP SD | SFDC | Unit master Stauts (SAP-SFDC) | SOW | Integration | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
58 | SAP SD | SFDC | Unit master Stauts (SFDC-SAP) | SOW | Integration | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
59 | SAP SD | SFDC | Customer master Creation | SOW | Integration | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
60 | SAP SD | SFDC | Broker Creation from SFDC to SAP | SOW | Integration | 4 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
61 | SAP SD | SFDC | Broker Invoice creation from SAP to SFDC | SOW | Integration | 10 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
62 | SAP SD | SFDC | Broker payment SAP-SFDC | SOW | Integration | 11 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
63 | SAP SD | SFDC | Booking creation SFDC-SAP | SOW | Integration | 5 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
64 | SAP SD | SFDC | Booking amendment | SOW | Integration | 6 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
65 | SAP SD | SFDC | Demand information sync to SFDC | SOW | Integration | 7 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
66 | SAP SD | SFDC | Debit note - wrt Demand no | SOW | Integration | 8 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
67 | SAP SD | SFDC | Credit note - wrt Demand no | SOW | Integration | 9 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
68 | SAP SD | SFDC | Unit Transfer | SOW | Integration | 12 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
69 | SAP SD | SFDC | Unit Cancellation | SOW | Integration | 13 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
70 | SAP SD | Clear tax | E invoicing/IRN Creation SAP-CT | SOW | Integration | 15 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
71 | SAP SD | Clear tax | E invoicing/IRN Cancellation SAP-CT | SOW | Integration | 15 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
72 | SAP SD | Clear tax | Eway Bill Generation SAP-CT | SOW | Integration | 15 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
73 | SAP SD | Clear tax | Eway Bill Cancellation SAP-CT | SOW | Integration | 15 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
74 | SAP SD | Clear tax | Get Eway Bill PDF | SOW | Integration | 15 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
75 | SAP SD | SFDC | Post Possession clearance | SOW | Integration | 14 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
76 | SAP SD | open text | Future Demand & Cash flow report | SOW | Report | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
77 | SAP SD | open text | Demand will not create if customer blocked | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
78 | SAP SD | open text | Delay In Process Report to identify the demand(Milestone trigger But due for billing) | SOW | Report | 1 | Post Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
79 | SAP SD | open text | RERA Form-3 | SOW | Form | 2 | Post Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
80 | SAP SD | open text | RERA Form-5 | SOW | Form | 2 | Post Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
81 | SAP SD | open text | Scrap Invoice | SOW | Form | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
82 | SAP SD | open text | Legacy Data Table & Upload Program | SOW | Report | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
83 | SAP MM | open text | Material Master Upload Program | SOW | Conversion | 1 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
84 | SAP MM | open text | Service Master Upload Program | SOW | Conversion | 1 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
85 | SAP MM | open text | HSN Master Upload-LSMW | SOW | Conversion | 1 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
86 | SAP MM | open text | Cutover Purchase Order Upload Program | SOW | Conversion | 1 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
87 | SAP MM | open text | Cutover Work Order Upload Program | SOW | Conversion | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
88 | SAP MM | open text | Initial Stock Upload Program | SOW | Conversion | 2 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
89 | SAP MM | open text | Purchase Order Print | SOW | Form | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
90 | SAP MM | open text | Purchase Order Amendment | SOW | Form | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
91 | SAP MM | open text | Work Order Print | SOW | Form | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
92 | SAP MM | open text | Work Order Amendment Form | SOW | Form | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
93 | SAP MM | open text | Purchase (Material) Debit Note | SOW | Form | 2 | Post Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
94 | SAP MM | open text | Purchase (Service) Debit Note | SOW | Form | 1 | Post Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
95 | SAP FICO | open text | Payment Request (Advance) | SOW | Form | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
96 | SAP FICO | open text | Vendor Onboading | SOW | Form | 2 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
97 | SAP MM | open text | Purchase Register - Indent to Payment | SOW | Report | 1 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
98 | SAP MM | open text | Work Order Amendment Enhancement | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
99 | SAP MM | open text | Release Strategy mandatory for PO/WO saving | SOW | Enhancement | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
100 | SAP MM | open text | Release Strategy Reset with Version Management | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
101 | SAP MM | open text | Transfer Posting 311Q to Contractor w.r.t. WO | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
102 | SAP MM | open text | Maintain WO Terms & Conditions – Header | SOW | Enhancement | 1 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
103 | SAP MM | open text | Bill Inward with Workflow | SOW | Enhancement | 1 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
104 | SAP MM | Smart app | PO/WO Intergration with Smart App for DPR | SOW | Integration | 2 | Hold | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
105 | SAP MM | Smart app | PR Integration with Smart App | SOW | Integration | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
106 | SAP MM | Smart app | Material and Service Procurement Bidding Intergration with Smart App | SOW | Integration | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
107 | SAP QM | open text | Inspection Plan Upload | SOW | Conversion | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
108 | SAP QM | open text | MIC Quantitative | SOW | Conversion | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
109 | SAP QM | open text | Sampling Procedure | SOW | Conversion | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
110 | SAP QM | open text | Catalog | SOW | Conversion | 2 | Go Live | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
111 | SAP QM | open text | Result Record Report - Smartform | SOW | Form | 2 | SIT | Medium | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
112 | SAP MM | open text | Cost Plan reference rate in Work Order/Purchase Order and warning message on higher rate than cost plan rate in purchasing | SOW | Enhancement | 2 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
113 | SAP MM | open text | Restricting Goods Receipt against Multiple Purchase order in One GRN Document | SOW | Enhancement | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
114 | SAP MM | open text | While Transfer Posting to Contractor Storage, debitable materials (Non-FOC) has to be captured for deductions from RA Bill | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
115 | SAP MM | open text | Quantity Validation for Project Material PR (Doc type ZPPR) | SOW | Enhancement | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
116 | SAP MM | open text | Restricting final RA Bill against Work order if any surplus material for the Work Order (Contractor Godown) is present in stock | SOW | Enhancement | 2 | Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
117 | SAP MM | open text | Debit head of one contractor to be tagged to work order of other contractor | SOW | Enhancement | 2 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
118 | SAP MM | open text | Custom Table and Validation on ITC and Non-ITC Tax Code in Purchase Document. | SOW | Enhancement | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
119 | SAP MM | open text | For Manufacturing Material require Barcode system . Which is Check after Delivery (Test / Performance Report) | Hold | Integration | 2 | Hold | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
120 | SAP MM | open text | Email trigger as per TAT for Bill Inward | SOW | Enhancement | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
121 | SAP MM | open text | Bill Inward TAT report | SOW | Report | 2 | Post Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
122 | SAP MM | open text | Email trigger as per TAT for Project service indent | SOW | Enhancement | 2 | SIT | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
123 | SAP MM | open text | Process payment abstract Print/COP | SOW | Form | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
124 | SAP MM | open text | SLA Report | SOW | Report | 3 | Post Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
125 | SAP MM | open text | Escalation / Price variation calculation in RA Bill | SOW | Enhancement | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
126 | SAP MM | open text | Material reconciliation & material recovery | SOW | Enhancement | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
127 | SAP MM | open text | Recovery of advances in RA Bill | SOW | Enhancement | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
128 | SAP MM | open text | Maintain materials to be issued against the Work Order (Free Supply / Debitable) | SOW | Enhancement | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
129 | SAP MM | open text | Creation of advance request RA Bill against the Work Order | SOW | Enhancement | 3 | SIT | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
130 | SAP MM | open text | Project service indent TAT report | SOW | Report | 2 | Post Go Live | Simple | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
131 | SAP FICO | HDFC/ICICI | Bank Interface | SOW | Integration | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025
132 | SAP FICO | open text | Cheque Back Print | SOW | Form | 2 | Go Live | Complex | 00630848 - Mr. Manssurali R Sayyed | 15.01.2025 | 15.01.2025 | 15.01.2025 | 15.01.2025 | 16.01.2025 | 16.01.2025 | 00630301 - Mr. Vinay Ramchandra Singh | 1 | 17.01.2025 | 17.01.2025 | 18.01.2025 | 18.01.2025 | 19.01.2025 | 19.01.2025 | 20.01.2025 | 21.01.2025

## Module Master Data
ModuleId | ModuleDesc
6 | .Net
115 | .NET Web Designer
66 | Accounts & Finance
108 | Admin
113 | Bid management
38 | BIM_2-3D
39 | BIM_5D
37 | BIM_Primavera_Unifier
100 | Business Analyst
118 | Business Development
70 | Business Development - Govt.
67 | Business Development - Pvt.
63 | Contract Manager
28 | CPI
46 | CRM
101 | CRM Technical
89 | Customer Success
99 | DBA - Database Admin
74 | Delivery
79 | DMS (Non SAP)
47 | Doc. Controller
106 | E-Office
122 | Executive - Contracts
116 | Executive - HR
124 | Executive HR 1
27 | FIORI
34 | FLM
119 | Graphic Designer
76 | Head - COE
61 | Head - Delivery
123 | Head – HR
41 | Helpdesk
102 | HR Manager
78 | Human Resource
112 | Human resource -Recruitment
29 | IDM
120 | Inside Sales
30 | ISU
87 | IT Support & Vendor Management
88 | JAVA Developer
117 | Jr HR Executive
91 | KMS SPOC
90 | Liaison Officer
32 | Lumira
68 | Marketing
21 | Middleware
92 | Mobile App developer (Android)
93 | Mobile App developer (IOS)
80 | Non SAP
109 | Office boy
110 | Office executive
83 | Open Text
73 | Operations
121 | Oracle
75 | Package Coordintaor
64 | PDTO
51 | Planning
52 | Portal
84 | POWER BI
114 | Pre sale Consultant junior
53 | Program Manager
50 | Project Coordinator
45 | Project Manager
71 | Recruitment
85 | RO Coordinator
2 | SAP ABAP
81 | SAP ABAP on HANA
65 | SAP analytics
125 | SAP Ariba DSN
5 | SAP BASIS
58 | SAP BI
59 | SAP BO
72 | SAP BPC
26 | SAP BW
55 | SAP C4C
31 | SAP Cloud Platform
17 | SAP CM
105 | SAP CO
42 | SAP CPM
18 | SAP DMS
43 | SAP EHS
13 | SAP EP
23 | SAP ETM
48 | SAP FI
1 | SAP FICO
104 | SAP GRC
107 | SAP Group Reporting
97 | SAP HANA
4 | SAP HCM
62 | SAP HR ESS/MSS
3 | SAP MM
15 | SAP PI
9 | SAP PM
20 | SAP PO
10 | SAP PP
96 | SAP PRA
16 | SAP PS
22 | SAP QM
11 | SAP REFX
60 | SAP SAC
54 | SAP SD
95 | SAP SEM
14 | SAP SF
44 | SAP Solution Architect
86 | SAP SRM
82 | SAP WM
33 | SAP x-ECM
77 | SAP-MDM
103 | Senior Executive - HR
49 | SME
56 | Software ( Non SAP)
57 | Solution Manager
98 | SQL Server Administrator
111 | SR HR Executive recruitment
40 | T&C Expert
69 | Technology & Innovation
36 | TRM
19 | VBA
94 | Wireframe Designer

## FRICE Category Data
FCategoryId | FCategoryName
1 | Conversion
2 | Enhancement
5 | Form
3 | Integration
4 | Report
6 | Work Flow

## Priority Master Data
PriorityId | PriorityName
1 | All
3 | Go Live
5 | Hold
4 | Post Go Live
2 | SIT

## Complexity Master Data
ComplexityId | ComplexityName
3 | Complex
2 | Medium
1 | Simple

## Consultant Master Data
Emp_Code | Emp_Name
2082 | 00002082 - Mr. Anilkumar Sangameshw Jeur
2726 | 00002726 - Mr. Mangesh Dattatray Wadaje
2878 | 00002878 - Mr. Upagupta Patnaik
3851 | 00003851 - Mr. Ashok Wani
4224 | 00004224 - Mr. Joydeep Banerjee
5494 | 00005494 - Mr. Rajesh Govindraya Shanbhag
5500 | 00005500 - Mr. Kaustav Das
6110 | 00006110 - Mr. Mahesh Babu Bayya
630008 | 00630008 - Mr. Santosh Mahangade
630044 | 00630044 - Mr. Raj Patel
630256 | 00630256 - Mr. Ravindra Ramesh Shenai
630284 | 00630284 - Mr. Sunil Manohar Pachgade
630393 | 00630393 - Mr. Nadeem Ul Haque Shaikh
630464 | 00630464 - Mr. Prashant Salvi
630564 | 00630564 - Mr. Gnanesh Kumsimutt
630658 | 00630658 - Ms. Meghana Bothare
630698 | 00630698 - Mr. Akhilesh Kumar Mishra
630627 | 00630627 - Mr. Saurabh Verma
630701 | 00630701 - Mr. Niladri Bhusan Harichandan
99999999 | 99999999 - Accounts Department
630579 | 00630579 - Mr. Simranjeet Singh Sond
630595 | 00630595 - Mr. Prakash Chandra Behera
630610 | 00630610 - Mr. Muzammil Husain Ansari
630656 | 00630656 - Mr. Prashant Kumar Sinha
630692 | 00630692 - Mr. Harshad N Mhatre
630721 | 00630721 - Mr. Bhabani Sankar Pal
630372 | 00630372 - Mr. Avinash Murlidhar Shelke
630534 | 00630534 - Mr. Raju Vasant Jadhav
630665 | 00630665 - Mr. Mohana Krishna Kandhi
630839 | 00630839 - Mr. Vikas Vilas Ghugare
630841 | 00630841 - Mr. Kuna Srujan
630016 | 00630016 - Mr. Santosh Choudhary
630054 | 00630054 - Ms. Ankita Abhijit Malavde
630291 | 00630291 - Mr. Ajit Uttam Desai
630846 | 00630846 - Mr. AKHIL CHERUKURI
630848 | 00630848 - Mr. Manssurali R Sayyed
630859 | 00630859 - Mr. Dilip Kumar Madderla
630301 | 00630301 - Mr. Vinay Ramchandra Singh
630530 | 00630530 - Mr. Madhu Vijaykumar Manchikatla
630741 | 00630741 - Mr. Snehal Kumbhar
630713 | 00630713 - Mr. Devendra Dandekar
630725 | 00630725 - Mr. Abhishek Pravin Godse
630727 | 00630727 - Mr. Vidhyadhar Tukaram Galande
630864 | 00630864 - Mr. Gaurav Nimbulkar
630792 | 00630792 - Mr. Rakesh Raushan
630887 | 00630887 - Mr. Ravi Varma Bhoompally
630828 | 00630828 - Mr. Vijay Mahajan
630770 | 00630770 - Mr. Saroj Kumar Jena
630802 | 00630802 - Mr. Sanjay Dhadwal
R-061 | R-061 - Mr. Deepak Garde
630890 | 00630890 - Mr. Mandar Ramakant Mhatre
630902 | 00630902 - Mr. Bharat Mainkar
630900 | 00630900 - Ms. BHUBANESWARI PRADHAN
630928 | 00630928 - Mr. Imtiyaz Khan
630940 | 00630940 - Mr. Gunarajashekar Mukkulolu
630942 | 00630942 - Mr. Sourabh Chhangani
630946 | 00630946 - Mr. NIRAJ PRATAP CHAVAN
631564 | 00631564 - Mr. Mohit Kishore Asrani
631570 | 00631570 - Mr. AKSHAY SIDDHARTH BHANGE
631572 | 00631572 - Mr. Pinkesh Navinbhai Shah
631574 | 00631574 - Mr. Akshay Sanjay Shimpi
631571 | 00631571 - Ms. Vrushali Vasant Jadhav
S-262 | S-262 - Mr. MEHUL KAILASH GOSWAMI
631577 | 00631577 - Mrs. Anjali Ganesh Hanumandla
631576 | 00631576 - Mr. Paruchuri Shankar
631578 | 00631578 - Mr. Gokul Prathyush Kolla
631584 | 00631584 - Mr. SONAL YADAV WAGHMARE
631585 | 00631585 - Mr. MD SADDAM Shaik Abdul Latif HUSSAIN
631580 | 00631580 - Mr. AKSHAY ANANDA KOKARE
S-264 | S-264 - Mr. Avatar Shiv Singh Chauhan
631583 | 00631583 - Mr. Deepesh Singh
I-051 | I-051 - Mr. Dhruv Deepesh Krishnan
S-268 | S-268 - Mr. SHIRISH SUBHASH BHAMARE
S-269 | S-269 - Mr. Rakesh Kumar
S-266 | S-266 - Mr. Shivakumar Devnoor
631592 | 00631592 - Mr. Ajitesh Kumar
631594 | 00631594 - Mr. SARVESH GANGARAM KUWAR
S-270 | S-270 - Mr. Deepak Nityanand Chawla
S-267 | S-267 - Mr. Aniket S
R-109 | R-109 - Mr. Partha Sarathi Ray
631648 | 00631648 - Ms. Srinidhi Sampathirao
631599 | 00631599 - Ms. Nikita Arvind Yedre
631601 | 00631601 - Mr. Siddhesh Dattatraya Bachal
631602 | 00631602 - Mr. SWAMY A R
631603 | 00631603 - Mr. Ganesh Prakash
S-276 | S-276 - Mr. Himanshu Jain
631604 | 00631604 - Ms. Nikita Kaushik
631605 | 00631605 - Mr. Abhijeet Dinkar Madage
630947 | 00630947 - Mrs. Shital Nitin Hingmire
S-047 | S-047 - Mr. K M Maxwell Richard
630948 | 00630948 - Mr. Naved Aslam Khan
630949 | 00630949 - Mrs. Ashwini Patil
630997 | 00630997 - Mr. Abhishek Sahu
630971 | 00630971 - Mr. Shekhar Shinde
630987 | 00630987 - Ms. SABINA BISWAL
630951 | 00630951 - Mr. Apurv Milan Patil
630955 | 00630955 - Ms. Sharayu Rajhans Ambadkar
630957 | 00630957 - Ms. Sakshi Gajendra Nikam
630965 | 00630965 - Mr. Charchit Kumar Dash
630980 | 00630980 - Mr. Jalindar Walunj
630989 | 00630989 - Mr. Chirag Navinchandra Bhandari
630977 | 00630977 - Mr. Kripa Singh
630978 | 00630978 - Mr. Durgesh Patil
630983 | 00630983 - Mr. Prasad Phadtare
631005 | 00631005 - Mr. RAHUL BHOGI
631033 | 00631033 - Mr. Pankaj Jaiswal
631031 | 00631031 - Mr. Karthik Purad
631038 | 00631038 - Mr. Rahul Singhal
631046 | 00631046 - Mr. Rahul Patil
S-060 | S-060 - Mr. Avadhut Mahadik
631043 | 00631043 - Mr. Kulandai Yesu
631049 | 00631049 - Mr. Arif Shaikh
631041 | 00631041 - Mr. Sachin Mohod
631056 | 00631056 - Mr. Pranit Marge
S-064 | S-064 - Mr. Charan Kumar
631058 | 00631058 - Mr. Vishal Chippa
631070 | 00631070 - Mr. Ganesh Chalak
631074 | 00631074 - Mr. Vishwajit Durgude
631076 | 00631076 - Mr. Sateesh Lunavathu
631084 | 00631084 - Mr. Deepak Narayan Wagh
631171 | 00631171 - Mr. Harshal Chandrashekhar Gite
631172 | 00631172 - Mr. Mahesh Shamsundar Hatle
631173 | 00631173 - Ms. Mayuri Daulat Patil
631181 | 00631181 - Mr. Nishant Srinivasan
631161 | 00631161 - Mr. Narendra Kumar Munugoti
631165 | 00631165 - Mr. Ashutosh Sandhya Kulkarni
631086 | 00631086 - Ms. Rashmi sinha
631088 | 00631088 - Mr. Dheeraj Bhardwaj
631090 | 00631090 - Ms. Lipika Nanda
631091 | 00631091 - Mr. Sumit kumar Vishwakarma
631094 | 00631094 - Ms. Silpa Dash
631109 | 00631109 - Mr. Sameer Wasudeo Gurnule
631100 | 00631100 - Mr. Rakesh kumar Rout
631101 | 00631101 - Mr. Pankaj kumar
631191 | 00631191 - Mr. Ratna Kamalakar Kaki
631192 | 00631192 - Mr. Rahul Singh
S-115 | S-115 - Mr. Krishna Choudhary
631224 | 00631224 - Mr. Prashant D Jagdale
631289 | 00631289 - Mr. Ronak Suresh Jain
S-147 | S-147 - Mr. Satish Bhakth
S-148 | S-148 - Mr. Shivraj Singh
631283 | 00631283 - Mr. Mahendra Hindurav Jadhav
631296 | 00631296 - Mr. Pramod Kumar Sahoo
631123 | 00631123 - Mr. Vikash Devuri
631121 | 00631121 - Mr. Harish chander Joshi
631134 | 00631134 - Mr. Saurabh Sharma
631135 | 00631135 - Mr. Ved Sinha
631136 | 00631136 - Mr. Samad Muhammed
631140 | 00631140 - Mr. Udayakiran Kodeboina
S-080 | S-080 - Mr. CHINMAYA KUMAR JENA
631147 | 00631147 - Mr. MOHAMMAD ABUZER
631148 | 00631148 - Mr. Deepak Vasant Jadhav
631156 | 00631156 - Mr. NIKHIL SHASHIKANT NARKHEDE
631138 | 00631138 - Mr. Nassim Akhtar
631167 | 00631167 - Mr. Pranav Dinkar Gawade
631168 | 00631168 - Mr. AKSHAY KISHOR BAIRAGI
631144 | 00631144 - Mr. Pavan Kumar
631149 | 00631149 - Mr. Srinivas Moturi
631600 | 00631600 - Mr. RUBAN PRASAD
S-273 | S-273 - Mr. RISHABH CHANDRAKANT BHANDARI
631610 | 00631610 - Mr. Pratik Naresh Mandlik
631613 | 00631613 - Mr. venkatesh Lankapalli
631606 | 00631606 - Mr. Chirag Prasanna
S-277 | S-277 - Mr. Sunil Dhariwal
631607 | 00631607 - Mr. Nikhil Mekala Bhoomaiah
631609 | 00631609 - Ms. Aafreen Mohd. Aasim Shaikh
R-112 | R-112 - Mr. PADINHARE VALIYAVEEDU AFRAZ
S-280 | S-280 - Mr. Rahul Ranoji Jadhav
S-281 | S-281 - Mr. Narender Umapathi Mamidi
631615 | 00631615 - Mr. Himanshu Gupta
631619 | 00631619 - Mr. Akshay Mahendra Rokade
631622 | 00631622 - Mrs. Gurleen Kaur
631623 | 00631623 - Mr. Sayed zegam abbass Taqvi
631625 | 00631625 - Mrs. Nikita Singh
631618 | 00631618 - Mr. Swapnil Santosh Purkar
631624 | 00631624 - Mr. Atul Kumar Dubey
S-291 | S-291 - Mrs. SHILPI PARIHAR
S-292 | S-292 - Mr. Kamal Singh
S-315 | S-315 - Mr. Stephen Dsouza
S-284 | S-284 - Mr. SANDESH SANTOSH VEKHANDE
631630 | 00631630 - Mr. Akshay Pandurang Hore
631634 | 00631634 - Mr. Ameen Mohiddin Shikalgar
631635 | 00631635 - Mr. Nischal Yalamaddi
631636 | 00631636 - Mr. Varun Itagampali
S-296 | S-296 - Mr. Ram Gupta
S-287 | S-287 - Mr. Gajanan Shivram Tagadpalle
631620 | 00631620 - Mr. TEJAS DEEPAK NAIK
631626 | 00631626 - Mr. Adarsh Ranjan
S-290 | S-290 - Mr. TANUJ DAHIYA
631628 | 00631628 - Mr. Tanmay Shridhar Parab
631631 | 00631631 - Mr. Onkar Ashish Kawde
631632 | 00631632 - Mr. Nikhil Jayendra Dandekar
631633 | 00631633 - Mr. Yash Pareshbhai Sheth
S-294 | S-294 - Mr. JITESH KUSHWAHA
631178 | 00631178 - Ms. Merlin Tomy
S-098 | S-098 - Mr. Parag Sinkar
S-109 | S-109 - Mr. Sridhar Yamala
631196 | 00631196 - Mr. Nikhil Patil
631202 | 00631202 - Mr. Akshay Harichandan
631227 | 00631227 - Mr. Dharmakumar Barrey
631221 | 00631221 - Mr. Prashant Vadlakonda
631228 | 00631228 - Mr. Pravin Shivaji Wahulkar
631235 | 00631235 - Mr. KAHNU CHARAN SAHU
S-123 | S-123 - Mr. Biltu Karjee
631247 | 00631247 - Mr. Dilip Kumar Kapa
631293 | 00631293 - Mr. Deepak Madishetti
631304 | 00631304 - Mr. Jayasurya Lakkoju
631294 | 00631294 - Mr. Sadanand Anant Sarmalkar
631295 | 00631295 - Mr. Sanjay Abhiman Patil
631299 | 00631299 - Mr. Yogeshkumar Ashokbhai Nai
631301 | 00631301 - Mr. Vinay Verma
631310 | 00631310 - Mr. Syed Taiyab Mahmood Hashmi
S-163 | S-163 - Mr. Mukesh Kumar Yadav
631318 | 00631318 - Mr. KODAVALURU NIKHIL REDDY
631319 | 00631319 - Mr. AHEMAD BILAL
631245 | 00631245 - Mr. Amrit Kumar Swain
631248 | 00631248 - Mr. Mangesh Vinayakrao Chitale
631256 | 00631256 - Mr. Aniket Shivram Karmalkar
631257 | 00631257 - Mr. Rupesh Vairal
631241 | 00631241 - Mr. Ashish Kumar Ranjan
631244 | 00631244 - Mr. prasant kumar Gopalkrishna Dash
631265 | 00631265 - Mr. Hrishikesh Pravin Nikam
631266 | 00631266 - Mr. Manikandan shanmugam
631246 | 00631246 - Mr. Harshad Sureshrao Dhande
631255 | 00631255 - Mr. Arun Nana Patil
S-138 | S-138 - Mr. Chirag Ashokkumar Shah
631259 | 00631259 - Mr. Chetan Chandrashekhar Birari
631263 | 00631263 - Mr. Yogesh K Mhadolkar
631268 | 00631268 - Mr. Shivraj More
631254 | 00631254 - Mr. Parvathaneni Srinivasulu
S-139 | S-139 - Mr. Abhinandan ABAP
631269 | 00631269 - Mr. Vivek Ugare
631276 | 00631276 - Mr. Vaibhav Dagadu Karale
631275 | 00631275 - Mr. Akshay Rajendra Gavali
631279 | 00631279 - Mr. AKASH KUMAR SAHU
S-146 | S-146 - Mr. Veeranjaneyulu Valluri
631282 | 00631282 - Ms. Archana Kailas Hire
631286 | 00631286 - Mr. Niket Ravindra Devkar
631287 | 00631287 - Mr. Gaurav Kumar
S-173 | S-173 - Ms. PRADNYA VISHWASRAO PATIL
631329 | 00631329 - Ms. Priyanka Arun Gaikar
631332 | 00631332 - Mr. SATISH PANCHADA
631334 | 00631334 - Mr. VENU JANGA
I-035 | I-035 - Mr. Vijay Sadashiv Salvi
S-171 | S-171 - Mr. Amarjeet Singh
631325 | 00631325 - Mr. Arijeet Chatterjee
631321 | 00631321 - Mr. Vinay Kumar Rudra
631322 | 00631322 - Mr. Harshal Prakash Patil
631328 | 00631328 - Mr. Sharanbasappa S
631330 | 00631330 - Mr. Sajid Biram Shaikh
631331 | 00631331 - Mr. Navin Kumar Pathak
631333 | 00631333 - Mr. Premjeet Milind Sakolkar
631337 | 00631337 - Mr. Prakash Raghunath Sutar
631341 | 00631341 - Mrs. Monica Swapnil Dhuri
I-038 | I-038 - Mr. kishor barkya Tambe
631348 | 00631348 - Mr. Ritesh Nikam
631353 | 00631353 - Mr. Nilesh Sanjay Shelar
S-183 | S-183 - Mr. RITESH PAL
631366 | 00631366 - Mr. THATAVARTHI SATYA RAVINDRA
631338 | 00631338 - Mr. Jeetendra Srichand Kshatriya
631342 | 00631342 - Mr. Mayur Rajesh Pansare
631345 | 00631345 - Mr. Prashant Ganapati Kurse
631346 | 00631346 - Mr. Naresh Uggera
631349 | 00631349 - Ms. Shamal Ramesh Jamadar
631369 | 00631369 - Mr. RAJ KUMAR KUNDU
631370 | 00631370 - Mr. Malagoud Sidagoud Patil
631376 | 00631376 - Ms. Aditi Harish Sharma
631351 | 00631351 - Mr. Rishi Kant Kumar
S-186 | S-186 - Mr. Prason Kumar
631358 | 00631358 - Mr. Harish Kisan Thakare
631356 | 00631356 - Mr. MOHAN REDDY MOGILI
631357 | 00631357 - Ms. Salma Sultana
631363 | 00631363 - Mr. Ashok Kumar Vishwakarma
631364 | 00631364 - Mr. NAVEEN KUMAR DAMODARAM
S-198 | S-198 - Mr. Aditya Shekhawat
631371 | 00631371 - Mr. Mohammed Abdul Thamjeeth Athahar
631381 | 00631381 - Mr. Sreehari C
S-199 | S-199 - Mr. DHANANJAY RAMCHANDRA KATRE
S-200 | S-200 - Mr. Mahipal Singh Devda
631384 | 00631384 - Mr. Suraj Siddharth Patil
631388 | 00631388 - Ms. DEEPIKA GUPTA
631389 | 00631389 - Mr. Hrishikesh Amarnath Bagul
631387 | 00631387 - Mr. Izharuddin Azeemuddin Quazi
631392 | 00631392 - Ms. Riya Routray
631395 | 00631395 - Mr. Rahul Hanumant Kumbhar
631396 | 00631396 - Mr. MUKESH UDAYBHAN PRAJAPATI
631397 | 00631397 - Mr. RITIKRAJ SINGH
631394 | 00631394 - Mr. Vishal Chaudhary
631402 | 00631402 - Mr. PRABHU SHIVAJI PANZADE
631403 | 00631403 - Mr. SHUBHAM GARG
S-204 | S-204 - Mrs. Vrushalee sharma
631410 | 00631410 - Mr. Zaid Surve
631398 | 00631398 - Mr. Arpit Ashok Agarwal
631399 | 00631399 - Mr. Gaurav Pimple
631405 | 00631405 - Mr. Ashish Amol Dagare
631407 | 00631407 - Mrs. RINKU PAUL
631411 | 00631411 - Ms. Sumita Maji
631413 | 00631413 - Mr. Anurag Mahadeo Dhepe
631415 | 00631415 - Mr. Namdev Sakharam Choure
631416 | 00631416 - Mr. SUMIT RAJESH JAIN
631417 | 00631417 - Mr. Darshil Tejkaran Bhavsar
631418 | 00631418 - Mr. Anurag Kumar Singh
S-207 | S-207 - Mr. Ravi Kiran Puppala
S-208 | S-208 - Mr. Nilesh Dnyaneshwar Wawge
S-206 | S-206 - Mr. Yadunath Singh
R-102 | R-102 - Mr. Ashish Rai
631422 | 00631422 - Mr. JAGADISH KUNA
631424 | 00631424 - Mr. VIKASH KUMAR PANDIT
S-209 | S-209 - Mr. NIKHIL VIJENDRA MALPE
631429 | 00631429 - Mr. SURENDRA NADHA REDDY MUTUKUNDU
631434 | 00631434 - Mr. Harshal Bhaidas Patil
631435 | 00631435 - Mr. Kalpesh Jagdish Patel
S-218 | S-218 - Mr. PANKAJ TRIPATHI
631427 | 00631427 - Mr. Shivam Sahal
631431 | 00631431 - Mr. SUMIT ANIL SINGH
631432 | 00631432 - Mr. ABHIJEET BALASAHEB PUND
631437 | 00631437 - Mr. KUNAL Nalawade
631445 | 00631445 - Mr. AVINASH SUSHMA AWADHIYA
S-224 | S-224 - Mr. Sanket Yadav
631442 | 00631442 - Mr. Dnyaneshwar M Bhavikatti
631443 | 00631443 - Mr. Habel Issac Jacob
S-220 | S-220 - Mr. SWAROOP SINGH
631466 | 00631466 - Mrs. KOMAL VIVEK JAVERIA
R-104 | R-104 - Mr. Chetan Anil Patil
631471 | 00631471 - Ms. Pooja Dattatry khot
S-222 | S-222 - Mr. Yuvraj Singh Shekhawat
631454 | 00631454 - Mr. Chandrakant Vikram Wagh
631462 | 00631462 - Mr. Milind Bhalchandra Erande
631468 | 00631468 - Ms. Shweta Singh
631456 | 00631456 - Mr. SAGAR SUNIL MORE
631474 | 00631474 - Mr. JAGDISH TEJABHAI BARVADIYA
631475 | 00631475 - Mr. Asif Manauwar
631457 | 00631457 - Mr. MD WASIM AKRAM
631458 | 00631458 - Mr. SHUBHAM PRAMOD SANGOLE
631461 | 00631461 - Ms. Sumaiya Shaikh
S-229 | S-229 - Mr. Abhishek Dayanand Kamble
631469 | 00631469 - Mr. Nikunj Daga
631476 | 00631476 - Mr. Amit Kishorrao Kalaskar
631478 | 00631478 - Mr. Susanta Kumar Nayak
631479 | 00631479 - Ms. Meghna Prusty
631483 | 00631483 - Mr. Sandip Mohan Shinde
S-233 | S-233 - Mr. ANKIT MORE
631481 | 00631481 - Ms. Saeema Parveen
631482 | 00631482 - Mr. Laxmikant Bajarang Zirpe
631484 | 00631484 - Mrs. Honey Bapna
631486 | 00631486 - Mr. CHALLA VIGHNESWARA RAO
631489 | 00631489 - Mr. Parveen Kaushik
S-240 | S-240 - Mr. Karanpal Singh Chouhan
631485 | 00631485 - Mr. SHANTANU SATISH GHODKE
S-237 | S-237 - Mr. Sandeep Parida
631487 | 00631487 - Mr. Shubham Dhanraj Dhamse
631590 | 00631590 - Ms. Darshini Sunder Pillai
631491 | 00631491 - Mr. SUMANT KUMAR BHARTI
631496 | 00631496 - Mr. Shreetam Tarenia
631501 | 00631501 - Mr. Ketan Vishwas Deshmukh
631505 | 00631505 - Mr. Ravi Madhesiya
631507 | 00631507 - Mr. Mayur Milind Joshi
631500 | 00631500 - Mr. Nakul Prabhakar Kamone
631524 | 00631524 - Mr. ABHIJEET RAIPURE
631525 | 00631525 - Mr. KALLEM UMAKANTH GOUD
631528 | 00631528 - Mr. Pranav Arvind Kakani
631504 | 00631504 - Ms. Arpita Gupta
631521 | 00631521 - Mr. YEDDULA VENKATA SIVA REDDY
631511 | 00631511 - Mrs. Anjali Sanger
631512 | 00631512 - Mr. MANGA VENKATA RAO
631510 | 00631510 - Mr. Yatin Sunil Pathak
631514 | 00631514 - Mr. Ramesh Ramkripal Gupta
631515 | 00631515 - Mr. SANDEEP KUMAR SWAIN
631518 | 00631518 - Mr. Vicky Meena
631519 | 00631519 - Mr. Akshay Sukhadeo Dhumal
631520 | 00631520 - Mr. Muneeb Ikram Khan
631530 | 00631530 - Mr. RAJA NARASIMHA MURTHY ARDHANI
631532 | 00631532 - Mr. Rushikesh Rajendra Kangane
631533 | 00631533 - Mr. G CHAKRAVARTHY
631537 | 00631537 - Mr. Amrendra Pratap Singh
S-245 | S-245 - Mr. Mahipal Singh Mojawat
631538 | 00631538 - Mr. Gokul K
631534 | 00631534 - Mr. Sameer Parab
R-107 | R-107 - Mr. PARAG PANDURANG MAHADIK
S-247 | S-247 - Mr. Jaydeep Singh Rathore
631542 | 00631542 - Mr. Karthik Chowdary Pendurthi
631543 | 00631543 - Mr. Syed Abdul Rizwaan
631545 | 00631545 - Mr. RAHUL BHOWMIK
631547 | 00631547 - Mr. Rohit Sudhakar Mane
I-048 | I-048 - Mr. Aditya Anirvan
631540 | 00631540 - Mr. Pavan Kalyan
631544 | 00631544 - Ms. Himani Aditee
631546 | 00631546 - Mr. Vedant Nitin Bhagwat
631548 | 00631548 - Mr. Nilesh Mohan Nikam
631553 | 00631553 - Mr. PANKAJ DATTATRAYA GHAWADE
S-252 | S-252 - Mr. Harshal Bhikan Patil
631556 | 00631556 - Mr. Dattatray Bhausaheb Godse
631558 | 00631558 - Mr. Hriday Das
631560 | 00631560 - Mr. Gautam Sen
631552 | 00631552 - Mr. Kunal Vinod Kulkarni
631554 | 00631554 - Ms. Shriya Sinha
631555 | 00631555 - Mr. Shrikant Ashokrao Alone
631563 | 00631563 - Mr. Pradeep Rawat
631566 | 00631566 - Mr. ANKIT Ganesh Ram MEHAR
631557 | 00631557 - Mr. Govinda Rajkumar Singhwal
631559 | 00631559 - Mr. Adnan Ejaz Mundewadi
631562 | 00631562 - Ms. Siddhi Sharad Mhamunkar
S-256 | S-256 - Mr. Sangramsinha Balavant Chougale
S-295 | S-295 - Mr. Rahul Kumawat
631643 | 00631643 - Mr. Kritik Mayur Joshi
631644 | 00631644 - Mr. Vishal Santosh Wadekar
S-306 | S-306 - Mr. Shivraj Singh Shekhawat
S-299 | S-299 - Mr. Alok Kumar Dubey
631653 | 00631653 - Mr. PRATIK BHOJRAJ PATIL
631657 | 00631657 - Mr. Purushottam Annasaheb Taur
631661 | 00631661 - Mr. Shubham Purushottam Parashar
S-309 | S-309 - Mr. Prajwal Satish Aher
631638 | 00631638 - Mr. Kaushal Sharma
631641 | 00631641 - Mr. Harshad Vivek Sawant
S-305 | S-305 - Mr. Jaydev Gajjar
631649 | 00631649 - Mr. Soum Gupta
631645 | 00631645 - Mr. Vaishnav Ganesh Dalvi
S-302 | S-302 - Mrs. BHARTI KUMARI
S-304 | S-304 - Mr. Alok RAJAK
S-308 | S-308 - Mr. Abhishek Kumar Upadhyay
631675 | 00631675 - Mr. Roshan Hande
631642 | 00631642 - Ms. Komal Anant Parab
631646 | 00631646 - Mr. Deepak Baviskar
631651 | 00631651 - Mr. VIKAS SINGH
S-307 | S-307 - Mr. Kiran Tetgure
631664 | 00631664 - Mr. Mohammad Monis
631668 | 00631668 - Mr. Rohit Kishor Thakare
I-050 | I-050 - Mr. Kartik Jha
631652 | 00631652 - Mr. JAY RAJENDRA RAUT
631654 | 00631654 - Mr. Salah Raeesuddin Shaikh
631655 | 00631655 - Mr. Shakir Iqbal Momin
631658 | 00631658 - Mr. Sahil Jagannath Pawar
631659 | 00631659 - Mr. Rushikesh Patil
631660 | 00631660 - Mr. Vipin Patankar
631662 | 00631662 - Mr. Mohammed Said Makarani
631663 | 00631663 - Mr. JAGADEESWARA REDDY CHENNURU
S-310 | S-310 - Mr. Rithik Jamana Shankar Chaturvedi
631667 | 00631667 - Mr. Abhishek Cheetirala
S-317 | S-317 - Mr. Vikas Kumar Singh
631669 | 00631669 - Mr. K.Udit Prasad
631677 | 00631677 - Mr. Kumar Anoop
631680 | 00631680 - Mr. Karan Jha
631681 | 00631681 - Mr. Mahesh Balavant Padaval
631686 | 00631686 - Mr. Debasish Datta
631688 | 00631688 - Mr. Durga Prasad PenuBothu
S-311 | S-311 - Mr. Mohan Reddy
S-312 | S-312 - Mr. Bharat Kumar Nagda
S-313 | S-313 - Mr. Ajinkya Sunil Bhaskar
631671 | 00631671 - Mrs. Kiran Mitthilesh Gupta
I-052 | I-052 - Ms. Shrutika Dilip Mudgalkar
631665 | 00631665 - Mr. Prajyot Pradeep Yerunkar
631674 | 00631674 - Mr. Yogesh Ranglal Katre
631684 | 00631684 - Mr. Kiran Ravindra Shelke
631687 | 00631687 - Mr. Ashutosh Tiwari
631694 | 00631694 - Ms. Swati Patil
S-324 | S-324 - Mr. Lokendra Singh
631705 | 00631705 - Mr. Lakkireddy Umamaheswarreddy
631666 | 00631666 - Mr. Zinit Bhupeshchandra Gautam
631672 | 00631672 - Mr. UMESH CHANDRA EMBETI
631673 | 00631673 - Mr. Malairaman C
R-115 | R-115 - Mr. Sumesh Mehta
631692 | 00631692 - Mr. Meher Chand Sirigiri
631678 | 00631678 - Mr. MAHESH CHANDRA MULUKUDITI
631693 | 00631693 - Mrs. Chitranshi Sharma
S-320 | S-320 - Mr. Akhil Kumar
S-322 | S-322 - Mr. Alok Sharma
S-323 | S-323 - Mr. Manohar Kornapalli
631697 | 00631697 - Mr. SUDESH PANDHARINATH KARNIK
631679 | 00631679 - Mr. ANIL NARAYAN SHINDE
631691 | 00631691 - Mr. Utkarsh Raj Chandra
631695 | 00631695 - Mrs. Shubhangi Pravin Ligade
631701 | 00631701 - Mr. Jaiveer Singh
S-325 | S-325 - Mr. Avinash P
631718 | 00631718 - Mr. Deepak Chatur Thakare
631682 | 00631682 - Mr. Ketan Joshi
631683 | 00631683 - Ms. Preethi J
S-319 | S-319 - Mr. Peddi Sivasurya Kishore Kumar
631685 | 00631685 - Ms. Khushboo Kumari
R-116 | R-116 - Mr. Bindumadhav Anant Ambike
S-321 | S-321 - Ms. Deepti Ketan Joshi
631696 | 00631696 - Mr. Shubham Patidar
631702 | 00631702 - Mrs. Pratibha Anilkumar Mishra
631707 | 00631707 - Mr. Rajas Sunil Chaudhari
S-326 | S-326 - Mr. Manmohan Singh
631708 | 00631708 - Mr. Yash Sanjay Pawar
631710 | 00631710 - Ms. Snehal Anil Jadhav
R-117 | R-117 - Mr. Amarendar Kumar
631699 | 00631699 - Mr. Prashant Dutta
631703 | 00631703 - Mr. Ketan Deshpande
631704 | 00631704 - Mr. Suman Acharyya
S-327 | S-327 - Mrs. Sailee A Bhoir
631709 | 00631709 - Mr. Ashwajit Purushottamrao Bansod
631711 | 00631711 - Mr. Mayur Vikas Kawale
631712 | 00631712 - Mr. Yatin Majgaonkar
S-328 | S-328 - Mr. Sarvesh Kumar
631713 | 00631713 - Mr. Tushar Pandurang Patil
631714 | 00631714 - Mrs. Nayan Jayshankar Hingmire
631715 | 00631715 - Mr. Akshay Anil Warang
631717 | 00631717 - Mr. Shivamsingh Narendra Chouhan
I-053 | I-053 - Mr. Pranav Dattatraya Borate
631719 | 00631719 - Mr. Mahesh Wakode
S-329 | S-329 - Mr. Shehjad Shaikh
S-330 | S-330 - Mr. Dhananjay Katre
631716 | 00631716 - Mr. Nilesh Laxman Jagtap
631720 | 00631720 - Mr. Lalit Asnani

## ABAP Consultant Master Data
Emp_Code | Emp_Name
630579 | 00630579 - Mr. Simranjeet Singh Sond
630665 | 00630665 - Mr. Mohana Krishna Kandhi
630841 | 00630841 - Mr. Kuna Srujan
630016 | 00630016 - Mr. Santosh Choudhary
630301 | 00630301 - Mr. Vinay Ramchandra Singh
630530 | 00630530 - Mr. Madhu Vijaykumar Manchikatla
630864 | 00630864 - Mr. Gaurav Nimbulkar
630828 | 00630828 - Mr. Vijay Mahajan
630946 | 00630946 - Mr. NIRAJ PRATAP CHAVAN
631577 | 00631577 - Mrs. Anjali Ganesh Hanumandla
630947 | 00630947 - Mrs. Shital Nitin Hingmire
630949 | 00630949 - Mrs. Ashwini Patil
630951 | 00630951 - Mr. Apurv Milan Patil
630955 | 00630955 - Ms. Sharayu Rajhans Ambadkar
630957 | 00630957 - Ms. Sakshi Gajendra Nikam
S-060 | S-060 - Mr. Avadhut Mahadik
S-064 | S-064 - Mr. Charan Kumar
631070 | 00631070 - Mr. Ganesh Chalak
631171 | 00631171 - Mr. Harshal Chandrashekhar Gite
631172 | 00631172 - Mr. Mahesh Shamsundar Hatle
631173 | 00631173 - Ms. Mayuri Daulat Patil
631165 | 00631165 - Mr. Ashutosh Sandhya Kulkarni
S-115 | S-115 - Mr. Krishna Choudhary
S-147 | S-147 - Mr. Satish Bhakth
631135 | 00631135 - Mr. Ved Sinha
631136 | 00631136 - Mr. Samad Muhammed
631138 | 00631138 - Mr. Nassim Akhtar
631167 | 00631167 - Mr. Pranav Dinkar Gawade
631168 | 00631168 - Mr. AKSHAY KISHOR BAIRAGI
631144 | 00631144 - Mr. Pavan Kumar
631149 | 00631149 - Mr. Srinivas Moturi
631606 | 00631606 - Mr. Chirag Prasanna
S-281 | S-281 - Mr. Narender Umapathi Mamidi
631615 | 00631615 - Mr. Himanshu Gupta
S-291 | S-291 - Mrs. SHILPI PARIHAR
S-284 | S-284 - Mr. SANDESH SANTOSH VEKHANDE
S-296 | S-296 - Mr. Ram Gupta
631626 | 00631626 - Mr. Adarsh Ranjan
631628 | 00631628 - Mr. Tanmay Shridhar Parab
631178 | 00631178 - Ms. Merlin Tomy
S-109 | S-109 - Mr. Sridhar Yamala
631196 | 00631196 - Mr. Nikhil Patil
631221 | 00631221 - Mr. Prashant Vadlakonda
S-123 | S-123 - Mr. Biltu Karjee
631304 | 00631304 - Mr. Jayasurya Lakkoju
631265 | 00631265 - Mr. Hrishikesh Pravin Nikam
S-139 | S-139 - Mr. Abhinandan ABAP
S-146 | S-146 - Mr. Veeranjaneyulu Valluri
S-171 | S-171 - Mr. Amarjeet Singh
631333 | 00631333 - Mr. Premjeet Milind Sakolkar
S-183 | S-183 - Mr. RITESH PAL
631342 | 00631342 - Mr. Mayur Rajesh Pansare
631349 | 00631349 - Ms. Shamal Ramesh Jamadar
S-186 | S-186 - Mr. Prason Kumar
631356 | 00631356 - Mr. MOHAN REDDY MOGILI
S-198 | S-198 - Mr. Aditya Shekhawat
631392 | 00631392 - Ms. Riya Routray
631410 | 00631410 - Mr. Zaid Surve
631415 | 00631415 - Mr. Namdev Sakharam Choure
631416 | 00631416 - Mr. SUMIT RAJESH JAIN
S-206 | S-206 - Mr. Yadunath Singh
S-209 | S-209 - Mr. NIKHIL VIJENDRA MALPE
631427 | 00631427 - Mr. Shivam Sahal
631445 | 00631445 - Mr. AVINASH SUSHMA AWADHIYA
S-220 | S-220 - Mr. SWAROOP SINGH
S-222 | S-222 - Mr. Yuvraj Singh Shekhawat
631468 | 00631468 - Ms. Shweta Singh
631457 | 00631457 - Mr. MD WASIM AKRAM
631458 | 00631458 - Mr. SHUBHAM PRAMOD SANGOLE
631478 | 00631478 - Mr. Susanta Kumar Nayak
631483 | 00631483 - Mr. Sandip Mohan Shinde
631491 | 00631491 - Mr. SUMANT KUMAR BHARTI
631505 | 00631505 - Mr. Ravi Madhesiya
631507 | 00631507 - Mr. Mayur Milind Joshi
631504 | 00631504 - Ms. Arpita Gupta
631510 | 00631510 - Mr. Yatin Sunil Pathak
631518 | 00631518 - Mr. Vicky Meena
S-247 | S-247 - Mr. Jaydeep Singh Rathore
631542 | 00631542 - Mr. Karthik Chowdary Pendurthi
631546 | 00631546 - Mr. Vedant Nitin Bhagwat
631548 | 00631548 - Mr. Nilesh Mohan Nikam
S-252 | S-252 - Mr. Harshal Bhikan Patil
631556 | 00631556 - Mr. Dattatray Bhausaheb Godse
S-295 | S-295 - Mr. Rahul Kumawat
S-309 | S-309 - Mr. Prajwal Satish Aher
631638 | 00631638 - Mr. Kaushal Sharma
S-304 | S-304 - Mr. Alok RAJAK
S-308 | S-308 - Mr. Abhishek Kumar Upadhyay
S-307 | S-307 - Mr. Kiran Tetgure
631668 | 00631668 - Mr. Rohit Kishor Thakare
I-050 | I-050 - Mr. Kartik Jha
S-310 | S-310 - Mr. Rithik Jamana Shankar Chaturvedi
631669 | 00631669 - Mr. K.Udit Prasad
631687 | 00631687 - Mr. Ashutosh Tiwari
S-324 | S-324 - Mr. Lokendra Singh
631695 | 00631695 - Mrs. Shubhangi Pravin Ligade
S-325 | S-325 - Mr. Avinash P
631717 | 00631717 - Mr. Shivamsingh Narendra Chouhan