## ABAP Objectr Tracker Template
SrNo | Module | Interface | Development Description | Scope | FRICE Category | Priority | PriorityType | Complexity | Functional Consultant | RGS |  |  |  | FS |  | ABAP Development |  |  |  | HBT Testing |  | CTM Testing |  | UAT Sign Off | Go-Live Planned Date (dd.mm.yyyy) | Reusability
[10 empty] | Planned Preparation Start Date (dd.mm.yyyy) | Planned Preparation Finish Date (dd.mm.yyyy) | Planned Submission Date (dd.mm.yyyy) | Planned Approval Date (dd.mm.yyyy) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned ABAP Consultant | Duration (Days) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned Start Date (dd.mm.yyyy) | Planned Finish Date (dd.mm.yyyy) | Planned Date (dd.mm.yyyy) |  | Reusable Client Name | Status | Additional Efforts (In Days) | Percentage | Remarks/ Details | Custom Tcode
1 | SAP SD | open text | WBS, Network, Activity, Mileston Upload Program | SOW | Conversion | 1 | SIT | Simple | S-313 / Mr. Ajinkya Sunil Bhaskar | 28.02.2025 | 28.02.2025 | 28.02.2025 | 28.02.2025 | 01.03.2025 | 01.03.2025 | 00631196 / Mr. Nikhil Patil | 1 | 02.03.2025 | 02.03.2025 | 03.03.2025 | 03.03.2025 | 04.03.2025 | 04.03.2025 | 05.03.2025 | 06.03.2025 | Test | WIP | 0.5 | 10 | Testing | T0054
2 | SAP SD | open text | BPO Upload Program | SOW | Conversion | 1 | Go Live | Simple | S-313 / Mr. Ajinkya Sunil Bhaskar | 28.02.2025 | 28.02.2025 | 28.02.2025 | 28.02.2025 | 01.03.2025 | 01.03.2025 | 00631196 / Mr. Nikhil Patil | 1 | 02.03.2025 | 02.03.2025 | 03.03.2025 | 03.03.2025 | 04.03.2025 | 04.03.2025 | 05.03.2025 | 06.03.2025
3 | SAP SD | open text | Unit Cost Plan Upload Program | SOW | Conversion | 2 | Go Live | Simple | S-313 / Mr. Ajinkya Sunil Bhaskar | 28.02.2025 | 28.02.2025 | 28.02.2025 | 28.02.2025 | 01.03.2025 | 01.03.2025 | 00631196 / Mr. Nikhil Patil | 1 | 02.03.2025 | 02.03.2025 | 03.03.2025 | 03.03.2025 | 04.03.2025 | 04.03.2025 | 05.03.2025 | 06.03.2025
4 | SAP SD | open text | Budget Approval Procedure & document attachment compulsary | SOW | Enhancement | 2 | SIT | Complex | S-313 / Mr. Ajinkya Sunil Bhaskar | 28.02.2025 | 28.02.2025 | 28.02.2025 | 28.02.2025 | 01.03.2025 | 01.03.2025 | 00631196 / Mr. Nikhil Patil | 1 | 02.03.2025 | 02.03.2025 | 03.03.2025 | 03.03.2025 | 04.03.2025 | 04.03.2025 | 05.03.2025 | 06.03.2025

## Module Master Data
ModuleId | ModuleDesc
6 | .Net
115 | .NET Web Designer
66 | Accounts & Finance
108 | Admin
113 | Bid management
38 | BIM_2-3D
39 | BIM_5D
37 | BIM_Primavera_Unifier
100 | Business Analyst
118 | Business Development
70 | Business Development - Govt.
67 | Business Development - Pvt.
63 | Contract Manager
28 | CPI
46 | CRM
101 | CRM Technical
89 | Customer Success
99 | DBA - Database Admin
74 | Delivery
79 | DMS (Non SAP)
47 | Doc. Controller
106 | E-Office
122 | Executive - Contracts
116 | Executive - HR
124 | Executive HR 1
27 | FIORI
34 | FLM
119 | Graphic Designer
76 | Head - COE
61 | Head - Delivery
123 | Head – HR
41 | Helpdesk
102 | HR Manager
78 | Human Resource
112 | Human resource -Recruitment
29 | IDM
120 | Inside Sales
30 | ISU
87 | IT Support & Vendor Management
88 | JAVA Developer
117 | Jr HR Executive
91 | KMS SPOC
90 | Liaison Officer
32 | Lumira
68 | Marketing
21 | Middleware
92 | Mobile App developer (Android)
93 | Mobile App developer (IOS)
80 | Non SAP
109 | Office boy
110 | Office executive
83 | Open Text
73 | Operations
121 | Oracle
75 | Package Coordintaor
64 | PDTO
51 | Planning
52 | Portal
84 | POWER BI
114 | Pre sale Consultant junior
53 | Program Manager
50 | Project Coordinator
45 | Project Manager
71 | Recruitment
85 | RO Coordinator
2 | SAP ABAP
81 | SAP ABAP on HANA
65 | SAP analytics
125 | SAP Ariba DSN
5 | SAP BASIS
58 | SAP BI
59 | SAP BO
72 | SAP BPC
26 | SAP BW
55 | SAP C4C
31 | SAP Cloud Platform
17 | SAP CM
105 | SAP CO
42 | SAP CPM
18 | SAP DMS
43 | SAP EHS
13 | SAP EP
23 | SAP ETM
48 | SAP FI
1 | SAP FICO
104 | SAP GRC
107 | SAP Group Reporting
97 | SAP HANA
4 | SAP HCM
62 | SAP HR ESS/MSS
3 | SAP MM
15 | SAP PI
9 | SAP PM
20 | SAP PO
10 | SAP PP
96 | SAP PRA
16 | SAP PS
22 | SAP QM
11 | SAP REFX
60 | SAP SAC
54 | SAP SD
95 | SAP SEM
14 | SAP SF
44 | SAP Solution Architect
86 | SAP SRM
82 | SAP WM
33 | SAP x-ECM
77 | SAP-MDM
103 | Senior Executive - HR
49 | SME
56 | Software ( Non SAP)
57 | Solution Manager
98 | SQL Server Administrator
111 | SR HR Executive recruitment
40 | T&C Expert
69 | Technology & Innovation
36 | TRM
19 | VBA
126 | Web Developer
94 | Wireframe Designer

## FRICE Category Data
FCategoryId | FCategoryName
1 | Conversion
2 | Enhancement
5 | Form
3 | Integration
4 | Report
6 | Work Flow

## Priority Master Data
PriorityId | PriorityName
1 | All
3 | Go Live
5 | Hold
4 | Post Go Live
2 | SIT

## Complexity Master Data
ComplexityId | ComplexityName
3 | Complex
2 | Medium
1 | Simple

## Consultant Master Data
Emp_Code | Emp_Name
2082 | 00002082 / Mr. Anilkumar Sangameshw Jeur
2726 | 00002726 / Mr. Mangesh Dattatray Wadaje
2878 | 00002878 / Mr. Upagupta Patnaik
3851 | 00003851 / Mr. Ashok Wani
4224 | 00004224 / Mr. Joydeep Banerjee
5494 | 00005494 / Mr. Rajesh Govindraya Shanbhag
5500 | 00005500 / Mr. Kaustav Das
6110 | 00006110 / Mr. Mahesh Babu Bayya
630008 | 00630008 / Mr. Santosh Mahangade
630044 | 00630044 / Mr. Raj Patel
630256 | 00630256 / Mr. Ravindra Ramesh Shenai
630284 | 00630284 / Mr. Sunil Manohar Pachgade
630393 | 00630393 / Mr. Nadeem Ul Haque Shaikh
630464 | 00630464 / Mr. Prashant Salvi
630564 | 00630564 / Mr. Gnanesh Kumsimutt
630658 | 00630658 / Ms. Meghana Bothare
630698 | 00630698 / Mr. Akhilesh Kumar Mishra
630627 | 00630627 / Mr. Saurabh Verma
630701 | 00630701 / Mr. Niladri Bhusan Harichandan
99999999 | 99999999 / Accounts Department
630579 | 00630579 / Mr. Simranjeet Singh Sond
630595 | 00630595 / Mr. Prakash Chandra Behera
630610 | 00630610 / Mr. Muzammil Husain Ansari
630656 | 00630656 / Mr. Prashant Kumar Sinha
630692 | 00630692 / Mr. Harshad N Mhatre
630721 | 00630721 / Mr. Bhabani Sankar Pal
630372 | 00630372 / Mr. Avinash Murlidhar Shelke
630534 | 00630534 / Mr. Raju Vasant Jadhav
630665 | 00630665 / Mr. Mohana Krishna Kandhi
630839 | 00630839 / Mr. Vikas Vilas Ghugare
630841 | 00630841 / Mr. Kuna Srujan
630016 | 00630016 / Mr. Santosh Choudhary
630054 | 00630054 / Ms. Ankita Abhijit Malavde
630291 | 00630291 / Mr. Ajit Uttam Desai
630846 | 00630846 / Mr. AKHIL CHERUKURI
630848 | 00630848 / Mr. Manssurali R Sayyed
630859 | 00630859 / Mr. Dilip Kumar Madderla
630301 | 00630301 / Mr. Vinay Ramchandra Singh
630530 | 00630530 / Mr. Madhu Vijaykumar Manchikatla
630741 | 00630741 / Mr. Snehal Kumbhar
630713 | 00630713 / Mr. Devendra Dandekar
630725 | 00630725 / Mr. Abhishek Pravin Godse
630727 | 00630727 / Mr. Vidhyadhar Tukaram Galande
630864 | 00630864 / Mr. Gaurav Nimbulkar
630792 | 00630792 / Mr. Rakesh Raushan
630887 | 00630887 / Mr. Ravi Varma Bhoompally
630828 | 00630828 / Mr. Vijay Mahajan
630770 | 00630770 / Mr. Saroj Kumar Jena
630802 | 00630802 / Mr. Sanjay Dhadwal
R-061 | R-061 / Mr. Deepak Garde
630890 | 00630890 / Mr. Mandar Ramakant Mhatre
630902 | 00630902 / Mr. Bharat Mainkar
630900 | 00630900 / Ms. BHUBANESWARI PRADHAN
630928 | 00630928 / Mr. Imtiyaz Khan
630940 | 00630940 / Mr. Gunarajashekar Mukkulolu
630942 | 00630942 / Mr. Sourabh Chhangani
630946 | 00630946 / Mr. NIRAJ PRATAP CHAVAN
631564 | 00631564 / Mr. Mohit Kishore Asrani
631570 | 00631570 / Mr. AKSHAY SIDDHARTH BHANGE
631572 | 00631572 / Mr. Pinkesh Navinbhai Shah
631574 | 00631574 / Mr. Akshay Sanjay Shimpi
631571 | 00631571 / Ms. Vrushali Vasant Jadhav
S-262 | S-262 / Mr. MEHUL KAILASH GOSWAMI
631577 | 00631577 / Mrs. Anjali Ganesh Hanumandla
631576 | 00631576 / Mr. Paruchuri Shankar
631578 | 00631578 / Mr. Gokul Prathyush Kolla
631584 | 00631584 / Mr. SONAL YADAV WAGHMARE
631585 | 00631585 / Mr. MD SADDAM Shaik Abdul Latif HUSSAIN
631580 | 00631580 / Mr. AKSHAY ANANDA KOKARE
S-264 | S-264 / Mr. Avatar Shiv Singh Chauhan
631583 | 00631583 / Mr. Deepesh Singh
I-051 | I-051 / Mr. Dhruv Deepesh Krishnan
S-268 | S-268 / Mr. SHIRISH SUBHASH BHAMARE
S-269 | S-269 / Mr. Rakesh Kumar
S-266 | S-266 / Mr. Shivakumar Devnoor
631592 | 00631592 / Mr. Ajitesh Kumar
631594 | 00631594 / Mr. SARVESH GANGARAM KUWAR
S-270 | S-270 / Mr. Deepak Nityanand Chawla
S-267 | S-267 / Mr. Aniket S
R-109 | R-109 / Mr. Partha Sarathi Ray
631648 | 00631648 / Ms. Srinidhi Sampathirao
631599 | 00631599 / Ms. Nikita Arvind Yedre
631603 | 00631603 / Mr. Ganesh Prakash
S-276 | S-276 / Mr. Himanshu Jain
631604 | 00631604 / Ms. Nikita Kaushik
631605 | 00631605 / Mr. Abhijeet Dinkar Madage
630947 | 00630947 / Mrs. Shital Nitin Hingmire
S-047 | S-047 / Mr. K M Maxwell Richard
630948 | 00630948 / Mr. Naved Aslam Khan
630949 | 00630949 / Mrs. Ashwini Patil
630997 | 00630997 / Mr. Abhishek Sahu
630971 | 00630971 / Mr. Shekhar Shinde
630987 | 00630987 / Ms. SABINA BISWAL
630951 | 00630951 / Mr. Apurv Milan Patil
630955 | 00630955 / Ms. Sharayu Rajhans Ambadkar
630957 | 00630957 / Ms. Sakshi Gajendra Nikam
630965 | 00630965 / Mr. Charchit Kumar Dash
630980 | 00630980 / Mr. Jalindar Walunj
630989 | 00630989 / Mr. Chirag Navinchandra Bhandari
630977 | 00630977 / Mr. Kripa Singh
630978 | 00630978 / Mr. Durgesh Patil
630983 | 00630983 / Mr. Prasad Phadtare
631005 | 00631005 / Mr. RAHUL BHOGI
631033 | 00631033 / Mr. Pankaj Jaiswal
631031 | 00631031 / Mr. Karthik Purad
631038 | 00631038 / Mr. Rahul Singhal
631046 | 00631046 / Mr. Rahul Patil
S-060 | S-060 / Mr. Avadhut Mahadik
631043 | 00631043 / Mr. Kulandai Yesu
631049 | 00631049 / Mr. Arif Shaikh
631041 | 00631041 / Mr. Sachin Mohod
631056 | 00631056 / Mr. Pranit Marge
S-064 | S-064 / Mr. Charan Kumar
631058 | 00631058 / Mr. Vishal Chippa
631070 | 00631070 / Mr. Ganesh Chalak
631074 | 00631074 / Mr. Vishwajit Durgude
631076 | 00631076 / Mr. Sateesh Lunavathu
631084 | 00631084 / Mr. Deepak Narayan Wagh
631171 | 00631171 / Mr. Harshal Chandrashekhar Gite
631172 | 00631172 / Mr. Mahesh Shamsundar Hatle
631173 | 00631173 / Ms. Mayuri Daulat Patil
631181 | 00631181 / Mr. Nishant Srinivasan
631165 | 00631165 / Mr. Ashutosh Sandhya Kulkarni
631086 | 00631086 / Ms. Rashmi sinha
631088 | 00631088 / Mr. Dheeraj Bhardwaj
631090 | 00631090 / Ms. Lipika Nanda
631091 | 00631091 / Mr. Sumit kumar Vishwakarma
631094 | 00631094 / Ms. Silpa Dash
631109 | 00631109 / Mr. Sameer Wasudeo Gurnule
631100 | 00631100 / Mr. Rakesh kumar Rout
631101 | 00631101 / Mr. Pankaj kumar
631191 | 00631191 / Mr. Ratna Kamalakar Kaki
631192 | 00631192 / Mr. Rahul Singh
S-115 | S-115 / Mr. Krishna Choudhary
631224 | 00631224 / Mr. Prashant D Jagdale
631289 | 00631289 / Mr. Ronak Suresh Jain
S-147 | S-147 / Mr. Satish Bhakth
S-148 | S-148 / Mr. Shivraj Singh
631283 | 00631283 / Mr. Mahendra Hindurav Jadhav
631296 | 00631296 / Mr. Pramod Kumar Sahoo
631123 | 00631123 / Mr. Vikash Devuri
631121 | 00631121 / Mr. Harish chander Joshi
631134 | 00631134 / Mr. Saurabh Sharma
631135 | 00631135 / Mr. Ved Sinha
631136 | 00631136 / Mr. Samad Muhammed
631140 | 00631140 / Mr. Udayakiran Kodeboina
S-080 | S-080 / Mr. CHINMAYA KUMAR JENA
631147 | 00631147 / Mr. MOHAMMAD ABUZER
631148 | 00631148 / Mr. Deepak Vasant Jadhav
631156 | 00631156 / Mr. NIKHIL SHASHIKANT NARKHEDE
631138 | 00631138 / Mr. Nassim Akhtar
631167 | 00631167 / Mr. Pranav Dinkar Gawade
631168 | 00631168 / Mr. AKSHAY KISHOR BAIRAGI
631144 | 00631144 / Mr. Pavan Kumar
631149 | 00631149 / Mr. Srinivas Moturi
631600 | 00631600 / Mr. RUBAN PRASAD
S-273 | S-273 / Mr. RISHABH CHANDRAKANT BHANDARI
631610 | 00631610 / Mr. Pratik Naresh Mandlik
631613 | 00631613 / Mr. venkatesh Lankapalli
631606 | 00631606 / Mr. Chirag Prasanna
S-277 | S-277 / Mr. Sunil Dhariwal
631607 | 00631607 / Mr. Nikhil Mekala Bhoomaiah
631609 | 00631609 / Ms. Aafreen Mohd. Aasim Shaikh
R-112 | R-112 / Mr. PADINHARE VALIYAVEEDU AFRAZ
S-280 | S-280 / Mr. Rahul Ranoji Jadhav
S-281 | S-281 / Mr. Narender Umapathi Mamidi
631615 | 00631615 / Mr. Himanshu Gupta
631619 | 00631619 / Mr. Akshay Mahendra Rokade
631622 | 00631622 / Mrs. Gurleen Kaur
631623 | 00631623 / Mr. Sayed zegam abbass Taqvi
631625 | 00631625 / Mrs. Nikita Singh
631618 | 00631618 / Mr. Swapnil Santosh Purkar
631624 | 00631624 / Mr. Atul Kumar Dubey
S-291 | S-291 / Mrs. SHILPI PARIHAR
S-292 | S-292 / Mr. Kamal Singh
S-315 | S-315 / Mr. Stephen Dsouza
S-284 | S-284 / Mr. SANDESH SANTOSH VEKHANDE
631630 | 00631630 / Mr. Akshay Pandurang Hore
631634 | 00631634 / Mr. Ameen Mohiddin Shikalgar
631635 | 00631635 / Mr. Nischal Yalamaddi
631636 | 00631636 / Mr. Varun Itagampali
S-296 | S-296 / Mr. Ram Gupta
S-287 | S-287 / Mr. Gajanan Shivram Tagadpalle
631620 | 00631620 / Mr. TEJAS DEEPAK NAIK
631626 | 00631626 / Mr. Adarsh Ranjan
S-290 | S-290 / Mr. TANUJ DAHIYA
631628 | 00631628 / Mr. Tanmay Shridhar Parab
631631 | 00631631 / Mr. Onkar Ashish Kawde
631632 | 00631632 / Mr. Nikhil Jayendra Dandekar
631633 | 00631633 / Mr. Yash Pareshbhai Sheth
S-294 | S-294 / Mr. JITESH KUSHWAHA
631178 | 00631178 / Ms. Merlin Tomy
S-098 | S-098 / Mr. Parag Sinkar
S-109 | S-109 / Mr. Sridhar Yamala
631196 | 00631196 / Mr. Nikhil Patil
631202 | 00631202 / Mr. Akshay Harichandan
631227 | 00631227 / Mr. Dharmakumar Barrey
631221 | 00631221 / Mr. Prashant Vadlakonda
631228 | 00631228 / Mr. Pravin Shivaji Wahulkar
631235 | 00631235 / Mr. KAHNU CHARAN SAHU
S-123 | S-123 / Mr. Biltu Karjee
631247 | 00631247 / Mr. Dilip Kumar Kapa
631293 | 00631293 / Mr. Deepak Madishetti
631304 | 00631304 / Mr. Jayasurya Lakkoju
631294 | 00631294 / Mr. Sadanand Anant Sarmalkar
631295 | 00631295 / Mr. Sanjay Abhiman Patil
631299 | 00631299 / Mr. Yogeshkumar Ashokbhai Nai
631301 | 00631301 / Mr. Vinay Verma
631310 | 00631310 / Mr. Syed Taiyab Mahmood Hashmi
S-163 | S-163 / Mr. Mukesh Kumar Yadav
631318 | 00631318 / Mr. KODAVALURU NIKHIL REDDY
631319 | 00631319 / Mr. AHEMAD BILAL
631245 | 00631245 / Mr. Amrit Kumar Swain
631248 | 00631248 / Mr. Mangesh Vinayakrao Chitale
631256 | 00631256 / Mr. Aniket Shivram Karmalkar
631257 | 00631257 / Mr. Rupesh Vairal
631241 | 00631241 / Mr. Ashish Kumar Ranjan
631244 | 00631244 / Mr. prasant kumar Gopalkrishna Dash
631265 | 00631265 / Mr. Hrishikesh Pravin Nikam
631266 | 00631266 / Mr. Manikandan shanmugam
631246 | 00631246 / Mr. Harshad Sureshrao Dhande
631255 | 00631255 / Mr. Arun Nana Patil
S-138 | S-138 / Mr. Chirag Ashokkumar Shah
631263 | 00631263 / Mr. Yogesh K Mhadolkar
631268 | 00631268 / Mr. Shivraj More
631254 | 00631254 / Mr. Parvathaneni Srinivasulu
S-139 | S-139 / Mr. Abhinandan ABAP
631269 | 00631269 / Mr. Vivek Ugare
631276 | 00631276 / Mr. Vaibhav Dagadu Karale
631275 | 00631275 / Mr. Akshay Rajendra Gavali
631279 | 00631279 / Mr. AKASH KUMAR SAHU
S-146 | S-146 / Mr. Veeranjaneyulu Valluri
631282 | 00631282 / Ms. Archana Kailas Hire
631286 | 00631286 / Mr. Niket Ravindra Devkar
631287 | 00631287 / Mr. Gaurav Kumar
S-173 | S-173 / Ms. PRADNYA VISHWASRAO PATIL
631329 | 00631329 / Ms. Priyanka Arun Gaikar
631332 | 00631332 / Mr. SATISH PANCHADA
631334 | 00631334 / Mr. VENU JANGA
I-035 | I-035 / Mr. Vijay Sadashiv Salvi
S-171 | S-171 / Mr. Amarjeet Singh
631325 | 00631325 / Mr. Arijeet Chatterjee
631321 | 00631321 / Mr. Vinay Kumar Rudra
631322 | 00631322 / Mr. Harshal Prakash Patil
631328 | 00631328 / Mr. Sharanbasappa S
631330 | 00631330 / Mr. Sajid Biram Shaikh
631331 | 00631331 / Mr. Navin Kumar Pathak
631333 | 00631333 / Mr. Premjeet Milind Sakolkar
631337 | 00631337 / Mr. Prakash Raghunath Sutar
631341 | 00631341 / Mrs. Monica Swapnil Dhuri
I-038 | I-038 / Mr. kishor barkya Tambe
631348 | 00631348 / Mr. Ritesh Nikam
631353 | 00631353 / Mr. Nilesh Sanjay Shelar
S-183 | S-183 / Mr. RITESH PAL
631366 | 00631366 / Mr. THATAVARTHI SATYA RAVINDRA
631338 | 00631338 / Mr. Jeetendra Srichand Kshatriya
631342 | 00631342 / Mr. Mayur Rajesh Pansare
631345 | 00631345 / Mr. Prashant Ganapati Kurse
631346 | 00631346 / Mr. Naresh Uggera
631349 | 00631349 / Ms. Shamal Ramesh Jamadar
631369 | 00631369 / Mr. RAJ KUMAR KUNDU
631370 | 00631370 / Mr. Malagoud Sidagoud Patil
631376 | 00631376 / Ms. Aditi Harish Sharma
631351 | 00631351 / Mr. Rishi Kant Kumar
S-186 | S-186 / Mr. Prason Kumar
631358 | 00631358 / Mr. Harish Kisan Thakare
631356 | 00631356 / Mr. MOHAN REDDY MOGILI
631357 | 00631357 / Ms. Salma Sultana
631363 | 00631363 / Mr. Ashok Kumar Vishwakarma
631364 | 00631364 / Mr. NAVEEN KUMAR DAMODARAM
S-198 | S-198 / Mr. Aditya Shekhawat
631371 | 00631371 / Mr. Mohammed Abdul Thamjeeth Athahar
631381 | 00631381 / Mr. Sreehari C
S-199 | S-199 / Mr. DHANANJAY RAMCHANDRA KATRE
S-200 | S-200 / Mr. Mahipal Singh Devda
631384 | 00631384 / Mr. Suraj Siddharth Patil
631388 | 00631388 / Ms. DEEPIKA GUPTA
631389 | 00631389 / Mr. Hrishikesh Amarnath Bagul
631387 | 00631387 / Mr. Izharuddin Azeemuddin Quazi
631392 | 00631392 / Ms. Riya Routray
631395 | 00631395 / Mr. Rahul Hanumant Kumbhar
631396 | 00631396 / Mr. MUKESH UDAYBHAN PRAJAPATI
631397 | 00631397 / Mr. RITIKRAJ SINGH
631394 | 00631394 / Mr. Vishal Chaudhary
631402 | 00631402 / Mr. PRABHU SHIVAJI PANZADE
631403 | 00631403 / Mr. SHUBHAM GARG
S-204 | S-204 / Mrs. Vrushalee sharma
631410 | 00631410 / Mr. Zaid Surve
631398 | 00631398 / Mr. Arpit Ashok Agarwal
631399 | 00631399 / Mr. Gaurav Pimple
631405 | 00631405 / Mr. Ashish Amol Dagare
631407 | 00631407 / Mrs. RINKU PAUL
631411 | 00631411 / Ms. Sumita Maji
631413 | 00631413 / Mr. Anurag Mahadeo Dhepe
631415 | 00631415 / Mr. Namdev Sakharam Choure
631416 | 00631416 / Mr. SUMIT RAJESH JAIN
631417 | 00631417 / Mr. Darshil Tejkaran Bhavsar
631418 | 00631418 / Mr. Anurag Kumar Singh
S-207 | S-207 / Mr. Ravi Kiran Puppala
S-206 | S-206 / Mr. Yadunath Singh
R-102 | R-102 / Mr. Ashish Rai
631422 | 00631422 / Mr. JAGADISH KUNA
631424 | 00631424 / Mr. VIKASH KUMAR PANDIT
S-209 | S-209 / Mr. NIKHIL VIJENDRA MALPE
631429 | 00631429 / Mr. SURENDRA NADHA REDDY MUTUKUNDU
631434 | 00631434 / Mr. Harshal Bhaidas Patil
631435 | 00631435 / Mr. Kalpesh Jagdish Patel
S-218 | S-218 / Mr. PANKAJ TRIPATHI
631427 | 00631427 / Mr. Shivam Sahal
631431 | 00631431 / Mr. SUMIT ANIL SINGH
631432 | 00631432 / Mr. ABHIJEET BALASAHEB PUND
631437 | 00631437 / Mr. KUNAL Nalawade
631445 | 00631445 / Mr. AVINASH SUSHMA AWADHIYA
S-224 | S-224 / Mr. Sanket Yadav
631442 | 00631442 / Mr. Dnyaneshwar M Bhavikatti
631443 | 00631443 / Mr. Habel Issac Jacob
S-220 | S-220 / Mr. SWAROOP SINGH
631466 | 00631466 / Mrs. KOMAL VIVEK JAVERIA
R-104 | R-104 / Mr. Chetan Anil Patil
631471 | 00631471 / Ms. Pooja Dattatry khot
S-222 | S-222 / Mr. Yuvraj Singh Shekhawat
631454 | 00631454 / Mr. Chandrakant Vikram Wagh
631462 | 00631462 / Mr. Milind Bhalchandra Erande
631468 | 00631468 / Ms. Shweta Singh
631456 | 00631456 / Mr. SAGAR SUNIL MORE
631474 | 00631474 / Mr. JAGDISH TEJABHAI BARVADIYA
631475 | 00631475 / Mr. Asif Manauwar
631457 | 00631457 / Mr. MD WASIM AKRAM
631458 | 00631458 / Mr. SHUBHAM PRAMOD SANGOLE
631461 | 00631461 / Ms. Sumaiya Shaikh
S-229 | S-229 / Mr. Abhishek Dayanand Kamble
631469 | 00631469 / Mr. Nikunj Daga
631476 | 00631476 / Mr. Amit Kishorrao Kalaskar
631478 | 00631478 / Mr. Susanta Kumar Nayak
631479 | 00631479 / Ms. Meghna Prusty
631483 | 00631483 / Mr. Sandip Mohan Shinde
S-233 | S-233 / Mr. ANKIT MORE
631481 | 00631481 / Ms. Saeema Parveen
631482 | 00631482 / Mr. Laxmikant Bajarang Zirpe
631484 | 00631484 / Mrs. Honey Bapna
631486 | 00631486 / Mr. CHALLA VIGHNESWARA RAO
631489 | 00631489 / Mr. Parveen Kaushik
631485 | 00631485 / Mr. SHANTANU SATISH GHODKE
S-237 | S-237 / Mr. Sandeep Parida
631487 | 00631487 / Mr. Shubham Dhanraj Dhamse
631590 | 00631590 / Ms. Darshini Sunder Pillai
631491 | 00631491 / Mr. SUMANT KUMAR BHARTI
631496 | 00631496 / Mr. Shreetam Tarenia
631501 | 00631501 / Mr. Ketan Vishwas Deshmukh
631505 | 00631505 / Mr. Ravi Madhesiya
631507 | 00631507 / Mr. Mayur Milind Joshi
631500 | 00631500 / Mr. Nakul Prabhakar Kamone
631524 | 00631524 / Mr. ABHIJEET RAIPURE
631525 | 00631525 / Mr. KALLEM UMAKANTH GOUD
631528 | 00631528 / Mr. Pranav Arvind Kakani
631504 | 00631504 / Ms. Arpita Gupta
631521 | 00631521 / Mr. YEDDULA VENKATA SIVA REDDY
631511 | 00631511 / Mrs. Anjali Sanger
631512 | 00631512 / Mr. MANGA VENKATA RAO
631510 | 00631510 / Mr. Yatin Sunil Pathak
631514 | 00631514 / Mr. Ramesh Ramkripal Gupta
631515 | 00631515 / Mr. SANDEEP KUMAR SWAIN
631518 | 00631518 / Mr. Vicky Meena
631519 | 00631519 / Mr. Akshay Sukhadeo Dhumal
631520 | 00631520 / Mr. Muneeb Ikram Khan
631530 | 00631530 / Mr. RAJA NARASIMHA MURTHY ARDHANI
631532 | 00631532 / Mr. Rushikesh Rajendra Kangane
631533 | 00631533 / Mr. G CHAKRAVARTHY
631537 | 00631537 / Mr. Amrendra Pratap Singh
631538 | 00631538 / Mr. Gokul K
631534 | 00631534 / Mr. Sameer Parab
R-107 | R-107 / Mr. PARAG PANDURANG MAHADIK
S-247 | S-247 / Mr. Jaydeep Singh Rathore
631542 | 00631542 / Mr. Karthik Chowdary Pendurthi
631543 | 00631543 / Mr. Syed Abdul Rizwaan
631545 | 00631545 / Mr. RAHUL BHOWMIK
631547 | 00631547 / Mr. Rohit Sudhakar Mane
I-048 | I-048 / Mr. Aditya Anirvan
631540 | 00631540 / Mr. Pavan Kalyan
631544 | 00631544 / Ms. Himani Aditee
631546 | 00631546 / Mr. Vedant Nitin Bhagwat
631548 | 00631548 / Mr. Nilesh Mohan Nikam
631553 | 00631553 / Mr. PANKAJ DATTATRAYA GHAWADE
S-252 | S-252 / Mr. Harshal Bhikan Patil
631556 | 00631556 / Mr. Dattatray Bhausaheb Godse
631558 | 00631558 / Mr. Hriday Das
631560 | 00631560 / Mr. Gautam Sen
631552 | 00631552 / Mr. Kunal Vinod Kulkarni
631554 | 00631554 / Ms. Shriya Sinha
631555 | 00631555 / Mr. Shrikant Ashokrao Alone
631563 | 00631563 / Mr. Pradeep Rawat
631566 | 00631566 / Mr. ANKIT Ganesh Ram MEHAR
631557 | 00631557 / Mr. Govinda Rajkumar Singhwal
631559 | 00631559 / Mr. Adnan Ejaz Mundewadi
631562 | 00631562 / Ms. Siddhi Sharad Mhamunkar
S-256 | S-256 / Mr. Sangramsinha Balavant Chougale
S-295 | S-295 / Mr. Rahul Kumawat
631643 | 00631643 / Mr. Kritik Mayur Joshi
631644 | 00631644 / Mr. Vishal Santosh Wadekar
S-306 | S-306 / Mr. Shivraj Singh Shekhawat
S-299 | S-299 / Mr. Alok Kumar Dubey
631653 | 00631653 / Mr. PRATIK BHOJRAJ PATIL
631657 | 00631657 / Mr. Purushottam Annasaheb Taur
631661 | 00631661 / Mr. Shubham Purushottam Parashar
S-309 | S-309 / Mr. Prajwal Satish Aher
631638 | 00631638 / Mr. Kaushal Sharma
631641 | 00631641 / Mr. Harshad Vivek Sawant
S-305 | S-305 / Mr. Jaydev Gajjar
631649 | 00631649 / Mr. Soum Gupta
631645 | 00631645 / Mr. Vaishnav Ganesh Dalvi
S-302 | S-302 / Mrs. BHARTI KUMARI
S-304 | S-304 / Mr. Alok RAJAK
S-308 | S-308 / Mr. Abhishek Kumar Upadhyay
631675 | 00631675 / Mr. Roshan Hande
631642 | 00631642 / Ms. Komal Anant Parab
631646 | 00631646 / Mr. Deepak Baviskar
631651 | 00631651 / Mr. VIKAS SINGH
S-307 | S-307 / Mr. Kiran Tetgure
631664 | 00631664 / Mr. Mohammad Monis
631668 | 00631668 / Mr. Rohit Kishor Thakare
I-050 | I-050 / Mr. Kartik Jha
631652 | 00631652 / Mr. JAY RAJENDRA RAUT
631654 | 00631654 / Mr. Salah Raeesuddin Shaikh
631655 | 00631655 / Mr. Shakir Iqbal Momin
631658 | 00631658 / Mr. Sahil Jagannath Pawar
631659 | 00631659 / Mr. Rushikesh Patil
631660 | 00631660 / Mr. Vipin Patankar
631662 | 00631662 / Mr. Mohammed Said Makarani
631663 | 00631663 / Mr. JAGADEESWARA REDDY CHENNURU
S-310 | S-310 / Mr. Rithik Jamana Shankar Chaturvedi
631667 | 00631667 / Mr. Abhishek Cheetirala
S-317 | S-317 / Mr. Vikas Kumar Singh
631669 | 00631669 / Mr. K.Udit Prasad
631677 | 00631677 / Mr. Kumar Anoop
631680 | 00631680 / Mr. Karan Jha
631681 | 00631681 / Mr. Mahesh Balavant Padaval
631686 | 00631686 / Mr. Debasish Datta
631688 | 00631688 / Mr. Durga Prasad PenuBothu
S-311 | S-311 / Mr. Mohan Reddy
S-312 | S-312 / Mr. Bharat Kumar Nagda
S-313 | S-313 / Mr. Ajinkya Sunil Bhaskar
631671 | 00631671 / Mrs. Kiran Mitthilesh Gupta
I-052 | I-052 / Ms. Shrutika Dilip Mudgalkar
631665 | 00631665 / Mr. Prajyot Pradeep Yerunkar
631674 | 00631674 / Mr. Yogesh Ranglal Katre
631684 | 00631684 / Mr. Kiran Ravindra Shelke
631687 | 00631687 / Mr. Ashutosh Tiwari
631694 | 00631694 / Ms. Swati Patil
S-324 | S-324 / Mr. Lokendra Singh
631705 | 00631705 / Mr. Lakkireddy Umamaheswarreddy
631666 | 00631666 / Mr. Zinit Bhupeshchandra Gautam
631672 | 00631672 / Mr. UMESH CHANDRA EMBETI
631673 | 00631673 / Mr. Malairaman C
R-115 | R-115 / Mr. Sumesh Mehta
631692 | 00631692 / Mr. Meher Chand Sirigiri
631678 | 00631678 / Mr. MAHESH CHANDRA MULUKUDITI
631693 | 00631693 / Mrs. Chitranshi Sharma
S-320 | S-320 / Mr. Akhil Kumar
S-322 | S-322 / Mr. Alok Sharma
S-323 | S-323 / Mr. Manohar Kornapalli
631697 | 00631697 / Mr. SUDESH PANDHARINATH KARNIK
631679 | 00631679 / Mr. ANIL NARAYAN SHINDE
631691 | 00631691 / Mr. Utkarsh Raj Chandra
631695 | 00631695 / Mrs. Shubhangi Pravin Ligade
631701 | 00631701 / Mr. Jaiveer Singh
S-325 | S-325 / Mr. Avinash P
631718 | 00631718 / Mr. Deepak Chatur Thakare
631682 | 00631682 / Mr. Ketan Joshi
631683 | 00631683 / Ms. Preethi J
S-319 | S-319 / Mr. Peddi Sivasurya Kishore Kumar
631685 | 00631685 / Ms. Khushboo Kumari
R-116 | R-116 / Mr. Bindumadhav Anant Ambike
S-321 | S-321 / Ms. Deepti Ketan Joshi
631696 | 00631696 / Mr. Shubham Patidar
631702 | 00631702 / Mrs. Pratibha Anilkumar Mishra
631707 | 00631707 / Mr. Rajas Sunil Chaudhari
S-326 | S-326 / Mr. Manmohan Singh
631708 | 00631708 / Mr. Yash Sanjay Pawar
631710 | 00631710 / Ms. Snehal Anil Jadhav
R-117 | R-117 / Mr. Amarendar Kumar
631699 | 00631699 / Mr. Prashant Dutta
631703 | 00631703 / Mr. Ketan Deshpande
631704 | 00631704 / Mr. Suman Acharyya
S-327 | S-327 / Mrs. Sailee A Bhoir
631709 | 00631709 / Mr. Ashwajit Purushottamrao Bansod
631711 | 00631711 / Mr. Mayur Vikas Kawale
631712 | 00631712 / Mr. Yatin Majgaonkar
S-328 | S-328 / Mr. Sarvesh Kumar
631713 | 00631713 / Mr. Tushar Pandurang Patil
631714 | 00631714 / Mrs. Nayan Jayshankar Hingmire
631715 | 00631715 / Mr. Akshay Anil Warang
631717 | 00631717 / Mr. Shivamsingh Narendra Chouhan
I-053 | I-053 / Mr. Pranav Dattatraya Borate
631719 | 00631719 / Mr. Mahesh Wakode
S-329 | S-329 / Mr. Shehjad Shaikh
S-330 | S-330 / Mr. Dhananjay Katre
631720 | 00631720 / Mr. Lalit Asnani
S-331 | S-331 / Mr. Mahaveer Singh Jhala
631724 | 00631724 / Mr. ADITYA CHANDRAKANT DINDORE
631725 | 00631725 / Ms. Supriya Shivalkar Shivalkar
S-332 | S-332 / Mr. ANKIT JOSHI
631721 | 00631721 / Mr. SANTOSH KUMAR LANDA
631722 | 00631722 / Mrs. Amruta Vaibhav Jadhav
S-334 | S-334 / Mr. Akhil Kumar
631726 | 00631726 / Ms. Palak Singh Sisodia
631727 | 00631727 / Mr. SASWAT KUMAR SAHOO
S-336 | S-336 / Mr. Utkarsh Chittora
631729 | 00631729 / Mr. Manuka Ramesh
631723 | 00631723 / Mr. Sanganagoud Patil
S-335 | S-335 / Mrs. Srujana Vangala
S-337 | S-337 / Mr. Surya G
S-338 | S-338 / Mr. Kiran Udayar
631730 | 00631730 / Mr. Palash Chatter
631733 | 00631733 / Mr. N. Kiran Kumar
S-333 | S-333 / Mr. Subhash Yermule
631728 | 00631728 / Ms. Ankita Gopal Joshilkar
631731 | 00631731 / Mr. Avichal Prashant Sonarghare
631732 | 00631732 / Ms. Aruamita Mohanty
631734 | 00631734 / Mr. Vihang Tilakchand Dhamgaye
S-339 | S-339 / Mr. Sandeep Singh
R-118 | R-118 / Mr. Jittesh Jagdish Purrohit

## ABAP Consultant Master Data
Emp_Code | Emp_Name
630579 | 00630579 / Mr. Simranjeet Singh Sond
630665 | 00630665 / Mr. Mohana Krishna Kandhi
630841 | 00630841 / Mr. Kuna Srujan
630016 | 00630016 / Mr. Santosh Choudhary
630301 | 00630301 / Mr. Vinay Ramchandra Singh
630530 | 00630530 / Mr. Madhu Vijaykumar Manchikatla
630864 | 00630864 / Mr. Gaurav Nimbulkar
630828 | 00630828 / Mr. Vijay Mahajan
630946 | 00630946 / Mr. NIRAJ PRATAP CHAVAN
631577 | 00631577 / Mrs. Anjali Ganesh Hanumandla
630947 | 00630947 / Mrs. Shital Nitin Hingmire
630949 | 00630949 / Mrs. Ashwini Patil
630951 | 00630951 / Mr. Apurv Milan Patil
630955 | 00630955 / Ms. Sharayu Rajhans Ambadkar
630957 | 00630957 / Ms. Sakshi Gajendra Nikam
S-060 | S-060 / Mr. Avadhut Mahadik
S-064 | S-064 / Mr. Charan Kumar
631070 | 00631070 / Mr. Ganesh Chalak
631171 | 00631171 / Mr. Harshal Chandrashekhar Gite
631172 | 00631172 / Mr. Mahesh Shamsundar Hatle
631173 | 00631173 / Ms. Mayuri Daulat Patil
631165 | 00631165 / Mr. Ashutosh Sandhya Kulkarni
S-115 | S-115 / Mr. Krishna Choudhary
S-147 | S-147 / Mr. Satish Bhakth
631135 | 00631135 / Mr. Ved Sinha
631136 | 00631136 / Mr. Samad Muhammed
631138 | 00631138 / Mr. Nassim Akhtar
631167 | 00631167 / Mr. Pranav Dinkar Gawade
631168 | 00631168 / Mr. AKSHAY KISHOR BAIRAGI
631144 | 00631144 / Mr. Pavan Kumar
631149 | 00631149 / Mr. Srinivas Moturi
631606 | 00631606 / Mr. Chirag Prasanna
S-281 | S-281 / Mr. Narender Umapathi Mamidi
631615 | 00631615 / Mr. Himanshu Gupta
S-291 | S-291 / Mrs. SHILPI PARIHAR
S-284 | S-284 / Mr. SANDESH SANTOSH VEKHANDE
S-296 | S-296 / Mr. Ram Gupta
631626 | 00631626 / Mr. Adarsh Ranjan
631628 | 00631628 / Mr. Tanmay Shridhar Parab
631178 | 00631178 / Ms. Merlin Tomy
S-109 | S-109 / Mr. Sridhar Yamala
631196 | 00631196 / Mr. Nikhil Patil
631221 | 00631221 / Mr. Prashant Vadlakonda
S-123 | S-123 / Mr. Biltu Karjee
631304 | 00631304 / Mr. Jayasurya Lakkoju
631265 | 00631265 / Mr. Hrishikesh Pravin Nikam
S-139 | S-139 / Mr. Abhinandan ABAP
S-146 | S-146 / Mr. Veeranjaneyulu Valluri
S-171 | S-171 / Mr. Amarjeet Singh
631333 | 00631333 / Mr. Premjeet Milind Sakolkar
S-183 | S-183 / Mr. RITESH PAL
631342 | 00631342 / Mr. Mayur Rajesh Pansare
631349 | 00631349 / Ms. Shamal Ramesh Jamadar
S-186 | S-186 / Mr. Prason Kumar
631356 | 00631356 / Mr. MOHAN REDDY MOGILI
S-198 | S-198 / Mr. Aditya Shekhawat
631392 | 00631392 / Ms. Riya Routray
631410 | 00631410 / Mr. Zaid Surve
631415 | 00631415 / Mr. Namdev Sakharam Choure
631416 | 00631416 / Mr. SUMIT RAJESH JAIN
S-206 | S-206 / Mr. Yadunath Singh
S-209 | S-209 / Mr. NIKHIL VIJENDRA MALPE
631427 | 00631427 / Mr. Shivam Sahal
631445 | 00631445 / Mr. AVINASH SUSHMA AWADHIYA
S-220 | S-220 / Mr. SWAROOP SINGH
S-222 | S-222 / Mr. Yuvraj Singh Shekhawat
631468 | 00631468 / Ms. Shweta Singh
631457 | 00631457 / Mr. MD WASIM AKRAM
631458 | 00631458 / Mr. SHUBHAM PRAMOD SANGOLE
631478 | 00631478 / Mr. Susanta Kumar Nayak
631483 | 00631483 / Mr. Sandip Mohan Shinde
631491 | 00631491 / Mr. SUMANT KUMAR BHARTI
631505 | 00631505 / Mr. Ravi Madhesiya
631507 | 00631507 / Mr. Mayur Milind Joshi
631504 | 00631504 / Ms. Arpita Gupta
631510 | 00631510 / Mr. Yatin Sunil Pathak
631518 | 00631518 / Mr. Vicky Meena
S-247 | S-247 / Mr. Jaydeep Singh Rathore
631542 | 00631542 / Mr. Karthik Chowdary Pendurthi
631546 | 00631546 / Mr. Vedant Nitin Bhagwat
631548 | 00631548 / Mr. Nilesh Mohan Nikam
S-252 | S-252 / Mr. Harshal Bhikan Patil
631556 | 00631556 / Mr. Dattatray Bhausaheb Godse
S-295 | S-295 / Mr. Rahul Kumawat
S-309 | S-309 / Mr. Prajwal Satish Aher
631638 | 00631638 / Mr. Kaushal Sharma
S-304 | S-304 / Mr. Alok RAJAK
S-308 | S-308 / Mr. Abhishek Kumar Upadhyay
S-307 | S-307 / Mr. Kiran Tetgure
631668 | 00631668 / Mr. Rohit Kishor Thakare
I-050 | I-050 / Mr. Kartik Jha
S-310 | S-310 / Mr. Rithik Jamana Shankar Chaturvedi
631669 | 00631669 / Mr. K.Udit Prasad
631687 | 00631687 / Mr. Ashutosh Tiwari
S-324 | S-324 / Mr. Lokendra Singh
631695 | 00631695 / Mrs. Shubhangi Pravin Ligade
S-325 | S-325 / Mr. Avinash P
631717 | 00631717 / Mr. Shivamsingh Narendra Chouhan
S-336 | S-336 / Mr. Utkarsh Chittora
S-335 | S-335 / Mrs. Srujana Vangala
S-338 | S-338 / Mr. Kiran Udayar
S-333 | S-333 / Mr. Subhash Yermule
S-339 | S-339 / Mr. Sandeep Singh

## Reusable Status Master Data
ResuableStatusId | ResuableStatusName
2 | Copied
1 | WIP