## Sheet1
ACTION PLAN FOR OPERATIONS PRIORITY PROCESSES
Sr.No | Description of Process | Target Quality | Target Production | Remarks
1 | Station Diary | 13/11/21 | 20/11/21 | 1. The said dates for movement to Production are considering no additional requirements are needed. 2. The mentioned processes are already in Quality server however additional requirements / observations are being implemented . 3. Biometric authentication of SAP with IDCube service has been implemented with test server installed in user laptop / desktop . However testing with ID Cube servers in Stations is not yet carried out as there has been no confirmation on the same from IDCube . Furthermore network connectivity in line with that in test environment needs to be provided by Mahametro Networking team. 4. Possession Register (Station) final requirement discussion is pending with end-user hence the same has not been included.
2 | Key Register | 13/11/21 | 20/11/21
3 | Equipment Failure | 13/11/21 | 20/11/21
4 | Biodata Register | 15/11/21 | 22/11/21
5 | Traffic Controller Diary | 16/11/21 | 23/11/21
6 | Train Operator Sign On - Sign Off Register | 16/11/21 | 23/11/21
7 | PTW (Station & OCC) | 17/11/21 | 24/11/21
8 | Cancellation of PTW (Station & OCC) | 17/11/21 | 24/11/21
9 | Possession Register (OCC) | 19/11/21 | 26/11/21
Note :-