## Tasklist
Srno. | Task | Start Date | End Date | Status
1 | Home Page Development - Responsive | 2020-06-01 | 2020-06-01 | Pending
2 | Location / Client Master | 2020-06-16 | 2020-06-16
3 | Employee Joining | 2020-06-17 | 2020-06-19
4 | Employee Exit | 2020-06-20 | 2020-06-20
5 | Location / Client Transfer / Allocation | 2020-06-22 | 2020-06-23
6 | Employee : Department Change | 2020-06-24 | 2020-06-24
7 | Employee : Reporting Change | 2020-06-25 | 2020-06-25
9 | Schedular Auto Leave cut generation | 2020-06-26 | 2020-06-27
8 | Schedular Leave Quota Calculation | 2020-06-29 | 2020-07-01
Formulas:
End Date = [Start Date]
End Date = [Start Date]+2
Start Date = [Start Date, row above]+1
Start Date = [End Date, row above]+1

## Location - Client ¦ Project Mas
Location / Client Master | [13 empty] | X
[15 empty] | Location | Active
|  | Location / Client Code: | 1 | [11 empty] | Client | Inactive
|  | Location / Client Name: | Head Office
|  | Address: | D-Wing, 14th Floor, Empire Tower, Reliable Cloud City, Off. Thane-Belapur Road, Airoli. | [6 empty] | Company Code: | 1 |  | …
Highbar Technocrat Ltd.
|  | Pin: | 400 708 |  |  | City: | Navi Mumbai |  |  | Type: | Location
|  | State: | Maharashtra |  |  | Country: | India |  |  | Status: | Active
|  | Project Manager: | NA for type Location |  |  | ….
Show
|  | Leave |  | Attendance |  | Mobile |  | Fuel |  | Voucher
|  |  | Add |  | Edit |  |  | Save |  | Reset
List
| Company Name | Loc. / Clnt Code | Loc. / Clnt Name |  |  |  |  | Type | City | State | Country | Status
| Highbar Technocrat Ltd. | 1 | Head Office |  |  |  |  | Location | Navi Mumbai | Maharashtra | India | Active
Form Validations | [6 empty] | Database details
| Unique Validation on: | [6 empty] | Save data in following tables
| Location Code | [6 empty] | tbl_hmst_company
| Location Name | [6 empty] | tbl_hmst_company_Location
Mandatory Fields Validation on:
Location Code
Location Name
Company Code
Type
City
State
Country
Conditional Mandatory Validation on:
Project Manager: only for Type "Client"
Status: can be deactivated only if no Employees assigned to this Location / Client
Default Status selected: Active

## Employee Joining
Employee Joining | [10 empty] | X
[12 empty] | Male | Regular | Single
|  | Search Employee: | Enter Code | …. | [7 empty] | Female | Contract | Married
[12 empty] | Other | Consultant
Employee Code:
First Name:
Middle Name:
Last Name:
|  | Mother Name: |  |  |  |  | Select Photo
Email-Id:
|  | Mobile No: |  |  |  | Telephone:
|  | Birthdate: |  |  |  | Gender:
|  | Marrital Status: |  |  |  | Anniversary:
no. of Kids:
|  |  | Current Address |  |  |  | Permanent Address
Address:
City:
Pin:
State:
Country:
Joining & Posting Details
|  | Joining Date: |  |  |  | Employment: | Regular |  | Retirement Date:
|  | Location: |  |  |  | …. | Department: |  | ….
|  | Designation: |  |  |  | …. | Band: |  | ….
|  | Reporting Manager: |  |  |  | …. | Self Approver: |  | Leave eligibility:
Other Information
|  | Bank Name: |  |  |  |  | A/C No.: |  |  | IFSC Code:
|  | Aadhar Card No.: |  |  |  |  | PAN Card No.: |  |  | Passport No.:
|  | EPFO No.: |  |  |  |  | Pension A/C No.: |  |  | Super Annuation:
|  |  | Add |  | Edit |  | Save | Reset
Form Validations | [5 empty] | Database details
| Unique Validation on: | [5 empty] | Save data in following tables
| Employee Code | [5 empty] | tbl_Employee_Mst
| Email Id | [5 empty] | TBL_EMPLOYEE_LOCATION
| Mandatory Fields Validation on: | [5 empty] | TBL_EMPLOYEE_DEPARTMENT
| All Fields Marked in Red | [5 empty] | TBL_EMPLOYEE_DESIGNATION
| Conditional Mandatory Validation on: | [5 empty] | TBL_EMPLOYEE_BAND
| Anniversary & no. of kids: only for Married Employees | [5 empty] | TBL_EMPLOYEE_RM
tbl_Employee_OMStructure

## Employee Exit
Employee Exit | [10 empty] | X
[12 empty] | Male | New Prospectus | Resigned
|  | Search Employee: | Enter Code | …. | [7 empty] | Female | Not Happy with Boss | Taken Back
[12 empty] | Other | Not Specified | Terminated
Employee Code:
Employee Name:
Email-Id:
Mobile No.:
Gender:
Joining & Posting Details
|  | Joining Date: |  |  |  | Employment: | Regular |  | Retirement Date:
|  | Location: |  |  |  |  | Department:
|  | Designation: |  |  |  |  | Band:
|  | Resignation Date; |  |  |  | Exit Reason : | Not Specified
|  | Date of Separation : |  |  |  | Status: | Resigned
|  |  | Add |  | Edit |  | Save | Reset |  | Print Relieving Letter
Form Validations | [5 empty] | Database details
| Mandatory Fields Validation on: | [5 empty] | Save data in following tables
| Employee Code | [5 empty] | TBL_EMPLOYEE_EXIT
| Resignation Date | [5 empty] | Update data in following tables
| Exit Reason | [5 empty] | tbl_Employee_Mst: update fields;
| Date of Separation | [5 empty] | emp_status
| Resignation Status | [5 empty] | Resig_Date
Conditional Validation on:
Resignation Date:
Should be less than Date of Separation
Date of Separation
Should be greater than Resignation Date
Editable only if Resignation Status is Resigned / Terminated
Record cannot be modified if today's date is greater than date of Separation
Print Relieving letter option available only if Today's date >= Date of Separation

## Emp - Location ¦ Project Alloca
Location / Client Transfer (Allocation) | [8 empty] | X
|  | Search Employee: | Enter Code | ….
Employee Code:
Employee Name:
Email-Id:
Mobile No.:
Gender:
Current Location / Client:
|  | New Location / Client: |  |  |  | …. |  | With effect From:
|  | Reporting Manager: |  |  |  | ….
|  | Allocation History | Location / Client |  | With effect From |  | Till Date
|  |  | Save |  | Reset
Form Validations | [5 empty] | Database details
| Mandatory Fields Validation on: | [5 empty] | Save data in following tables
| Employee Code | [5 empty] | TBL_EMPLOYEE_LOCATION
| Location Code | [5 empty] | TBL_EMPLOYEE_RM
| With effect from date | [5 empty] | Update data in following tables
| Reporting manager | [5 empty] | tbl_Employee_Mst: update fields;
| Conditional Validation on: | [5 empty] | emp_location
| With Effect from date: | [5 empty] | tbl_Employee_OMStructure
should be greater than today
non editable while modifying / Edit
Till Date:
Null & Non editable for New Recrds
Auto Set Till Date = with effect from date - 1 of New record created for same Employee
New Location:
if a Location is changed for an employee i.e. new record created with different location
then all applied leaves of future date (i.e. Leaves for dates >= With effect from Date) should get auto cancelled and email to respective employee
non editable while modifying / Edit

## Emp - Department Mapping
Department Change | [8 empty] | X
|  | Search Employee: | Enter Code | ….
Employee Code:
Employee Name:
Email-Id:
Mobile No.:
Gender:
Current Department:
|  | New Department: |  |  |  | …. |  | With effect From:
|  | History | Department |  | With effect From |  | Till Date
|  |  | Save |  | Reset
Form Validations | [5 empty] | Database details
| Mandatory Fields Validation on: | [5 empty] | Save data in following tables
| Employee Code | [5 empty] | TBL_EMPLOYEE_DEPARTMENT
| Department | [5 empty] | tbl_Employee_OMStructure
| With effect from date | [5 empty] | Update data in following tables
tbl_Employee_Mst: update fields;
| Conditional Validation on: | [5 empty] | dept_id
| With Effect from date: | [5 empty] | department
should be greater than today
non editable while modifying / Edit
Till Date:
Null & Non editable for New Recrds
Auto Set Till Date = with effect from date - 1 of New record created for same Employee
New department:
if a Department is changed for an employee i.e. new record created with different Department, automatically HOD would change
then all Pending approvals of Leave, Attendance, Reimbursements to be shifted in the name of new HOD
non editable while modifying / Edit

## Reporting Manager Change
Reporting Manager Change | [8 empty] | X
|  | Search Employee: | Enter Code | ….
Employee Code:
Employee Name:
Email-Id:
Mobile No.:
Gender:
Current Location / Client:
Current Reporting Manager:
|  | New Reporting Manager: |  |  |  | …. |  | With effect From:
|  | History | Location | Reporting Manager |  | With effect From |  | Till Date
|  |  | Save |  | Reset
Form Validations | [5 empty] | Database details
| Mandatory Fields Validation on: | [5 empty] | Save data in following tables
| Employee Code | [5 empty] | TBL_EMPLOYEE_LOCATION
| Reporting manager | [5 empty] | TBL_EMPLOYEE_RM
| With effect from date | [5 empty] | Update data in following tables
tbl_Employee_Mst: update fields;
| Conditional Validation on: | [5 empty] | emp_location
| With Effect from date: | [5 empty] | tbl_Employee_OMStructure
should be greater than today
non editable while modifying / Edit
Till Date:
Null & Non editable for New Recrds
Auto Set Till Date = with effect from date - 1 of New record created for same Employee
Reporting manager
if a Reporting manager is changed for an employee i.e. new record created with different Reporting manager
then all Pending approvals of Leave, Attendance, Reimbursements to be shifted in the name of new Reporting Manager
non editable while modifying / Edit

## Schedulars
Schedulars |  |  | X
Schedular Leave Quota Calculation
Schedular to Run on 1st Day of Every Month
Schedular to Update PL & Timeoffs As per Leave Quota Table
Schedular Auto Leave cut generation
.5 days PL to be deducted for following conditions
if 9 hrs working not completed for a day with no OD/WFH/PL/SL/TO
if Intime > 10:00 AM & completed 9 hrs working
if intime > 10:00 AM & < 2:00 PM and completed 5 hrs Working with OD/WFH/PL/SL/TO in First Half
1 days PL to be deducted for following conditions
if working hrs less than 5 with no OD/WFH/PL/SL/TO
if Intime > 10:00 AM & left office before completing 9 hrs working with no OD/WFH/PL/SL/TO
if intime > 2:00 PM
no Intime out time records for the day and no OD/WFH/PL/SL/TO
.5 day PL should not be deducted for late coming in following conditions
If for a day OD/WFH/PL/SL/TO is applied including 1st half
If worked for >= 12 hrs on immediate previous working day, then 1 hrs late /early is allowed i.e. if intime is <= 11:00 am or 8 hrs working is allowed