## Sheet1
Sr No | Task Name | Duration | Start | Finish | Predecessors | Responsibility
1 | SAP Implementation at ISC | 105 days | Mon 23-12-24 | Thu 08-05-25
2 | Phase 1: S4 HANA Implementation | 105 days | Mon 23-12-24 | Thu 08-05-25
3 | Implementation | 83 days | Mon 23-12-24 | Tue 08-04-25
4 | Explore | 5 days | Mon 23-12-24 | Mon 30-12-24
5 | KDS/Development review | 5 days | Mon 23-12-24 | Mon 30-12-24
6 | Review of KDS/Development/RGS | 3 days | Mon 23-12-24 | Thu 26-12-24 |  | HBT/ISC
7 | Incorporate changes, if any | 1 day | Fri 27-12-24 | Fri 27-12-24 | 6 | HBT
8 | Signoff of KDS/Development/RGS | 1 day | Mon 30-12-24 | Mon 30-12-24 | 7 | ISC
9 | Realize | 56 days | Mon 23-12-24 | Tue 04-03-25
10 | SAP System | 10 days | Mon 23-12-24 | Sat 04-01-25
11 | Availability of SAP system | 5 days | Mon 23-12-24 | Mon 30-12-24 | 6SS | HBT
12 | Initial system settings | 5 days | Tue 31-12-24 | Sat 04-01-25 | 11 | HBT
13 | Functional Specifications | 6 days | Mon 30-12-24 | Sat 04-01-25
14 | Prepare functional specifications | 6 days | Mon 30-12-24 | Sat 04-01-25 | 7 | HBT
15 | Configure and Validate Baseline | 14 days | Mon 06-01-25 | Wed 22-01-25
16 | Configure Processes and Functions in golden master (100) | 7 days | Mon 06-01-25 | Tue 14-01-25 | 12,14 | HBT
17 | Transfer of Configuration to Dev testing | 1 day | Wed 15-01-25 | Wed 15-01-25 | 16 | HBT
18 | Unit testing-1 (Consultant) | 5 days | Thu 16-01-25 | Tue 21-01-25 | 17 | HBT
19 | Document and Resolve Issues | 5 days | Thu 16-01-25 | Tue 21-01-25 | 18SS | HBT
20 | Submit Unit Testing result & completion of baselune config | 1 day | Wed 22-01-25 | Wed 22-01-25 | 19 | HBT
21 | Core team training & UT | 11 days | Wed 22-01-25 | Tue 04-02-25
22 | Plan for Level-2 training (CTM) | 1 day | Wed 22-01-25 | Wed 22-01-25 | 20SS | HBT
23 | Making necessery training arrangement - PPT + tutorial | 2 days | Thu 23-01-25 | Fri 24-01-25 | 22 | HBT
24 | Conducting Level-2 Training (Module wise) | 3 days | Mon 27-01-25 | Wed 29-01-25 | 23 | HBT
25 | Unit Testing by Core team | 5 days | Thu 30-01-25 | Tue 04-02-25 | 24 | ISC
26 | Migration to SAP system | 40 days | Mon 23-12-24 | Wed 12-02-25
27 | Receipt of SAP server | 10 days | Mon 23-12-24 | Sat 04-01-25 | 6SS | ISC
28 | SAP client readiness | 7 days | Mon 06-01-25 | Tue 14-01-25 | 27 | HBT
29 | Migration of Config/Developments to new SAP client | 3 days | Wed 05-02-25 | Fri 07-02-25 | 25 | HBT
30 | Testing of Configuration & Developments | 3 days | Mon 10-02-25 | Wed 12-02-25 | 29 | HBT
31 | System Integration Test | 23 days | Thu 30-01-25 | Thu 27-02-25
32 | Integration test Plan | 2 days | Thu 30-01-25 | Fri 31-01-25
33 | Identify scenerios for Integration test | 2 days | Thu 30-01-25 | Fri 31-01-25 | 24 | HBT
34 | Write scripts for Integration test | 2 days | Thu 30-01-25 | Fri 31-01-25 | 33SS | HBT
35 | Conduct System integration test | 21 days | Sat 01-02-25 | Thu 27-02-25
36 | Perform Integration testing by Consultant | 7 days | Sat 01-02-25 | Mon 10-02-25 | 34 | HBT
37 | Perform User Acceptance test - CTM | 10 days | Tue 11-02-25 | Fri 21-02-25 | 36 | ISC
38 | Resolving the issues, if any | 10 days | Tue 11-02-25 | Fri 21-02-25 | 37SS | HBT
39 | Retesting of scenarios | 3 days | Mon 24-02-25 | Wed 26-02-25 | 38 | ISC
40 | UAT (by CTM) signoff | 1 day | Thu 27-02-25 | Thu 27-02-25 | 39 | ISC
41 | ABAP Development - UAT critical | 39 days | Wed 15-01-25 | Tue 04-03-25
42 | Develop reports | 30 days | Wed 15-01-25 | Thu 20-02-25 | 16 | HBT
43 | Testing by consultant | 30 days | Sat 18-01-25 | Tue 25-02-25 | 42SS+3 days | HBT
44 | Testing by CTM | 30 days | Wed 22-01-25 | Fri 28-02-25 | 43SS+3 days | ISC
45 | Sign off Development | 30 days | Mon 27-01-25 | Tue 04-03-25 | 44SS+3 days | ISC
46 | Cutover Strategy | 4 days | Fri 28-02-25 | Tue 04-03-25
47 | Discussion on cutover strategy | 2 days | Fri 28-02-25 | Sat 01-03-25 | 40 | ISC & HBT
48 | Cutover & data responsibility Plan | 2 days | Mon 03-03-25 | Tue 04-03-25 | 47 | ISC & HBT
49 | Communication to Organisation for Cutover | 1 day | Tue 04-03-25 | Tue 04-03-25 | 48FF | ISC
50 | End user training plan | 4 days | Mon 24-02-25 | Thu 27-02-25
51 | Preparation of End User training plan | 2 days | Mon 24-02-25 | Tue 25-02-25 | 37 | ISC & HBT
52 | Communicate plan to ISC | 1 day | Wed 26-02-25 | Wed 26-02-25 | 51 | ISC
53 | Completion of Realization Phase | 1 day | Thu 27-02-25 | Thu 27-02-25 | 40FF | ISC
54 | Deliverables | 33 days | Wed 22-01-25 | Tue 04-03-25
55 | D: Test scripts | 1 day | Sat 01-02-25 | Sat 01-02-25 | 34 | HBT
56 | D: Unit test result document | 1 day | Wed 22-01-25 | Wed 22-01-25 | 18 | HBT
57 | D: Integration testing document | 1 day | Tue 11-02-25 | Tue 11-02-25 | 36 | HBT
58 | D: User Acceptance testing document | 1 day | Thu 27-02-25 | Thu 27-02-25 | 40FF | HBT
59 | D: Final master data templates | 1 day | Tue 04-03-25 | Tue 04-03-25 | 49FF | HBT
60 | D: Data migration strategy document | 1 day | Tue 04-03-25 | Tue 04-03-25 | 49FF | HBT
61 | Deploy | 82 days | Mon 23-12-24 | Mon 07-04-25
62 | Coordinate ABAP Development - Go Live critical | 30 days | Fri 21-02-25 | Mon 31-03-25
63 | Develop reports | 22 days | Fri 21-02-25 | Thu 20-03-25 | 42 | HBT
64 | Testing by consultant | 22 days | Wed 26-02-25 | Tue 25-03-25 | 63SS+3 days | HBT
65 | Testing by CTM | 22 days | Fri 28-02-25 | Thu 27-03-25 | 64SS+2 days | ISC
66 | Sign off Development | 22 days | Tue 04-03-25 | Mon 31-03-25 | 65SS+3 days | ISC
67 | End User Training | 16 days | Fri 28-02-25 | Wed 19-03-25
68 | Prepare end user training manual | 3 days | Fri 28-02-25 | Mon 03-03-25 | 40 | HBT
69 | Conduct end user training | 10 days | Tue 04-03-25 | Sat 15-03-25 | 68 | ISC
70 | Conduct training to HODs/Management | 3 days | Mon 17-03-25 | Wed 19-03-25 | 69 | ISC
71 | Production Environment Preparation | 3 days | Fri 28-02-25 | Mon 03-03-25
72 | Transport final configurations | 1 day | Fri 28-02-25 | Fri 28-02-25 | 40 | HBT
73 | Maintain number ranges | 1 day | Sat 01-03-25 | Sat 01-03-25 | 72 | HBT
74 | Maintain client specific data | 1 day | Mon 03-03-25 | Mon 03-03-25 | 73 | HBT
75 | User creation | 17 days | Thu 27-02-25 | Wed 19-03-25
76 | Finalize list of users for production enviornment | 2 days | Thu 27-02-25 | Fri 28-02-25 | 52 | ISC & HBT
77 | Finalise Authorization Matrix | 3 days | Sat 01-03-25 | Tue 04-03-25 | 76 | ISC & HBT
78 | Check roles and authorization | 3 days | Mon 17-03-25 | Wed 19-03-25 | 69 | ISC & HBT
79 | Data preparation and upload | 81 days | Mon 23-12-24 | Fri 04-04-25
80 | Receipt of master data | 65 days | Mon 23-12-24 | Sat 15-03-25 | 6SS | ISC
81 | Validate & cleanse master data | 1 day | Mon 17-03-25 | Mon 17-03-25 | 80 | ISC
82 | Upload master data in Production | 5 days | Mon 17-03-25 | Fri 21-03-25 | 81SS | ISC & HBT
83 | Confirm uploaded master data | 1 day | Mon 24-03-25 | Mon 24-03-25 | 82 | ISC
84 | Receipt of cutover data | 5 days | Tue 25-03-25 | Sat 29-03-25 | 83 | ISC
85 | Validate & cleanse cutover data | 5 days | Tue 25-03-25 | Sat 29-03-25 | 84SS | ISC
86 | Upload cutover data in production | 5 days | Mon 31-03-25 | Fri 04-04-25 | 84,82 | ISC & HBT
87 | Check and validate uploaded data | 1 day | Fri 04-04-25 | Fri 04-04-25 | 86FF | ISC
88 | Deliverables | 20 days | Sat 01-03-25 | Wed 26-03-25
89 | D: End user training manual | 3 days | Tue 04-03-25 | Thu 06-03-25 | 68 | HBT
90 | D: Data migration plan & checklist | 3 days | Mon 17-03-25 | Wed 19-03-25 | 80 | HBT
91 | D: Master data upload programs | 3 days | Mon 24-03-25 | Wed 26-03-25 | 82 | HBT
92 | D: Sample data upload validation | 1 day | Mon 24-03-25 | Mon 24-03-25 | 82 | HBT
93 | D: Final SAP Authorization matrix | 1 day | Sat 01-03-25 | Sat 01-03-25 | 76 | HBT
94 | Obtain Approval & phase Sign Off | 1 day | Mon 07-04-25 | Mon 07-04-25
95 | Deploy signoff | 1 day | Mon 07-04-25 | Mon 07-04-25 | 87 | ISC
96 | Completion of Final Preparation (Deploy) Phase | 1 day | Mon 07-04-25 | Mon 07-04-25 | 95FF | ISC
97 | Go Live | 1 day | Tue 08-04-25 | Tue 08-04-25 | 95 | ISC & HBT
98 | Stabilization | 22 days | Wed 09-04-25 | Thu 08-05-25
99 | Stabilization | 22 days | Wed 09-04-25 | Thu 08-05-25 | 97 | ISC & HBT
100 | Deliverables | 22 days | Wed 09-04-25 | Thu 08-05-25
101 | D: Issue list with resolution status | 22 days | Wed 09-04-25 | Thu 08-05-25 | 99SS | HBT
102 | D: Configuration documents | 22 days | Wed 09-04-25 | Thu 08-05-25 | 99SS | HBT
103 | D: FS & TS | 22 days | Wed 09-04-25 | Thu 08-05-25 | 99SS | HBT
104 | D: Cre team training document | 22 days | Wed 09-04-25 | Thu 08-05-25 | 99SS | HBT

## Sheet2
Start Date | 2024-12-23
Golive Date | 2025-04-08
Days | 106
Current date | 2024-12-31
Completed | 8
Balance day | 98