## Plan For pending task
ISC Project Plan for remaining work (Verson 3) -16-08-2024
Revised plan for Wave 1A and Wave 1B |  | Plan
Activity |  | Start Date | End Date | Responsibility
Completion of developments
| Bank Interface - Golive object | 2024-08-01 | 2024-08-28 | HBT | Nikhil
| DRC integration -ASP/GSP | 2024-08-01 | 2024-08-28 | HBT | Rahul
| E-Invoice & E Way Bill format completion (Dependency of DRC) | 2024-08-28 | 2024-08-31 | HBT | Rahul
| Payement approval - Observation changes | 2024-08-01 | 2024-08-21 | HBT | Rajiv Singh
| KEKA interface development | 2024-08-20 | 2024-08-30 | HBT | Rajiv Singh
| C4C pending development activities | 2024-08-01 | 2024-08-28 | HBT | Sumeet
UAT
| FICO | 2024-08-16 | 2024-08-26 | ISC & HBT | Rajiv
| C4C pending development process | 2024-08-20 | 2024-08-26 | ISC & HBT | Sumeet
| Signoff of UAT | 2024-09-27 | 2024-09-28 | ISC & HBT
Roles and Authorisation
| Prepare Roles & Authorization matrix | 2024-08-02 | 2024-08-25 | ISC & HBT
| Approval from ISC | 2024-08-08 | 2024-08-25 | ISC & HBT
| Assign Roles & authorizattion | 2024-08-10 | 2024-08-25 | ISC & HBT
| Test authorizations & UAT | 2024-08-12 | 2024-08-25 | ISC & HBT
End User Training
| Prepare end user plan (List of user, Date,time, Process cover, Faculty CTM) | 2024-08-19 | 2024-08-20 | ISC & HBT
| Circulate Plan to end user | 2024-08-20 | 2024-08-20 | ISC & HBT
| Ensure End user ID , role and authorisation, network, system available for end user | 2024-08-21 | 2024-08-21 | ISC & HBT
| End User Training | 2024-08-22 | 2024-08-28 | ISC & HBT
| End User Training -FICO | 2024-08-28 | 2024-08-30 | ISC & HBT
Prodcution system readiness
| Production Readyness | 2024-08-01 | 2024-08-03 | HBT
| TR Movement - Config and Custome | 2024-08-05 | 2024-08-30 | HBT
| Number range assigment | 2024-08-09 | 2024-08-10 | HBT
Master Data upload
| Receipt of master data (Independent) | 2024-08-09 | 2024-08-22 | ISC
| Upload data in Production server | 2024-08-10 | 2024-08-25 | HBT
| Checking of upload data | 2024-08-10 | 2024-08-26 | ISC
| Approval of upload data | 2024-08-09 | 2024-08-26 | ISC
| Preparation of Master data template for dependent master data | 2024-08-11 | 2024-08-28 | ISC
| Receipt of master data (dependent) | 2024-08-12 | 2024-08-28 | ISC
| Upload data in Production server | 2024-08-29 | 2024-09-04 | HBT
| Checking of upload data | 2024-09-04 | 2024-09-04 | ISC
| Approval of upload data | 2024-09-05 | 2024-09-05 | ISC
Cut off date
|  | 2024-08-31 | 2024-08-31 | ISC & HBT
Cut Over data as on 20.07.2024
| Prepare cut over data | 2024-08-31 | 2024-09-07 | ISC
| Receipt of cutover data | 2024-09-08 | 2024-09-12 | ISC
| Upload data in Production server | 2024-09-09 | 2024-09-15 | HBT
| Checking of upload data | 2024-09-16 | 2024-09-17 | ISC
| Approval of upload data | 2024-09-16 | 2024-09-17 | ISC
Golive
| User ID test - before golive | 2024-09-18 | 2024-09-18 | ISC & HBT
| Identification of T Code for golive | 2024-09-18 | 2024-09-18 | ISC & HBT
| T Code readiness check | 2024-09-18 | 2024-09-18 | ISC & HBT
| First Transaction by MD and Decleare golive | 2024-09-18 | 2024-09-18 | ISC
Post Golive - Critical care support
| Set up helpdesk mechanism | 2024-09-18 | 2024-09-18 | ISC & HBT
| Issue resolution againt issue ticket | 2024-09-18 | 2024-10-28 | ISC & HBT
| Prepare issue list with solution details | 2024-09-18 | 2024-10-28 | ISC & HBT
| Hand over process to AMC team | 2024-10-18 | 2024-10-28 | ISC
Wave 1C-Dashboard - SAC Analytic development
| SAC system readiness for dashboard development | 2024-08-20 | 2024-08-25 | ISC & HBT
| Creation of user ID | 2024-08-25 | 2024-08-25 | HBT
| Finalisation of User Interface Design (UID) | 2024-08-26 | 2024-08-27 | ISC & HBT
| Finalisation 10 number dashboard (Max 03 KPI/DB) | 2024-08-28 | 2024-08-31 | ISC & HBT
| Preparation of Requirment finalisation document | 2024-08-28 | 2024-08-31 | HBT
| Sighnoff dashboard requirement final document | 2024-09-01 | 2024-09-01 | ISC
| Preparation of FS | 2024-09-02 | 2024-09-09 | HBT
| CDS preparation for dashboard | 2024-09-04 | 2024-09-12 | HBT
| Dashboard design | 2024-09-06 | 2024-09-15 | HBT
| Dashboard testing by HBT | 2024-09-07 | 2024-09-16 | HBT
| Observation and correction | 2024-09-08 | 2024-09-17 | HBT
| Dashboard testing by ISC | 2024-09-09 | 2024-09-20 | ISC
| Observation and correction | 2024-09-10 | 2024-09-22 | HBT
| Final testing | 2024-09-12 | 2024-09-24 | ISC
| Sighnoff dashboard completion | 2024-09-12 | 2024-09-25 | ISC
| Export in Production system | 2024-09-14 | 2024-09-27 | HBT
| Golive - Dashboard | 2024-09-28 | 2024-09-28 | ISC