## FRICEW LIST
Sr.No | Module | Functionality | Development List | Type of Dev | Overall Status | Sign off Status | Document link | Changes/New Dev | RGS Required | ABAP Resource | Expected Timelines | Status
1 | PS | Estimation | Cost Plan Upload Program |  | PRD | Signoff Doc Attached | 4.PS Module\3.UAT\UAT_Approval_BOQ_Costplanupload_project details_Budget_Noida.pdf
2 | PS | Estimation | Execution BOQ Master |  | PRD | Signoff Doc Attached | 4.PS Module\3.UAT\UAT_Approval_BOQ_Costplanupload_project details_Budget_Noida.pdf
3 | PS | Estimation | Material and Services Planned against each WBS |  | PRD | Signoff Doc Attached | 4.PS Module\3.UAT\UAT_Approval_BOQ_Costplanupload_project details_Budget_Noida.pdf
4 | PS | Estimation | Cost Plan Vs Budget Allotted Vs Commitment Vs Actual and Advances at Project Definition Level |  | PRD | Signoff Doc Attached | 4.PS Module\3.UAT\UAT_Approval_BOQ_Costplanupload_project details_Budget_Noida.pdf
5 | PS | Estimation | WBS Wise detailed Breakup of work order |  | PRD | Signoff Doc Attached | 4.PS Module\3.UAT\UAT_Approval_WBS_Wise detailed breakup of work order_Noida.pdf
6 | MM | Purchase | Purchase Register |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/2.MM%20Module/3.UAT/Script%20Sign-offs/UAT-%20Purchase%20Register%20Report_Noida.pdf
7 | MM | Purchase | Additional fields in MM60 Report |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT- Additional fields in MM60 Report_Gurgao&Noida.pdf
8 | MM | Purchase | Amendemnt Report for PO |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT- PO Amendment Report_Noida.pdf
9 | MM | Purchase | Purchase Order Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
10 | MM | Purchase | Tax code validation in PO based on Plant & Vendor region code |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf
11 | MM | Purchase | Validation on Plant in material master based on the profit center |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_5.pdf
12 | MM | Purchase | Validation for PO Plant with WBS Plant |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf
13 | MM | Purchase | Freight/Custom duty Order Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT- Freight and Custom duty order print_Noida.pdf
14 | MM | Stores | Purchase Requisition Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
15 | MM | Stores | Material Issue Print | sss | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
16 | MM | Stores | MIGO screen- additional tab to be captured for additional data at header level |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
17 | MM | Stores | Quantity check validation in PR with WBS for Material |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_3-Saugata.pdf
18 | MM | Stores | Auto material transfer from WBS stock to plant stock after GRN (101Q) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
19 | MM | Stores | Validation for PR Plant with WBS Plant |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Validation for PR Plant with WBS Plant.msg
20 | MM | Stores | Addition Tab in PR header for Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
21 | MM | Stores | GRN Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
22 | MM | Stores | Stock Transfer Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
23 | MM | Stores | Contractor GRN Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
24 | QM | Quality | UD Mail Notification |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/Lab_Report_Extra_Attach_Material%20Assignment_Post%20Go-Live_Signoff_Noida.pdf
25 | QM | Quality | Reverse Stock Posting from Quality ( UD Reverse ) |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/Lab_Report_Extra_Attach_Material%20Assignment_Post%20Go-Live_Signoff_Noida.pdf
26 | QM | Quality | Report attachment on Result Record during mail trigger |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/Lab_Report_Extra_Attach_Material%20Assignment_Post%20Go-Live_Signoff_Noida.pdf
27 | QM | Quality | Extra attachment on the mail trigger |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/Lab_Report_Extra_Attach_Material%20Assignment_Post%20Go-Live_Signoff_Noida.pdf
28 | QM | Quality | ARN Number Generation |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
29 | QM | Quality | ARN Report details |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
30 | QM | Quality | Result Record Report - Smartform |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
31 | QM | Quality | Report Mail Notification |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
32 | QM | Quality | ARN Print - BARCODE Machine Form - Smartform |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
33 | QM | Quality | Inspection Plan Upload |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
34 | QM | Quality | MIC Quantitative |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
35 | QM | Quality | Result Record Report |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/ARN%20Generation_Barcode%20Print_Report_Print,%20Upload%20tool_Noida.pdf
36 | QM | Quality | Inspection Plan assignment to Material |  | PRD | Signoff Doc Attached | file://192.168.100.4/SAP-Doc/3.%20SAP%20Scope%20and%20BBP%20Documents/5.QM%20Module/3.UAT/Lab_Report_Extra_Attach_Material%20Assignment_Post%20Go-Live_Signoff_Noida.pdf
37 | MM | Contracts | Quantity check validation in PO with WBS for Service |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
38 | MM | Contracts | Work Order Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
39 | MM | Contracts | Custom Screen for WO creation/change/display to fetch data from BOQ along with Payment terms at header & line item level. |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
40 | MM | Contracts | WO terms & condition Header |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
41 | MM | Contracts | FOC Materials to be issued against Work Order |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
42 | MM | Contracts | Advance Request for RA Bill |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
43 | MM | Contracts | WO T&C for General Escalation (Item) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
44 | MM | Contracts | Advance requisition should not be more than remaining PO amount (PO amount- Bill Booked Amount) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
45 | MM | Contracts | Service Requisition Print (non-projects) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT-Service Requisition Print_Noida.pdf
46 | MM | Billing | Payment abstract Report |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT- Payment Abstract Report_Noida.pdf
47 | MM | Billing | Approval Matrix for RA Bill process |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT-Approval Matrix for RA bill Process_Noida.pdf
48 | MM | Billing | Abstract Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Payment Abstract Sign off.msg
49 | MM | Billing | Price Variance Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
50 | MM | Billing | RA BILL Preparation_Work done quantity confirmation against Work order with SES posting |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
51 | MM | Billing | Payment abstract Print (COP) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
52 | MM | Billing | General Item Escalation Calculation |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
53 | MM | Billing | Service BOM |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
54 | MM | Billing | Necessary controls to be built in Coefficient customised screen so as to trigger necessary approvals for changes made in the theoretical coefficient, allowable wastage and base rate. (Contractor material tagging with WO) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
55 | MM | Billing | Price variation escalation |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
56 | MM | Billing | Advance Recovery against RA Bill |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
57 | MM | Billing | Posting of invoice,recovery,debit note,credit note,etc document along with Payment abstract screen |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
58 | MM | Billing | Reconciliation & Recovery of FOC Materials issued against Work done |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
59 | MM | Billing | Subcon Billing Screen (all subcon tcodes in one screen) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
60 | MM | Billing | ML81N not allowed for RA Bill WO document Types |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_4-Devidayal.pdf
61 | MM | Billing | Delete program for Ra bill process |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
62 | MM | Billing | SOB Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
63 | FICO | Accounts | Bank Integration1- To Bank - ICICI |  | Hold | Signoff Doc Not Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
64 | FICO | Accounts | Bank Integration2- To Bank |  | Hold | Signoff Doc Not Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_3-Saugata.pdf
65 | FICO | Accounts | Bank Integration3- To Bank |  | Hold | Signoff Doc Not Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
66 | FICO | Accounts | Prolect Integration ( Payroll Integration ) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\68. Employee payments and HR Payroll_noida.pdf
67 | FICO | Accounts | Bill Wise Payment Details Register |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\69. ZPAYR PAYMENT WISE BILL REGISTER_noida.pdf
68 | FICO | Accounts | Payment Request Register |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\69. ZPAYR PAYMENT WISE BILL REGISTER_noida.pdf
69 | FICO | Accounts | Interest calculation |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\SOA for Testing_Noida.msg
70 | FICO | Sales | Customer Receipt Report |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\73. Customer Receipt Register Signoff_Noida.pdf
71 | FICO | Accounts | Vendor/Customer Duplication Check |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\74. Vendor Master Duplication Check_noida.pdf
72 | FICO | Accounts | Cash flow Report |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\76. cash flow sign off_noida.pdf
73 | FICO | Accounts | Vendor Aging Report |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\77. Vendor Aging Report Signoff_noida.pdf
74 | FICO | Sales | Customer Ageing Report |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\78. Customer Aging and DAYBOOK_noida.pdf
75 | FICO | Accounts | Bank Cheque Print ICICI bank |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\CHEQUE PRINT.pdf
76 | FICO | Accounts | Bank Cheque Print Kotak Mahindra bank |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\CHEQUE PRINT.pdf
77 | FICO | Accounts | FBL1N ( Vendor Line Item Report) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\81. Vendor Ledger Signoff_noida.pdf
78 | FICO | Accounts | FBL3N ( GL Line Item Report) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\82. ledger enchancement sign off.pdf
79 | FICO | Accounts | FBL5N ( Customer Line item Report) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\Sign off\FBL5N (Customer Line item report).pdf
80 | FICO | Accounts | TDS Paybale Report |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\84. TDS Report Signoff_Noida.pdf
81 | FICO | Accounts | TDS Receivable Report |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\TDS Receivable Report_Noida.pdf
82 | FICO | Accounts | GL Upload Program |  | PRD | Conversion
83 | FICO | Accounts | Vendor Master Upload Program |  | PRD | Conversion
84 | FICO | Accounts | Asset Master Data Upload Program |  | PRD | Conversion
85 | FICO | Accounts | F-28 Bapi for payment receipt of historical data |  | PRD | Conversion
86 | FICO | Sales | Customer Master Upload Program |  | PRD | Conversion
87 | FICO | Accounts | F-29 BDC FOR Advance from Customer Historical Data |  | PRD | Conversion
88 | FICO | Accounts | GSTR-1 |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\92. GSTR1 report sign off_noida.pdf
89 | FICO | Accounts | GSTR-2 |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\93. GSTR2 Reprt Signoff_noida.pdf
90 | FICO | Accounts | GSTR-3B |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\94. GSTR3B Sign off_noida.pdf
91 | TRM | Accounts | BG alert in Case of Mobilization Advance |  | PRD | Signoff Doc Attached
92 | SD | Sales | Mutation |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Buyer transfer. Death case. name addition. Name deletion. name substitutation.Nmae mutation.Main applicant change_Noida.msg
93 | SD | Sales | Name Addition |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Buyer transfer. Death case. name addition. Name deletion. name substitutation.Nmae mutation.Main applicant change_Noida.msg
94 | SD | Sales | Name Deletion |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Buyer transfer. Death case. name addition. Name deletion. name substitutation.Nmae mutation.Main applicant change_Noida.msg
95 | SD | Sales | Name Substitution |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Name Addition,Name Deletion,Name substitution,Death Case,Name Mutation,Buyer transfer,Main Applicant change\Re Requesting for Sign-off.msg
96 | SD | Sales | Conveyance Deed |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-off PDF SD\Notice of offer Possession and Conveyance deed UAT SIGN- Off.pdf
97 | SD | Sales | Buyer Transfer Letter |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Buyer transfer. Death case. name addition. Name deletion. name substitutation.Nmae mutation.Main applicant change_Noida.msg
98 | SD | Sales | NOC in Death Case |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Buyer transfer. Death case. name addition. Name deletion. name substitutation.Nmae mutation.Main applicant change_Noida.msg
99 | SD | Sales | Notice for Offer of Possession |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-off PDF SD\Notice of offer Possession and Conveyance deed UAT SIGN- Off.pdf
100 | SD | Sales | Pre hand over - RSD Creation (Including UI,Tables,Mapping,ALV) |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
101 | SD | Sales | Pre hand over - RSD Approval (Including Tables,Mapping,ALV) |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
102 | SD | Sales | Pre hand over - Co-Allotees Bifurcation Declaration (Report, Workflow,UI) |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
103 | SD | Sales | Pre hand over - Calculation Starts Accumulation Report - Interactive Runtime Report |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
104 | SD | Sales | Pre hand over - Calculation Starts Payout Report - Interactive Runtime Report |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
105 | SD | Sales | Pre hand over - Collective Accumulation Report |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
106 | SD | Sales | Pre hand over - Parking Finance Document - Payout Case |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
107 | SD | Sales | Pre hand over - BRS Entry (Including Tables,Mapping,ALV,Start/End Date Determination) |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
108 | SD | Sales | Pre hand over - Workflow on demand note accumulated value |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
109 | SD | Sales | Pre hand over - Payout Entry post as per Vendor TDS %. |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
110 | SD | Sales | Pre hand over - Notification to be trigger for payout entries |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Fwd Pre-Handover UAT Feedback.msg |  |  |  | 2024-06-29
111 | SD | Sales | Brokerage - Normal Master |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
112 | SD | Sales | Brokerage - Special Master |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
113 | SD | Sales | Brokerage - To be Disburse Master |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
114 | SD | Sales | Brokerage - Ratio Master |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
115 | SD | Sales | Brokerage - Program Collection Wise Calculation |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
116 | SD | Sales | Brokerage - Payment Plan Wise Calculation |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
117 | SD | Sales | Brokerage - Calculation Approval (Release) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
118 | SD | Sales | Brokerage - Report |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
119 | SD | Sales | Brokerage - FI Park and Post Report with Workflow & Notification |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
120 | SD | Sales | Auto GST Reversal - Calculation Module Pool |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
121 | SD | Sales | Auto GST Reversal - Forfeiture Calculation Process |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
122 | SD | Sales | Auto GST Reversal - Post Credit memo Program |  | UAT | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
123 | SD | Sales | Auto GST Reversal - Gst Posting Program |  | UAT | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
124 | SD | Sales | Auto GST Reversal - JV Creation/Upload Program(FI)/Forfeiture Amt Posting |  | UAT | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
125 | SD | Sales | Auto GST Reversal - GST Credit memo Process(FI) |  | UAT | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
126 | SD | Sales | Auto GST Reversal - Pricing calculation on credit request |  | UAT | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\FW Auto GST reversal Sign off UAT.msg |  |  |  | 2024-07-01
127 | SD | Sales | PDR- Property detail report Billed |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\PDR Report Sign off_Noida.msg
128 | SD | Sales | Mass Print (Where all forms will print) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Mass Print UAT.pdf
129 | SD | Sales | Residential Allotment Letter Noida |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\NOIDA\LAVISH\Sign-off_Lavish_Allotment_letter.pdf
130 | SD | Sales | Commercial Allotment Letter Noida |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\SAP output smart form Welcome +Residential and Commercial Allotment letter noida .msg
131 | SD | Sales | BBA Letter For Panipat |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Signoff_BBA_Panipat_&_Mass_Invoice_Noida.msg
132 | SD | Sales | Date Validation in VA01 and VA02 |  | PRD | Signoff Doc Not Attached
133 | SD | Sales | Additional fields at the Order level to maintain details Like loan information, Money receipt |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Additional fields at the Order level to maintain details Like loan information_Panipat.msg
134 | SD | Sales | Status Change of Material Master /Error message pop in sales order if the unit is already sold or block. |  | PRD | Signoff Doc Not Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Customer_Master_Update_API_Signoff.msg"
135 | SD | Sales | Welcome Letter + Allotment letter (Panipat) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\PANIPAT\Sign-off_Panipat_Allotment, demand , TPR, TPD, Customer Ledger, Receipt, Credit & Debit Memo.pdf
136 | SD | Sales | Provisional Receipt |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Normal,Provisional Reciept_Noida.msg
137 | SD | Sales | Demand Note (invoice standard) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Sign-off_Demand_Note_Noida.msg
138 | SD | Sales | Customer Reciept |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Panipat Uat Sign off\Allotment Letter,TPR,TPD,Payment Reciept,Customer Ledger,Demand Letter,Credit,Debit Memmo.msg
139 | SD | Sales | Customer Ledger (Smartform) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Panipat Uat Sign off\Sales Order,Customer Master,CP,Customer Ledger.msg
140 | SD | Sales | Car Parking Allotment Report |  | PRD | Signoff Doc Not Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\RE M3M - Post Sales - UAT Initiate.msg"
141 | SD | Sales | Unit availability Report |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\MassPrint.UnitAvblRpt.CustLedger.DOBDOA.pdf
142 | SD | Sales | Timely Payment Receipt (TPR) |  | RGS | Signoff Doc Not Attached |  |  |  |  | 2024-07-17
143 | SD | Sales | Timely Payment Discount (TPD) |  | RGS | Signoff Doc Not Attached |  |  |  |  | 2024-07-17
144 | SD | Sales | Sales Order Data Historical |  | PRD | Conversion
145 | SD | Sales | Invoice Data Historical |  | PRD | Conversion
146 | SD | Sales | Program for Historical Data Upload |  | PRD | Conversion
147 | SD | Sales | Statement of Account Report (SOARS) |  | PRD | Signoff Doc Not Attached
148 | SD | Sales | Date of Birth/ Anniversary Date |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\MassPrint.UnitAvblRpt.CustLedger.DOBDOA.pdf
149 | SD | Sales | Demand Note For PLot |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\PANIPAT\Sign-off_Panipat_Demand Note plot.pdf
150 | SD | Sales | Allotment Letter For Noida |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\NOIDA\LAVISH\Sign-off_Lavish_Allotment_letter.pdf
151 | SFDC/SD | Sales | Unit Master-manras |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Seven_Number API_Signoff.msg
152 | SFDC/SD | Sales | Customer Creation-HBT |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Customer_Master_Creation_API_Signoff.msg
153 | SFDC/SD | Sales | Price Master-HBT |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Seven_Number API_Signoff.msg
154 | SFDC/SD | Sales | Unit Status-HBT |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Seven_Number API_Signoff.msg
155 | SFDC/SD | Sales | Unit Status-Manras |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Seven_Number API_Signoff.msg
156 | SFDC/SD | Sales | Price Master-Manras |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Seven_Number API_Signoff.msg
157 | SFDC/SD | Sales | Payment Plan (GET API)-HBT |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Finance_API_Signoff.pdf"
158 | SFDC/SD | Sales | Payment Plan-Manras |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Seven_Number API_Signoff.msg"
159 | SFDC/SD | Sales | Booking/Sales Order-HBT |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Sales order_API_Signoff.msg"
160 | SFDC/SD | Sales | Payment Advance Status-Manras |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Finance_API_Signoff.pdf"
161 | SFDC/SD | Sales | Payments-Manras |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Finance_API_Signoff.pdf"
162 | SFDC/SD | Sales | Demand-Manras |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Finance_API_Signoff.pdf"
163 | SFDC/SD | Sales | Customer Update-HBT |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Customer_Master_Creation_API_Signoff.msg"
164 | FICO | Sales | Customer Receipt Workflow |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\146. ZAPPROVE & ZRECEIPT_Noida.pdf
165 | FICO | sales | Customer advance clearing form |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\147. Customer Receipt clearing form.pdf
166 | FICO | Sales | Payment amount is greater than invoice (clearing form) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\148. Payment amount is greater then Invoice Signoff.pdf
167 | FICO | Sales | Customer Reciept 2 |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\149. Payment amount is greater then Invoice Signoff.pdf
168 | FICO | Accounts | Accounting Entry Print (For Advance) |  | PRD
169 | FICO | Sales | Dunning Form (Pre-Cancellation Draft After OOP) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\150. Dunning form pre canellation.pdf
170 | FICO | Sales | Dunning Form (Pre-Cancellation Draft Before OOP) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\151. Dunning form post canellation.pdf
171 | MM | Purchase | Base Price Variation report |  | PRD
172 | FICO | Sales | Dunning for cancellation Notice |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\151. Dunning form post canellation.pdf
173 | FICO | Accounts | ZFF67 Bank Reconciliation |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Sign-off_Scrap Sales order Print.msg
174 | SFDC/SD | Sales | Payment Advance EOI |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Finance_API_Signoff.pdf"
175 | SFDC/SD | Sales | Cancellation request-HBT |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
176 | SFDC/SD | Sales | cancellation Reques Status-Manras |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
177 | SFDC/SD | Sales | Transfer Request-HBT |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
178 | SFDC/SD | Sales | Transfer Request Status-Manras |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
179 | SFDC/SD | Sales | ATS Request-HBT |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
180 | SFDC/SD | Sales | ATS Doc status-Manras |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
181 | SFDC/SD | Sales | Bank Loan Request-HBT |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
182 | SFDC/SD | Sales | Booking/Sales Order update-manras |  | Not Started | Signoff Doc Not Attached |  |  |  |  | TBD
183 | SD | Sales | Tax Invoice for scrap sale |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Tax Scrap_Sale_Invoice_Noida.pdf
184 | SD | Sales | Scrap Sales order Print |  | PRD | Signoff Doc Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\NOIDA\LAVISH\Scrap Sales order Print.pdf"
185 | SFDC/SD | Accounts | Channel Partner Status API |  | PRD
186 | SD | Sales | Scrap Delivery Challan Print |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Scrap_delivery_challan_Panipat.msg
187 | FICO | Sales | Incoming Payment Tracking |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Report-Due as per payment plan_Noida.msg
188 | PS | Estimation | Custom workflow for Budget creation (Budgeting Manager) and approval (Budgeting Head). |  | PRD | Signoff Doc Attached | 4.PS Module\3.UAT\UAT_Approval_Budget Approval workflow_29.09.2023.pdf
189 | MM | Contracts | Control to be develop in system for HSN Master.6 digit or 8 Digit HSN Code for Material should be allowed |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT SR wrt to BOQ_Noida.pdf
190 | MM | Billing | Necessary controls to be built in Coefficient customised screen so as to trigger necessary approvals for changes made in the theoretical coefficient, allowable wastage and base rate. (FOC material tagging with WO) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
191 | MM | Billing | System enable checkpoints and document attachment should be mandatory for reviewing RA bill certification |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
192 | FICO | Accounts | In absence of this system control, single document will have 2 different business place will lead to inconsistence of data and compliance issue |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Vendor Master Duplication Check 1.pdf
193 | FICO | Accounts | There is no visibility to vendor for payment breakup for the payment received from company since no vendor payment advice is sent to him. |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Vendor Master Duplication Check 1.pdf
194 | FICO | Accounts | Company Code wise Vendor master report required |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\180. Vendor Master Report_noida.pdf
195 | FICO | Accounts | Journal Voucher print to be devloped |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\181. JV & Payment Advice.pdf
196 | FICO | Accounts | Daybook Report from SAP |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\182. Customer Aging and DAYBOOK_noida.pdf
197 | SD | Sales | Customized validation for WBS element in the material master update to ensure that correct project data/WBS is mapped into the material master |  | PRD | Signoff Doc Not Attached
198 | SD | Sales | Automation through custom solution/cockpit can be used to avoid manual release of billing plan. |  | PRD | Signoff Doc Not Attached
199 | FICO | Accounts | Customer collection report - Accounts |  | UAT | Signoff Doc Not Attached |  | New Development | Yes |  | 2024-07-05 | To be considered after current development completion
200 | SD | Sales | A workflow needs to be define along with integration mapping between SAP &SFDC |  | NA | Signoff Doc Not Attached
201 | SD | Sales | Leverage the customization solution/cockpit which is currently being developed to ensure the Invoice generation as per specific user criteria |  | PRD | Signoff Doc Not Attached
202 | SD | Sales | Additional field required to tag the short codes for the customer (TIP etc) |  | PRD | Signoff Doc Not Attached
203 | SD | Sales | Interest letter format to be defined in the system and should be auto trigger to the customer |  | PRD | Signoff Doc Not Attached
204 | SD | Sales | Optimize the print format for Possession demand by configuring the appropriate title to differentiate final demand with other demands |  | PRD | Signoff Doc Not Attached
205 | SD | Sales | Unit readiness not visible while inviting customer for inspection |  | PRD | Signoff Doc Not Attached |  |  |  |  | 2024-05-31
206 | SD | Sales | Leverage the customization Solution/Cockpit for Credit note generation (being developed), Considering this calculation will be a complex logic to consider the net value and GST reversal applicable, the users must be trained appropriately for the same. |  | NA | NA
207 | SD | Sales | Approval matrix needs to be define along with the escalation matrix |  | NA | Signoff Doc Not Attached
208 | SD | Sales | Due as per Payment Plan Report |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT_Report-Due as per payment plan_Noida.msg
209 | FICO | Accounts | MIRO Dr/CR Print |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\198. MIRO Debit Credit Print Noida.pdf
210 | FICO | Accounts | Bank Reco. Statement Print |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\199. BRS PRINT & DEPRECIATION UAT NOIDA.pdf
211 | FICO | Accounts | Bank reconciliation Program- ZBRS |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\200. ZBRS Sign off.pdf
212 | DMS | Sales | Mass Upload of Images for BBA Form |  | PRD | Signoff Doc Attached
213 | SD | Sales | Cancellation Notice ( Noida ) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\NOIDA\LAVISH\Sign-off_Lavish_Dunning_Calcellation.pdf
214 | MM | Stores | Email Intimation to Estimation & Purchase Team when a PR/SR is raised |  | PRD | Signoff Doc Not Attached | 2.MM Module\3.UAT\Script Sign-offs\RE Confirmation for M3M_EN_MM_AD07Email Intimation to Estimation Team and Purchase Team when PR SR is raised. .msg
215 | MM | Billing | Service Entry sheet Print for Non-Ra Bill work orders |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RE M3M Service Entry Sheet Printout for Non-Projects.msg
216 | MM | Purchase | Validation in PO for Online approval text field mandatory |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf
217 | MM | Purchase | Additional tab in PO header for tagging WO no. (for contract material purchase) & BG/PBG,etc. applicability |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf
218 | MM | Billing | RA Bill Report |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_4-Devidayal.pdf
219 | MM | Purchase | Account Assignment validation for Purchase req & Purcahse orders |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_2.pdf
220 | MM | Purchase | Material type validation in PR & PO |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_3-Saugata.pdf
221 | MM | Purchase | Version Tick mandatory in case of version change |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf
222 | MM | Purchase | Change of PO not allowed in ME21N (PO Creation screen) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf
223 | MM | Purchase | Only contractor store applicable for Contract material purchase PO |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
224 | MM | Purchase | PR01 PR type authorization control |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation_3-Saugata.pdf
225 | MM | Stores | Storage loction Validation for movement type S11,S21,C21 |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
226 | MM | Stores | Work Order & Vendor selection validation in GRN for movement type S11,S21,C21 |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\RA bill scenario UAT_Noida.pdf
227 | MM | Billing | Material Reconcilation (FOC & Contractor material) Report |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Material Reconcillation report and print_Noida.pdf
228 | MM | Billing | Material Reconcilation (FOC & Contractor material) Print |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Material Reconcillation report and print_Noida.pdf
229 | MM | Billing | Cordination Charges (CFI) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Cordinated charges and Nominated Subcontractor_Noida.pdf
230 | MM | Billing | Nominated Subcontractor (NSC) |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Cordinated charges and Nominated Subcontractor_Noida.pdf
231 | SD | Sales | Finance Periodic Due Report (NR- 03.11.2023 ) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\PDR Report Sign off_Noida.msg
232 | SD | Sales | Credit Note Smartform (NR- 03.11.2023 ) ( Noida) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Noida & Panipat\NOIDA\LAVISH\Sign-off_Lavish_Credit note Smartform.pdf
233 | SD | Sales | Permission to Mortage Smartform ( Noida/ panipat) |  | PRD | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-off - PTM Noida.msg
234 | SD | Sales | Brokrage Invoice Print (NR-03-11-2023) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\UAT Sign-Off Brokerage.msg
235 | SD | Sales | Broker Report (NR-03-11-2023) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Vendor Master Duplication Check 1.pdf
236 | FICO | Accounts | Cash flow Report- New |  | Canceled | Signoff Doc Not Attached |  | N/A | N/A | N/A | N/A
237 | FICO | Accounts | Work done Vs Invoice report(MIGO-MIRO) |  | PRD | Signoff Doc Attached | 1.FICO Module\3.UAT\228. Work Done vs Invoice report Singoff.pdf
238 | SD | Sales | vendor Customer master duplication check |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Vendor Master Duplication Check 1.pdf
239 | SD | Sales | WBS wise Brokerage report |  | Not Started | Signoff Doc Not Attached |  | Changes |  | Amarjeet
240 | MM | Purchase | Email intimation to approving authorities for PR / SR |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Email intimation to approving authorities for PR SR and PO SO.msg
241 | MM | Purchase | Email intimation to approving authorities for PO / WO |  | PRD | Signoff Doc Attached | 2.MM Module\3.UAT\Script Sign-offs\Email intimation to approving authorities for PR SR and PO SO.msg
242 | FICO | Accounts | Dunning Form (Last and Final Opportunity After OC) (Panipat) |  | PRD
243 | MM | Purchase | Masss Material Upload |  | PRD | Conversion | 2.MM Module\Conversion development\Abap Development _Conversion_Mass Material Upload.doc
244 | MM | Contracts | Mass PO Upload |  | PRD | Conversion | 2.MM Module\Conversion development\Abap Development _Conversion_Mass Purchase Order Upload .doc
245 | MM | Contracts | Mass Service Upload |  | PRD | Conversion | 2.MM Module\Conversion development\Abap Development _Conversion_Mass Service Upload - Copy.doc
246 | SFDC/SD | Sales | Sales order Approval API |  | PRD | Signoff Doc Not Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Sales order_API_Signoff.msg"
247 | SFDC/SD | Sales | Customer Master data Post API |  | PRD | Signoff Doc Not Attached | "\\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\6.Interface\UAT\SFDC_Finance_API_Signoff.pdf"
248 | FICO | Sales | Approval Workflow for Customer receipt |  | PRD | Signoff Doc Not Attached
249 | SD | Sales | New BBA format to be developed (Panipat Post Merger) |  | PRD | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\RE BBA Letter City of Dreams II..msg
250 | SD | Sales | Booking approval form |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Panipat Uat Sign off\Booking Apppoal Form Sign off Noida and Panipat.pdf | Changes |  | Amarjeet
251 | SD | Sales | Allotment letter for city of dreams -2 Panipat |  | PRD | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-Off_Allotment Letter City of Dreams II.msg
252 | SD | Sales | New BBA format to be developed (M3M Sky line avenue) |  | PRD | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-off_BBA_M3M_The_Line_Avenue.msg
253 | SD | Sales | New BBA format to be developed (M3M Sky line Pentsuites) |  | PRD | Signoff Doc Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Sign-off_BBA_M3M_The_Line_pentsuites.msg
254 | MM | Purchase | Cheque No on Advance payment COP screen |  | PRD | Signoff Doc Attached | RE New Object Testing1.pdf
255 | FICO | Accounts | Dunning Form (Last and Final Opportunity Before OC) (Panipat) |  | PRD
256 | MM | Purchase | Recovery Screen Button |  | PRD | Signoff Doc Attached | RE New Object Testing1.pdf | New Development | yes | Amarjeet Singh
257 | MM | Purchase | COP format finalization |  | Not Feasible |  |  | New Development | Yes
258 | MM | Purchase | WO Extract & uploader |  | PRD | Signoff Doc Not Attached |  | New Development | Yes | Amarjeet Singh
259 | MM | Purchase | PO Advance Approval hierarchy |  | PRD | signed |  | New Development | Yes | abhinandan
260 | FICO | Accounts | Dunning Form (Reminder 1 After OC) ( Panipat) |  | PRD
261 | FICO | Accounts | Dunning Form (Reminder 1 Before OC) ( Panipat) |  | UAT | Signoff Doc Not Attached | \\192.168.100.4\SAP-Doc\3. SAP Scope and BBP Documents\3.SD Module\3.UAT\UAT SIGN OFF\Tax Scrap_Sale_Invoice_Noida.pdf | Changes | No | Santosh Choudhry | 2024-07-01
262 | FICO | Accounts | Customer Invoice and Advance open item report |  | PRD | Signoff Doc Not Attached | #N/A | New Development | Yes | Amarjeet Singh
263 | FICO | Accounts | Advance receipt output before clearing |  | PRD | Signoff Doc Not Attached | #N/A | New Development | Yes | Santosh Choudhry | 24/05/2024
264 | SD | Sales | Agreement Register of Agreement Register Details |  | WIP | Signoff Doc Not Attached |  | New Development | Yes |  | 28/05/2024
265 | SFDC/SD | Accounts | Channel Partner Master Creation API |  | WIP |  |  | New Development | No | Niraj Chavan | 2024-06-29
266 | SFDC/SD | Accounts | Channel Partner Master Change API |  | WIP |  |  | New Development | No | Niraj Chavan | 2024-06-29
267 | SD | Sales | Area Change | Enhancement | WIP |  |  | New Development | Yes |  | 2024-06-29
268 | FICO | Accounts | GST Report |  | PRD |  | #N/A | Changes | No | Amarjeet Singh | 2024-07-02
269 | FICO | Accounts | JV Print, Voucher print and Payment advice, Payment voucher |  | PRD | Signoff Doc Not Attached | #N/A | New Development | Yes | Sanjaya Kunar | 2024-03-06
270 | MM | Billing | Purchase Order COP Print |  | PRD | Signoff Doc Not Attached | 2.MM Module\3.UAT\Script Sign-offs\UAT_Signoff_Validation _1.pdf |  |  |  | 2024-06-28 | UAT sign off required.
271 | MM | Purchase | Residential PO/WO tax code validation. |  | PRD
272 | SD-14 Critical | CRM | Stamp Duty Calculation |  | WIP
273 | SFDC/SD | Accounts | Channel Partner Master Creation API - Inward |  | UAT
274 | SFDC/SD | Accounts | Channel Partner Master Change API-Outward |  | UAT
275 | FICO | Accounts | TDS Report |  | PRD
276 | FICO | Accounts | ledger enchancement of FBL3N for customer code |  | PRD
277 | FICO | Accounts | TDS report TMG creation for JV entries |  | PRD
278 | FICO | Accounts | Transfer of Ownsership concerns |  | PRD
279 | FICO | Accounts | Issue in Fund Transfer ( refer transfer of ownership) |  | PRD
280 | FICO | Accounts | Fund Transfer in case of Transfer of Ownership (interest due transfer in case of ownership transfer) |  | PRD
281 | FICO | Accounts | Z-Approve (SAP id and date of entry and) |  | PRD
282 | MM | Purchase | Non -project document type and Input GST |  | PRD
283 | FICO | Accounts | Collection Report |  | PRD
284 | MM | Purchase | Requirement of amount change feasibility in COP- |  | PRD
285 | FICO | Accounts | Creditors Bill wise Due Report |  | PRD
286 | FICO | Accounts | Validation on GST no & GST Type in Non PO posting (FB60) |  | PRD
287 | FICO | Accounts | Clearing Document Issue (DZ Entry Zapprove T code) Old invoice should be set of first. |  | PRD
288 | FICO | Accounts | Advance adjustment Validation |  | PRD
289 | FICO | Accounts | Editing option on Advance screen |  | PRD
290 | FICO | Accounts | Credit note is more than the demand |  | PRD
291 | FICO | Accounts | Bounced entry in SAP change |  | PRD
292 | SD | Accounts | Credit Note Output |  | WIP
293 | FICO | Accounts | * Vendor Ledger custom report to be corrected _Narration - TEXT filed in ledger column Vendor Ledger - TDS + Advance total showing . Separate column need to show |  | PRD
294 | FICO | Accounts | 2. Payment advise - Payment Voucher (Zfi_Print) * Cheque no not appearing in the print option + bank Name & Number |  | PRD
295 | FICO | Accounts | * Cheque number entered in the WO COP , not appearing in the bank COP posting option .During Bank assignment this information of cheque number should auto move to assignment field + narration as well. |  | PRD
296 | MM | Purchase | Material PO COP - Bill processing |  | PRD
297 | FICO | Accounts | GSTR1/GSTR2 |  | PRD
298 | SD | Accounts | Name Addition/Deletion/Substitution/Transfer of ownership |  | UAT
299 | SD | Accounts | Booking Category |  | UAT
300 | FICO | Accounts | Dunning Forms to be developed |  | WIP
301 | FICO | Accounts | Interest Calculation Changes |  | PRD
302 | MM | Purchase | Advance Payment -SMA Part Payment Functionality |  | Not Started
303 | FICO | Accounts | Secured / Unnsecured loan sub ledger is not allowed for creation and GL is not allowing the TDS dedcution |  | PRD
304 | MM | Purchase | MSME No in PO print |  | PRD
305 | FV-SD | CRM | Agreement Register of Agreement Register Details |  | PRD
306 | FV-SD | CRM | Amendment Register of Name Change |  | PRD
307 | FV-SD | CRM | Application Details Register of Application Details Register |  | PRD
308 | FV-SD | CRM | Booking Register Detail custom |  | PRD
309 | FV-SD | CRM | Booking Register FOC |  | PRD
310 | FV-SD | CRM | Brokerage Report of Brokerage Invoice Register (Details) |  | Not Started
311 | FV-SD | CRM | Brokerage Report of Brokerage Invoice(With BillingTerm) |  | Not Started
312 | FV-SD | CRM | Brokerage Report of Brokerage Report |  | Not Started
313 | FV-SD | CRM | Customer Outstanding of Combined Outstanding Report(Custom) |  | WIP
314 | FV-SD | CRM | Customer Outstanding of Periodic Due Report With Un Billed |  | UAT
315 | FV-SD | CRM | Invoice Register of Invoice Register Details |  | PRD
316 | FV-SD | CRM | M3M UNIT CANCELLATION CUSTOM |  | UAT
317 | FV-SD | CRM | Lien Report |  | PRD
318 | FV-SD | CRM | Rera Mis of Rera Report |  | UAT
319 | FV-SD | CRM | Sales Details(Custom) |  | WIP
320 | FV-SD | CRM | Sales Mis of Billed Vs Collection |  | WIP
321 | FV-SD | CRM | Sales Mis of Credit Rating Register |  | Not Started
322 | FV-SD | CRM | Credit Note Register of Credit Note Register |  | PRD
323 | FV-SD/FI | CRM | Late Payment Fee Ledger |  | Not Started
324 | FV-SD/FI | CRM | Late Payment Fee of Late Payment Fee Register Details |  | Not Started
325 | FV-SD/FI | CRM | Payment To Customer Register of Payment To Customer Register |  | UAT
326 | FV-SD/FI | CRM | Receipt Reversal Register of Receipt Reversal Register Details |  | UAT
327 | FV-FI | Accounts | Account confirmation Output |  | UAT
328 | FV-FI | Accounts | Bill wise payment detail register |  | UAT
329 | FV-FI | Accounts | banking of day book |  | UAT
330 | FV-FI | Accounts | contra voucher |  | UAT
331 | FV-FI | Accounts | finance ledger |  | UAT
332 | FV-FI | Accounts | Ledger of general ledger |  | UAT
333 | FV-FI | Accounts | Journal Register |  | UAT
334 | SD-14 Critical | CRM | 3 Area Change Database Creation |  | UAT
335 | SD-14 Critical | CRM | Area Main Screen To Access |  | UAT
336 | SD-14 Critical | CRM | Report to Capture New Area Change Detail |  | UAT
337 | SD-14 Critical | CRM | Report to Approve New Area Change Detail |  | UAT
338 | SD-14 Critical | CRM | Enhancement to Change Unit Master Area |  | UAT
339 | SD-14 Critical | CRM | Report to Capture New Booking Amendment Detail |  | UAT
340 | SD-14 Critical | CRM | Report to Approve New Booking Amendment Detail |  | UAT
341 | SD-14 Critical | CRM | Enhancement to Change Booking Payment Plan |  | UAT
342 | SD-14 Critical | CRM | Enhancement to Change Booking and Component Pricing |  | UAT
343 | SD-14 Critical | CRM | Enhancement to Create Credit Note Request Number |  | UAT
344 | SD-14 Critical | CRM | Enhancement for Finance to approve credit note request |  | UAT
345 | SD-14 Critical | CRM | Report for History for Area Change |  | UAT
346 | SD-14 Critical | CRM | Credit Note Posting Screen |  | Not Started
347 | SD-14 Critical | CRM | Possession Form |  | Not Started
348 | SD | Sales | Workflow for Pre-cancellation intimation and interest charges reminder /notification to the customer needs to be defined |  | Canceled | Signoff Doc Not Attached
349 | SD-14 Critical | CRM | Auto GST Reversal UAT |  | WIP
350 | SD-14 Critical | CRM | 4 Booking Category Database Creation |  | Not Started
351 | SD-14 Critical | CRM | Screen Creation to Capture tags |  | Not Started
352 | SD-14 Critical | CRM | Approval Process on each category |  | Not Started
353 | SD-14 Critical | CRM | Enhacements for each category |  | Not Started
354 | SD-14 Critical | CRM | Report for Booking Category |  | Not Started
355 | SD-14 Critical | CRM | Pre Handover |  | Not Started
356 | SD-14 Critical | CRM | 5 Post Handover Database Creation |  | Not Started
357 | SD-14 Critical | CRM | Rule Set Creation Screen |  | Not Started
358 | SD-14 Critical | CRM | Approval Screen on Tenant Data |  | Not Started
359 | SD-14 Critical | CRM | Payout Report |  | Not Started
360 | SD-14 Critical | CRM | FI Payout Post Report |  | Not Started
361 | SD-14 Critical | CRM | Document API |  | Not Started
362 | SD-14 Critical | CRM | Antaliya Hills Format |  | Not Started
363 | SD-14 Critical | CRM | Antaliya Hills Phase 1 &2 Pre Emi Subvention Letter |  | Not Started
364 | SD-14 Critical | CRM | Antalya 26 White Goods Letter |  | Not Started
365 | SD-14 Critical | CRM | BBA Discount Antalya Hills |  | Not Started
366 | SD-14 Critical | CRM | BBA Discount Golf Hills |  | Not Started
367 | SD-14 Critical | CRM | Capital 26 White Goods Letter |  | Not Started
368 | SD-14 Critical | CRM | Car Parking Letter For All Projects |  | Not Started
369 | SD-14 Critical | CRM | Commercial Accumaltion Format |  | Not Started
370 | SD-14 Critical | CRM | Commercial Format |  | Not Started
371 | SD-14 Critical | CRM | Crown 26 White Goods Letter |  | Not Started
372 | SD-14 Critical | CRM | Crown Pre Emi Subvention Letter |  | Not Started
373 | SD-14 Critical | CRM | First Transfer Free Letter for All Projects |  | Not Started
374 | SD-14 Critical | CRM | Golf Hills Format |  | Not Started
375 | SD-14 Critical | CRM | Golf Hills Lawn Letter Only for Ground Floor |  | Not Started
376 | SD-14 Critical | CRM | Golf Hills Phase 1 & 2 Pre Emi Subvention Letter |  | Not Started
377 | SD-14 Critical | CRM | Golf Hills Phase 1 Tpr Non-Subvention Letter |  | Not Started
378 | SD-14 Critical | CRM | Golf Hills Phase 1Tpr Subvention Letter |  | Not Started
379 | SD-14 Critical | CRM | Golf Hills Phase 2 Tpr Non-Subvention Format |  | Not Started
380 | SD-14 Critical | CRM | Maintainance Letter for All Projects |  | Not Started
381 | SD-14 Critical | CRM | One Time Discount All Commercial Projects Letter |  | Not Started
382 | SD-14 Critical | CRM | One Time Discount All Residential Preojects Letter |  | Not Started
383 | SD-14 Critical | CRM | One Time Rebate All Commercial Projects Letter |  | Not Started
384 | SD-14 Critical | CRM | One Time Rebate All Residential Project Letter |  | Not Started
385 | SD-14 Critical | CRM | Pre Payment Letter For All Projects |  | Not Started
386 | SD-14 Critical | CRM | Recovery Clause For Residential Format |  | Not Started
387 | SD-14 Critical | CRM | Recovery Clause Format |  | Not Started
388 | SD-14 Critical | CRM | Residential Accumation Format |  | Not Started
389 | SD-14 Critical | CRM | Residential Format |  | Not Started
390 | SD-14 Critical | CRM | Soulitude Format |  | Not Started
391 | SD-14 Critical | CRM | Timely Payment Discount Residential Project |  | Not Started
392 | SD-14 Critical | CRM | Timely Payment Discount Commercial Project |  | Not Started
393 | SD-14 Critical | CRM | Timely Payment Rebate Commercial Project |  | Not Started
394 | SD-14 Critical | CRM | Timely Payment Rebate Resdential Project |  | Not Started
395 | SD-14 Critical | CRM | Tpd Antaliya Hills |  | Not Started
396 | SD-14 Critical | CRM | Tpr 400 |  | Not Started
397 | SD-14 Critical | CRM | Double Rebate Benefit Letter |  | Not Started
398 | SD-14 Critical | CRM | BBA Rebate letter Mansion |  | Not Started
399 | SD-14 Critical | CRM | Dunning Cockpit |  | Not Started
400 | SD-14 Critical | CRM | Reminder 1 |  | Not Started
401 | SD-14 Critical | CRM | Pre Cancellation Letter |  | Not Started
402 | SD-14 Critical | CRM | Last and Final Opportunity |  | Not Started
403 | SD-14 Critical | CRM | Cancellation Sent |  | Not Started
404 | SD-14 Critical | CRM | TPR TPD |  | Not Started
405 | SD-14 Critical | CRM | BBA Printing |  | Not Started
406 | SD-14 Critical | CRM | CD Printing |  | Not Started
407 | SD-14 Critical | CRM | Brokerage Module |  | Not Started
408 | PS | Projects | Require validation in BOQ in ZPS_BOQ Tcode |  | PRD
409 | FICO | Accounts | DAPP |  | WIP
410 | FICO | Accounts | COP Multiple cheque |  | PRD
411 | FICO | Accounts | Material PO adavance program with approval matrix |  | PRD
412 | FICO | Accounts | Lower TDS in cop screen |  | PRD
413 | SD | CRM | Credit note output- scrap |  | WIP
414 | MM | Purchase | Legacy report - farvision mapping to sap |  | PRD
415 | SD | CRM | Comfort letter -The Cullinan Avenue |  | PRD
416 | SD | CRM | Comfort letter -The Emporium |  | PRD
417 | SD | CRM | Comfort letter - The Line Pen suite Preops adjustment with AR |  | PRD
418 | SD | CRM | Comfort letter - The Line Pen suite Preops only AR |  | PRD
419 | SD | CRM | Comfort letter - The Line Pen suite retail Preops adjustment with AR |  | PRD
420 | SD | CRM | Comfort letter - The Line Pen suite retail Preops Payout with AR |  | PRD
421 | MM | Contracts | Price Variance - Tagging removal from Wo |  | Not Started
422 | MM | Contracts | Price Variance - Mapping in transfer posting |  | Not Started
423 | MM | Contracts | Price Variance maintenanace - Screen changes line item addition |  | Not Started
424 | MM | Contracts | Price Variance calcualtion -Screen changes |  | Not Started
425 | SD | CRM | Interest charges - ZINT condition type |  | PRD
426 | MM | Contracts | advance screen billing period additon |  | Not Started
427 | MM | Contracts | advance COP billing period additon in COP screen & print |  | Not Started
428 | MM | Contracts | HTC (TDS) validatoin in COP screen |  | UAT
429 | MM | Contracts | HSN code mandate in MIRO from WO |  | UAT
430 | MM | Contracts | Abstract print rate subtotal |  | UAT