## Project Plan
Project : | CONVERSION/ IMPLEMENTATION/UPGRADE OF SAP ERP FROM SAP ECC 6.O EHP 8.0 SUITE ON HANA (PERPETUAL LICENSE MODEL) HOSTED AT SAP HANA ENTERPRISE CLOUD TO RISE WITH SAP S/4HANA PRIVATE CLOUD VERSION 2023 (SUBSCRIPTION MODEL) HOSTED AT SAP HANA ENTERPRISE CLOUD
Client : | MORMUGAO PORT AUTHORITY
SI : | Highbar Technocrat Limited
Subject : | Status of the Activities that are under the Project Plan | [9 empty] | Not Started
Sr# | Activity Description | Duration | Down Time Required | Plan |  | Actual |  | Status | Responsibilities | Remarks | WIP
|  |  |  | Start Date | End Date | Start Date | End Date |  |  |  | Completed
Phase 1 - Part 1 - Project Inititation | [7 empty] | Completed
1 | Project-Kickoff | 1 |  | 2024-10-21 | 2024-10-21 | 2024-10-21 | 2024-10-21 | 100% | Joint
2 | Project Plan Submission | 1 |  | 2024-10-22 | 2024-10-22 | 2024-10-29 | 2024-10-29 | 100% | HBT PM
3 | Team Mobilization | 1 |  | 2024-10-21 | 2024-10-21 | 2024-10-21 | 2024-10-21 | 100% | HBT PM
4 | RISE & Existing Landscape Understaning to Project Team | 1 |  | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 100% | Joint
5 | Project Plan Review and Sign off | 2 |  | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-10-24 | 100% | MPA PM
Phase 1 - Part 2 - POC (Production data migration & Simulation) | [7 empty] | In Progress
6 | Source : SAP ECC EHPx Sandbox Server setup |  |  |  |  | 2024-11-06 | 2024-11-06 | 100%
7 | Validate the refreshed PRD data (ECC6 data) | 0.5 |  | 2024-10-28 | 2024-10-28 | 2024-11-06 | 2024-11-06 | 100% | HBT BASIS & HBT Functional
8 | Apply DB/SAP patches (if required as per PAM) | 0.5 |  | 2024-10-29 | 2024-10-29 | 2024-11-07 | 2024-11-07 | 100% | HBT BASIS
9 | Impliment Notes Realated to Simplification Check | 1 |  | 2024-10-30 | 2024-10-30 | 2024-11-08 | 2024-11-08 | 100% | HBT BASIS
10 | Existing Business Process Understanding and identification of FIORI lighthouse apps for each module | 5 |  | 2024-11-04 | 2024-11-08 | 2024-11-11 | 2024-11-13 | 100% | HBT Functional + MPA CTM / Process Owner
11 | Simplification Item-Check | 3 |  | 2024-11-06 | 2024-11-08 | 2024-11-11 | 2024-11-15 | 100% | HBT Functional
12 | Custom Code Analysis | 3 |  | 2024-11-05 | 2024-11-07 | 2024-12-05 | 2024-12-20 | 0% | HBT BASIS | This 'Custom Code Analysis' task can be effectively performed during the SPDD and SPAU phases.
13 | SUM DMO Conversion | 4 |  | 2024-11-11 | 2024-11-14 | 2024-11-25 | 2024-11-29 | 100% | HBT BASIS
14 | SPDD & Other program corrections ( If Any) | 1 |  | 2024-11-15 | 2024-11-15 | 2024-12-02 | 2024-12-02 | 100% | HBT ABAP
15 | Continue with SUM | 2 |  | 2024-11-18 | 2024-11-19 | 2024-12-03 | 2024-12-04 | 100% | HBT BASIS
16 | Cleaning Up Obsolete Data After the Conversion | 1 |  | 2024-11-20 | 2024-11-20 | 2024-12-05 | 2024-12-05 | 75% | HBT BASIS
17 | SAPU Custom Code Adaptation / Check all Z t-codes | 3 |  | 2024-11-20 | 2024-11-22 | 2024-12-05 | 2024-12-26 | 0% | HBT ABAP
18 | Follow-On Activities for the Conversion of Authorizations - SU25 | 1 |  | 2024-11-25 | 2024-11-25 | 2024-12-05 | 2024-12-05 | 100% | HBT BASIS
19 | Conversion / Migration of POS ( Port Operating System ) T-Codes to New FIORI URL | 5 |  | 2024-11-26 | 2024-12-02 |  |  |  | HBT ABAP/FIORI
20 | Activation of FIORI Lighthouse APPS | 5 |  | 2024-11-26 | 2024-12-02 | 2024-12-20 | 2024-12-31 | 100% | HBT FIORI
21 | EP System Upgrade/Conversion / Migration to RISE EP system and Split App & DB | 5 |  | 2024-11-26 | 2024-12-02 |  |  |  | HBT BASIS/EP Consultant
22 | PI System upgrade from Dual stack to Single stack and Split App & DB | 5 |  | 2024-11-26 | 2024-12-02 |  |  |  | HBT Basis/PO Consultant
23 | Testing - HBT - Functional Business Processes and Interfaces | 6 |  | 2024-12-03 | 2024-12-09 | 2024-12-05 | 2024-12-26 |  | HBT Functional
24 | Client Testing & Acceptance | 8 |  | 2024-12-10 | 2024-12-19 |  |  |  | MPA
25 | Phase Sign-off | 1 |  | 2024-12-20 | 2024-12-20 |  |  |  | MPA PM
Phase 1 - Part 3 - Development System Migration to RISE with SAP cloud Dev. Server
26 | Source : SAP ECC EHPx Development Server setup
27 | Apply DB/SAP patches (if required as per PAM) | 0.5 |  | 2024-12-23 | 2024-12-23 |  |  |  | HBT BASIS
28 | Impliment Notes Realated to Simplification Check | 0.5 |  | 2024-12-23 | 2024-12-23 |  |  |  | HBT BASIS
29 | Simplification Item-Check | 2 |  | 2024-12-24 | 2024-12-26 |  |  |  | HBT Functional
30 | Custom Code Analysis | 1 |  | 2024-12-26 | 2024-12-26 |  |  |  | HBT BASIS
31 | SUM DMO Conversion | 4 |  | 2024-12-27 | 2025-01-02 |  |  |  | HBT BASIS
32 | SPDD & Other program corrections ( If Any) | 0.5 |  | 2025-01-03 | 2025-01-03 |  |  |  | HBT ABAP
33 | Continue with SUM | 2 |  | 2025-01-06 | 2025-01-07 |  |  |  | HBT BASIS
34 | Cleaning Up Obsolete Data After the Conversion | 0.5 |  | 2025-01-08 | 2025-01-08 |  |  |  | HBT BASIS
35 | SAPU Custom Code Adaptation / Check all Z t-codes | 2 |  | 2025-01-09 | 2025-01-10 |  |  |  | HBT ABAP
36 | Follow-On Activities for the Conversion of Authorizations - SU25 | 0.5 |  | 2025-01-13 | 2025-01-13 |  |  |  | HBT BASIS
37 | Conversion / Migration of POS ( Port Operating System ) T-Codes to New FIORI URL | 0.5 |  | 2025-01-10 | 2025-01-10 |  |  |  | HBT ABAP/FIORI
38 | Activation of FIORI Lighthouse APPS | 0.5 |  | 2025-01-10 | 2025-01-10 |  |  |  | HBT FIORI
39 | EP System Upgrade/Conversion / Migration to RISE EP system | 3 |  | 2025-01-10 | 2025-01-14 |  |  |  | HBT BASIS/EP Consultant
40 | PI System upgrade from Dual stack to Single stack | 3 |  | 2025-01-10 | 2025-01-14 |  |  |  | HBT Basis/PO Consultant
41 | Testing - HBT - Functional Business Processes and Interfaces | 3 |  | 2025-01-15 | 2025-01-17 |  |  |  | HBT Functional
42 | Client Testing & Acceptance | 5 |  | 2025-01-20 | 2025-01-24 |  |  |  | MPA
43 | Phase Sign-off | 1 |  | 2025-01-25 | 2025-01-25 |  |  |  | MPA PM
Phase 1 - Part 4- - Quality System Migration to RISE with SAP cloud QAS Server
44 | Source : SAP ECC EHPx Quality Server setup
45 | Apply DB/SAP patches (if required as per PAM) | 0.5 |  | 2025-01-27 | 2025-01-27 |  |  |  | HBT BASIS
46 | Impliment Notes Realated to Simplification Check | 0.5 |  | 2025-01-27 | 2025-01-27 |  |  |  | HBT BASIS
47 | Simplification Item-Check | 2 |  | 2025-01-28 | 2025-01-29 |  |  |  | HBT Functional
48 | SUM DMO Conversion | 4 |  | 2025-01-30 | 2025-02-04 |  |  |  | HBT BASIS
49 | SPDD & Other program corrections ( If Any) | 0.5 |  | 2025-02-05 | 2024-02-05 |  |  |  | HBT ABAP
50 | Continue with SUM | 2 |  | 2026-02-06 | 2025-02-07 |  |  |  | HBT BASIS
51 | Cleaning Up Obsolete Data After the Conversion | 0.5 |  | 2025-02-10 | 2025-02-10 |  |  |  | HBT BASIS
52 | SAPU Custom Code Adaptation / Check all Z t-codes | 2 |  | 2025-02-11 | 2025-02-12 |  |  |  | HBT ABAP
53 | Follow-On Activities for the Conversion of Authorizations - SU25 | 1 |  | 2025-02-13 | 2025-02-13 |  |  |  | HBT BASIS
54 | Conversion / Migration of POS ( Port Operating System ) T-Codes to New FIORI URL | 1 |  | 2025-02-14 | 2025-02-14 |  |  |  | HBT ABAP/FIORI
55 | Activation of FIORI Lighthouse APPS | 1 |  | 2025-02-14 | 2025-02-14 |  |  |  | HBT FIORI
56 | EP System Upgrade/Conversion / Migration to RISE EP system | 3 |  | 2025-02-14 | 2025-02-18 |  |  |  | HBT BASIS/EP Consultant
57 | PI System upgrade from Dual stack to Single stack | 3 |  | 2025-02-14 | 2025-02-18 |  |  |  | HBT Basis/PO Consultant
58 | Testing - HBT - Functional Business Processes and Interfaces | 2 |  | 2025-02-20 | 2025-02-21 |  |  |  | HBT Functional
59 | Client Testing & Acceptance | 5 |  | 2025-02-24 | 2025-02-28 |  |  |  | MPA
60 | Phase Sign-off | 1 |  | 2025-02-28 | 2025-02-28 |  |  |  | MPA PM
Phase 1 - Part 5 - Production System Migration to RISE with SAP cloud PRD Server
61 | Source : SAP ECC EHPx Production Server setup
62 | Apply DB/SAP patches (if required as per PAM) | 0.5 | Y | 2025-03-01 | 2025-03-01 |  |  |  | HBT BASIS
63 | Impliment Notes Realated to Simplification Check | 0.5 | N | 2025-03-01 | 2025-03-01 |  |  |  | HBT BASIS
64 | Simplification Item-Check | 2 | N | 2025-03-03 | 2025-03-04 |  |  |  | HBT Functional
65 | SUM DMO Conversion | 3 | Y | 2025-03-07 | 2025-03-09 |  |  |  | HBT BASIS
66 | SPDD & Other program corrections ( If Any) |  | Y | 2025-03-07 | 2025-03-09 |  |  |  | HBT ABAP
67 | Continue with SUM |  | Y | 2025-03-07 | 2025-03-09 |  |  |  | HBT BASIS
68 | Cleaning Up Obsolete Data After the Conversion |  | Y | 2025-03-07 | 2025-03-09 |  |  |  | HBT BASIS
69 | SAPU Custom Code Adaptation / Check all Z t-codes | 1 | N | 2025-03-10 | 2025-03-10 |  |  |  | HBT ABAP
70 | Follow-On Activities for the Conversion of Authorizations - SU25 |  | N | 2025-03-10 | 2025-03-10 |  |  |  | HBT BASIS
71 | Conversion / Migration of POS ( Port Operating System ) T-Codes to New FIORI URL |  | N | 2025-03-10 | 2025-03-10 |  |  |  | HBT ABAP/FIORI
72 | Activation of FIORI Lighthouse APPS |  | N | 2025-03-10 | 2025-03-10 |  |  |  | HBT FIORI
73 | EP System Upgrade/Conversion / Migration to RISE EP system and Split App & DB | 3 | Y | 2025-03-14 | 2025-03-16 |  |  |  | HBT BASIS/EP Consultant
74 | PI System upgrade from Dual stack to Single stack and Split App & DB | 3 | Y | 2025-03-14 | 2025-03-16 |  |  |  | HBT Basis/PO Consultant
75 | Checking & Go-Live | 1 |  | 2025-03-18 | 2025-03-18 |  |  |  | MPA PM
Phase 2 - Run - PGLS
76 | Post Go Live Support & Implementation of ESS/MSS, India localisation reports & Bank Reconciliation. | 26 weeks |  | 2025-03-19 | 2025-09-18 |  |  |  | HBT