## Renaatus Consolidate Gap List
Objects | [9 empty] | RGS | [9 empty] | FS |  |  |  | ABAP Development | [7 empty] | HBT Testing | [7 empty] | CTM Testing | [8 empty] | UAT Sign Off |  |  |  | Go-Live |  |  |  | Reusability
Sr No | Module | Development Description | Total Objects | Scope | FRICEW Category | Priority Catagory | Priority | Complexity | Functional Consultant | Planned discussion with BPO | Actual discussion with BPO | Planned Submission | Actual Submission | Suggested Changes in-corporated | Planned Re-Submission | Actual Re-Submission | Planned Approval | Actual Approval | RGS Status | Planned Submission Date | Revised Date | Actual Date | FS Status | Plan ABAP Consultant | Actual ABAP Consultant | Duration | Planned Start | Planned Finish | Actual Start | Actual Finish | Development Status | UT-SIT Test Scripts Planned Finish | UT-SIT Test Scripts Actual Finish | Testing Planned Start | Testing Planned Finish | Testing Planned Duration | Testing Actual Start | Testing Actual Finish | HBT Testing Status | CTM Name | Training Start | Training Finish | Duration | Planned Start | Planned Finish | Actual Start | Actual Finish | CTM Testing Status | Final Test Script Submission Date | UAT Planned Date | UAT Actual Date | UAT Status | PRD Status | Duration | Go-Live Planned Date | Go-Live Actual Date | Reusable Object | Reusable Client Name |  | Remarks
1 | FI | Validation for Business Place & Section Code Fields in MIR7/MIRO | 1 | SOW | Enhancement | 1 | SIT | Simple | Venkata | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP1 |  |  | 2024-09-28 | 2024-10-01
2 | FI | Validation for Business Place & Section Code Fields in FB60 & FB65 | 1 | SOW | Enhancement | 1 | SIT | Simple | Venkata | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP1 |  |  | 2024-10-03 | 2024-10-05
3 | FI | Required new Tab in Asset Master | 1 | SOW | Enhancement | 1 | SIT | Simple | Venkata | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP1 |  |  | 2024-10-07 | 2024-10-10
4 | FI | Required Check Box for MSME | 1 | SOW | Enhancement | 1 | SIT | Simple | Venkata | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP1 |  |  | 2024-10-11 | 2024-10-14
5 | FI | GL/Supplier/Customer Legcay Balance upload | 1 | SOW | Conversion | 1 | SIT | Medium | Venkata | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP1 |  |  | 2024-10-15 | 2024-10-17 | [28 empty] | Yes | Kinjal | ZFI_FB01
6 | FI | Vendor/Customer Master Upload Template | 1 | SOW | Conversion | 1 | SIT | Medium | Venkata | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP1 |  |  | 2024-10-18 | 2024-10-21 | [28 empty] | Yes | Kinjal | ZMM_VEN_UPD
7 | SD | Contract & RA Billing Approval | 1 | SOW | Enhancement | 1 | SIT | Complex |  | 2024-09-21 |  | 2024-09-23 |  |  |  |  | 2024-09-25 |  |  | 2024-09-27 |  |  |  | ABAP2 |  |  | 2024-09-27 | 2024-10-01
8 | FI | Bank Reconciliation Statement | 1 | SOW | Enhancement | 1 | SIT | Complex | Venkata | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP1 |  |  | 2024-10-22 | 2024-10-26
9 | FI | Asset Master Report with enhancement fields. | 1 | SOW | Report | 2 | GO LIVE | Medium | Venkata | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03
10 | FI | Balance Sheet | 1 | SOW | Report | 2 | GO LIVE | Medium | Venkata | 2024-09-27 |  | 2024-09-28 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03
11 | FI | BG / LC Tracker | 1 | SOW | Report | 2 | GO LIVE | Complex | Venkata | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 | [36 empty] | Yes | kinjal | ZFI_BG
12 | FI | Bank Host to Host Integration - 3 Banks in India 1. banks interface will be in scope for account payable only. Receivable interface is Notrequired. 2. For Maldives, Mauritius, KSA 01 bank each interface objects will be part of proposed objects under e | 4 | SOW | Interface | 2 | GO LIVE | Complex | Venkata | 2024-09-30 |  | 2024-10-01 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
13 | FI | HR One - Payroll Accounting | 2 | SOW | Interface | 2 | GO LIVE | Complex | Venkata | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
14 | FI | E Invoicing, e way billing & GSTR2 interface required using APIs | 6 | SOW | Interface | 2 | GO LIVE | Complex | Venkata | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
15 | FI | E Invoicing, e way billing & GSTR2 interface required using APIs | 1 | SOW | Report | 2 | GO LIVE | Complex | Venkata | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
16 | FI | E Invoicing, e way billing & GSTR2 interface required using APIs | 3 | SOW | Enhancement | 2 | GO LIVE | Complex | Venkata | 2024-10-03 |  | 2024-10-05 |  |  |  |  | 2024-10-07 |  |  | 2024-10-09
17 | FI | Cash Flow Report | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Venkata | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
18 | FI | P&L | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Venkata | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
19 | FI | Loan & Loan Outstanding Report | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Venkata | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
20 | FI | Insurance & Interest entry (Auto interest calculator) | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Venkata | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
21 | MM | Validation of Profit Centre - Plant in Material Master | 1 | SOW | Enhancement | 1 | SIT | Simple | Manikandan | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP6 |  |  | 2024-09-30 | 2024-10-03
22 | MM | WO terms & condition - Header level | 1 | SOW | Enhancement | 1 | SIT | Simple | Manikandan | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP6 |  |  | 2024-10-04 | 2024-10-07
23 | MM | Material Master Upload | 1 | SOW | Conversion | 1 | SIT | Simple | Manikandan | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP6 |  |  | 2024-10-08 | 2024-10-09 | [29 empty] | SRC
24 | MM | Material request(Field Request Slip) - Reservation | 1 | SOW | Enhancement | 1 | SIT | Simple | Manikandan | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP6 |  |  | 2024-10-10 | 2024-10-12
25 | MM | Material shelf life expiration date Report after GRN | 1 | SOW | Report | 1 | SIT | Medium | Manikandan | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP6 |  |  | 2024-10-14 | 2024-10-16
26 | MM | Transfer Form - OBD print | 1 | SOW | Form | 1 | SIT | Medium | Manikandan | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP6 |  |  | 2024-10-17 | 2024-10-19
27 | MM | PO Print - Domestic PO | 1 | SOW | Form | 1 | SIT | Medium | Manikandan | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP6 |  |  | 2024-10-21 | 2024-10-23
28 | MM | WO terms & condition- SC Advance | 1 | SOW | Enhancement | 1 | SIT | Medium | Manikandan | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP6 |  |  | 2024-10-24 | 2024-10-26
29 | MM | PO Print - WO, Service PO | 1 | SOW | Form | 1 | SIT | Medium | Manikandan | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-09-30 | 2024-10-03
30 | MM | Service Master Upload | 1 | SOW | Conversion | 1 | SIT | Medium | Manikandan | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-10-04 | 2024-10-05 | [29 empty] | SRC
31 | MM | Open PO Upload/Open WO Upload | 1 | SOW | Conversion | 1 | SIT | Medium | Manikandan | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-10-07 | 2024-10-08 | [29 empty] | Tata Projects
32 | MM | Ra Bill, Labour Bill approver Maintanence Table | 1 | SOW | Enhancement | 1 | SIT | Medium | Manikandan | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-10-09 | 2024-10-12
33 | MM | Rent Tracking entry screen | 1 | SOW | Enhancement | 1 | SIT | Medium | Manikandan | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-10-14 | 2024-10-16
34 | MM | Reservation Report for equipment wise for consumption Report | 1 | SOW | Report | 1 | SIT | Medium | Manikandan | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-10-17 | 2024-10-19
35 | MM | Weighment Related fields | 1 | SOW | Enhancement | 1 | SIT | Medium | Manikandan | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP7 |  |  | 2024-10-21 | 2024-10-23
36 | MM | Service Category and Service Group Validation | 1 | SOW | Enhancement | 1 | SIT | Medium | Manikandan | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP7 |  |  | 2024-10-24 | 2024-10-26
37 | MM | Material Type and Material Group Validation | 1 | SOW | Enhancement | 1 | SIT | Medium | Manikandan | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-03 | 2024-10-05
38 | MM | PR Print | 1 | SOW | Form | 1 | SIT | Medium | Manikandan | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-07 | 2024-10-09
39 | MM | Advance entry based on the WO -2 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Manikandan | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-10 | 2024-10-12
40 | MM | Company Muster Bill -2 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Manikandan | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-14 | 2024-10-16
41 | MM | Material request(Field Request Slip) -1 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Manikandan | 2024-09-27 |  | 2024-09-28 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-17 | 2024-10-19
42 | MM | Rate Approval /Fixing-1 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Manikandan | 2024-09-27 |  | 2024-09-28 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-21 | 2024-10-23
43 | MM | Formwork/Equipment/Machineries stock Report site wise | 1 | SOW | Report | 1 | SIT | Complex | Manikandan | 2024-09-27 |  | 2024-09-28 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP8 |  |  | 2024-10-24 | 2024-10-28
44 | MM | Create RA Bill (Service Entry Sheet) from approved RFI | 1 | SOW | Enhancement | 1 | SIT | Complex | Manikandan | 2024-09-27 |  | 2024-09-28 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP5 |  |  | 2024-10-16 | 2024-10-17 | [29 empty] | M3M |  | RA Bill - Please check the Program in M3M's System
45 | MM | Recovery of Mobilisation Advance and Royalty | 1 | SOW | Enhancement | 1 | SIT | Complex | Manikandan | 2024-09-27 |  | 2024-09-28 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03 |  |  |  | ABAP5 |  |  | 2024-10-18 | 2024-10-22 | [31 empty] | RA Bill - Please check the Program in M3M's System
46 | MM | Reconciliation and recovery of materials | 1 | SOW | Enhancement | 1 | SIT | Complex | Manikandan | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 |  |  |  | ABAP5 |  |  | 2024-10-23 | 2024-10-28 | [31 empty] | RA Bill - Please check the Program in M3M's System
47 | MM | Process payment Abstract | 1 | SOW | Enhancement | 1 | SIT | Complex | Manikandan | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 |  |  |  | ABAP4 |  |  | 2024-10-25 | 2024-10-29 | [31 empty] | RA Bill - Please check the Program in M3M's System
48 | MM | Interface with Thumb Tag: Head count basis Advance recommendation/NMR Bill Processing | 3 | SOW | Interface | 1 | SIT | Complex | Manikandan | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
49 | MM | Interface with Weighbridge - 02 Make | 6 | SOW | Interface | 1 | SIT | Complex | Manikandan | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
50 | MM | Ra Bill Deletion | 1 | SOW | Enhancement | 1 | SIT | Complex | Manikandan | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
51 | MM | Module pool for Flexible Workflow for approver data Maintanence | 1 | SOW | Enhancement | 1 | SIT | Complex | Manikandan | 2024-09-30 |  | 2024-10-01 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
52 | MM | Rate Maintenance for Formwork | 1 | SOW | Enhancement | 2 | GO LIVE | Medium | Manikandan | 2024-09-30 |  | 2024-10-01 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
53 | MM | External hire materials Maintenance | 1 | SOW | Enhancement | 2 | GO LIVE | Medium | Manikandan | 2024-09-30 |  | 2024-10-01 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
54 | MM | Reservation subcon and WO number fields required | 1 | SOW | Enhancement | 2 | GO LIVE | Medium | Manikandan | 2024-09-30 |  | 2024-10-01 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
55 | MM | Rent Tracking Report | 1 | SOW | Report | 2 | GO LIVE | Medium | Manikandan | 2024-09-30 |  | 2024-10-01 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
56 | MM | Internal Hire bill for Formwork and Tracking | 1 | SOW | Report | 2 | GO LIVE | Medium | Manikandan | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
57 | MM | Internal Hire bill for equipment and Tracking | 1 | SOW | Report | 2 | GO LIVE | Medium | Manikandan | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
58 | MM | Material Transfer Voucher - Returnable Gate Pass / NOn-Returnable Gate Pass | 1 | SOW | Form | 2 | GO LIVE | Medium | Manikandan | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
59 | MM | Subcon Bill - Summary Report | 1 | SOW | Report | 2 | GO LIVE | Complex | Manikandan | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
60 | MM | Hire Formwork Material Tracking | 1 | SOW | Enhancement | 2 | GO LIVE | Complex | Manikandan | 2024-10-01 |  | 2024-10-03 |  |  |  |  | 2024-10-05 |  |  | 2024-10-07
61 | MM | Hire Equipment Tracking from external vendor | 1 | SOW | Report | 2 | GO LIVE | Complex | Manikandan | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
62 | MM | Material quantity validation with cost planning - PR & PO | 1 | SOW | Enhancement | 2 | GO LIVE | Complex | Manikandan | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
63 | MM | Project wise Hire Report | 1 | SOW | Report | 3 | POST GO LIVE | Medium | Manikandan | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
64 | MM | Material Reconciliation | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Manikandan | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
65 | MM | Age wise Stock Analyze Report | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Manikandan | 2024-10-03 |  | 2024-10-04 |  |  |  |  | 2024-10-06 |  |  | 2024-10-08
66 | PM | Additional Custom field enhancements in Equipment Master | 1 | SOW | Enhancement | 1 | SIT | Medium | Prathyush | 2024-09-18 |  | 2024-09-19 |  |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP5 |  |  | 2024-09-23 | 2024-09-25 | [28 empty] | Yes | SRC
67 | PM | BDC to Upload the Task List | 1 | SOW | Conversion | 1 | SIT | Medium | Prathyush | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP5 |  |  | 2024-09-26 | 2024-09-28 | [28 empty] | Yes | Patel
68 | PM | Additional fields in Display equipment list report | 1 | SOW | Enhancement | 1 | SIT | Medium | Prathyush | 2024-09-18 |  | 2024-09-19 |  |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP5 |  |  | 2024-09-30 | 2024-10-03
69 | PM | RTO, Car, Vehicle, Asset Insurance details Report | 1 | SOW | Report | 1 | SIT | Complex | Prathyush | 2024-09-18 |  | 2024-09-19 |  |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP5 |  |  | 2024-10-04 | 2024-10-09 | [28 empty] | Yes | Patel
70 | PM | RTO, Car, Vehicle, Asset Insurance details report | 2 | SOW | Enhancement | 1 | SIT | Complex | Prathyush | 2024-09-18 |  | 2024-09-19 |  |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP5 |  |  | 2024-10-10 | 2024-10-15 | [28 empty] | Yes | Patel
71 | PM | Equipment Utilization, Productivity Report | 1 | SOW | Report | 2 | GO LIVE | Medium | Prathyush | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 | [36 empty] | Yes | SRC
72 | PM | Own Hire Report (Machinery) | 1 | SOW | Report | 2 | GO LIVE | Medium | Prathyush | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
73 | PM | Equipment Log Entry Screen | 1 | SOW | Enhancement | 2 | GO LIVE | Complex | Prathyush | 2024-09-18 |  | 2024-09-19 |  |  |  |  | 2024-09-21 |  |  | 2024-09-23 | [36 empty] | Yes | SRC
74 | PM | Equipment Log Report | 1 | SOW | Report | 2 | GO LIVE | Complex | Prathyush | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 | [36 empty] | Yes | SRC
75 | PM | Equipment Division Assets P&L Report | 1 | SOW | Report | 3 | POST GO LIVE | Medium | Prathyush | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
76 | PM | P& M Mileage Report | 1 | SOW | Report | 3 | POST GO LIVE | Medium | Prathyush | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
77 | PM | Driver/Operator Cost & Performance Calculation | 1 | SOW | Report | 3 | POST GO LIVE | Medium | Prathyush | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
78 | PP | Interface with Batching Plant | 2 | SOW | Interface | 2 | GO LIVE | Complex | Shivraj | 2024-09-18 | 2024-09-19 | 2024-09-19 |  |  |  |  | 2024-09-21 |  |  | 2024-09-23
79 | PP | Upload, download programs for Asphalt, Hot Mix Plants | 2 | SOW | Interface | 2 | GO LIVE | Complex | Shivraj | 2024-09-19 | 2024-09-19 | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
80 | QM | Request for Inspection ( RFI) | 1 | SOW | Enhancement | 1 | SIT | Complex | Srinivas | 2024-09-18 | 19/09/2024 | 2024-09-19 | 19/09/2024 |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP2 |  |  | 2024-10-22 | 2024-10-24 | [28 empty] | Yes | Al-Ali | QM01
81 | PS | Each Project will have Customer Enhancement fields in order to capture all the information needed in reporting like BG Value, BG Start date, | 1 | SOW | Enhancement | 1 | SIT | Medium | Pooja | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP3 |  |  | 2024-09-23 | 2024-09-25 | [28 empty] | Yes | K-ride
82 | PS | Quantity based Budget control in PR / SR | 2 | SOW | Enhancement | 1 | SIT | Complex | Pooja | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP3 |  |  | 2024-09-26 | 2024-10-01
83 | PS | WBS Structure Upload | 1 | SOW | Conversion | 1 | SIT | Medium | Pooja | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP3 |  |  | 2024-10-03 | 2024-10-05 | [28 empty] | Yes | K-Ride
84 | PS | Activity Upload (incl.Time Schedule) | 1 | SOW | Conversion | 1 | SIT | Medium | Pooja | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP3 |  |  | 2024-10-07 | 2024-10-09 | [28 empty] | Yes | K-Ride
85 | PS | Cost Plan Upload | 1 | SOW | Conversion | 1 | SIT | Medium | Pooja | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP3 |  |  | 2024-10-10 | 2024-10-11 | [28 empty] | Yes | K-Ride
86 | PS | Budget amendment-3 Level | 3 | SOW | Workflow | 1 | SIT | Complex | Pooja | 2024-09-21 |  | 2024-09-23 |  |  |  |  | 2024-09-25 |  |  | 2024-09-27 |  |  |  | ABAP3 |  |  | 2024-10-12 | 2024-10-17
87 | PS | Budget Submission -3 Level | 1 | SOW | Workflow | 1 | SIT | Complex | Pooja | 2024-09-21 |  | 2024-09-23 |  |  |  |  | 2024-09-25 |  |  | 2024-09-27 |  |  |  | ABAP3 |  |  | 2024-10-18 | 2024-10-23
88 | PS | Base rate fixing(Basic rate -Project specific) | 2 | SOW | Enhancement | 1 | SIT | Complex | Pooja | 2024-09-23 | 2024-09-19 | 2024-09-24 | 2024-09-19 |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP3 |  |  | 2024-10-24 | 2024-10-28
89 | PS | BPO rate approval | 1 | SOW | Workflow | 1 | SIT | Medium | Pooja | 2024-09-23 | 2024-09-19 | 2024-09-24 | 2024-09-19 |  |  |  | 2024-09-26 |  |  | 2024-09-28 |  |  |  | ABAP4 |  |  | 2024-09-23 | 2024-09-25
90 | PS | DPR-Material | 1 | SOW | Enhancement | 1 | SIT | Medium | Pooja | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | 2024-09-21 |  |  | 2024-09-23 |  |  |  | ABAP4 |  |  | 2024-09-26 | 2024-09-28
91 | PS | Resource Schedule(M,M,M)(Monthly Projection with Amount) | 1 | SOW | Enhancement | 1 | SIT | Medium | Pooja | 2024-09-19 | 2024-09-19 | 2024-09-20 | 2024-09-19 |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-09-30 | 2024-10-03
92 | PS | Budget Revision(Suplimentry Budget Only)-including Version | 1 | SOW | Enhancement | 1 | SIT | Medium | Pooja | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-10-04 | 2024-10-07
93 | PS | Budget Submission | 1 | SOW | Enhancement | 1 | SIT | Medium | Pooja | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-10-08 | 2024-10-10
94 | PS | Daily Progress Entry (DPR) -1 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Pooja | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-10-11 | 2024-10-14
95 | PS | Project Closure(Technical & Financial)-3 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Pooja | 2024-09-19 |  | 2024-09-20 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-10-15 | 2024-10-17
96 | PS | Project Creation Amendment-1 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Pooja | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-10-18 | 2024-10-21
97 | PS | Project Creation (including WareHouse)-1 Level | 1 | SOW | Workflow | 1 | SIT | Medium | Pooja | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25 |  |  |  | ABAP4 |  |  | 2024-10-22 | 2024-10-24
98 | PS | DPR- Quantity(Activity Confirmation) | 1 | SOW | Enhancement | 2 | GO LIVE | Medium | Pooja | 2024-09-21 |  | 2024-09-23 |  |  |  |  | 2024-09-25 |  |  | 2024-09-27
99 | PS | DLR- Labour | 1 | SOW | Enhancement | 2 | GO LIVE | Medium | Pooja | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
100 | PS | Cash Inflow Report( incl.Monthly Projection) | 1 | SOW | Enhancement | 2 | GO LIVE | Complex | Pooja | 2024-09-20 |  | 2024-09-21 |  |  |  |  | 2024-09-23 |  |  | 2024-09-25
101 | PS | JCR Top Sheet | 2 | SOW | Enhancement | 2 | GO LIVE | Complex | Pooja | 2024-09-21 |  | 2024-09-23 |  |  |  |  | 2024-09-25 |  |  | 2024-09-27
102 | PS | DLR Report | 1 | SOW | Report | 3 | POST GO LIVE | Complex | Pooja | 2024-09-21 |  | 2024-09-23 |  |  |  |  | 2024-09-25 |  |  | 2024-09-27
103 | All (share point) | Interface with share point for Document Storage | 7 | SOW | Interface | 1 | SIT | Complex | Venkata/Mani/Arjeet/Prathyush/Srinu/Shiva/Pooja | 2024-09-28 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
104 | SD | BOQ Z Table billing long text | 1 | SOW | Enhancement | 1 | SIT | Simple | Arjeet | 2024-09-21 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 |  |  |  | ABAP2 |  |  | 2024-10-03 | 2024-10-04
105 | SD | BOQ upload | 1 | SOW | Conversion | 1 | SIT | Medium | Arjeet | 2024-09-21 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 |  |  |  | ABAP2 |  |  | 2024-10-05 | 2024-10-07 | [28 empty] | Yes | Patel | ZSD_BOQ
106 | SD | Client Billing - Certification-1 level | 1 | SOW | Workflow | 1 | SIT | Medium | Arjeet | 2024-09-21 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 |  |  |  | ABAP2 |  |  | 2024-10-08 | 2024-10-10
107 | SD | Packing list screen | 1 | SOW | Enhancement | 1 | SIT | Complex | Arjeet | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30 |  |  |  | ABAP2 |  |  | 2024-10-11 | 2024-10-15
108 | SD | Client Change Order- 1 Level | 1 | SOW | Workflow | 1 | SIT | Complex | Arjeet | 2024-09-21 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05 |  |  |  | ABAP2 |  |  | 2024-10-16 | 2024-10-21
109 | SD | Service Form | 1 | SOW | Form | 2 | GO LIVE | Simple | Arjeet | 2024-09-26 |  | 2024-09-27 |  |  |  |  | 2024-09-30 |  |  | 2024-10-03
110 | SD | Client bill abstract | 1 | SOW | Report | 2 | GO LIVE | Medium | Arjeet | 2024-09-21 |  | 2024-09-30 |  |  |  |  | 2024-10-03 |  |  | 2024-10-05
111 | SD | Work in Progress | 1 | SOW | Report | 2 | GO LIVE | Medium | Arjeet | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28
112 | SD | Invoice Out Put Sales Billing - Products, Service, Scrap, Asset | 1 | SOW | Form | 2 | GO LIVE | Medium | Arjeet | 2024-09-25 |  | 2024-09-26 |  |  |  |  | 2024-09-28 |  |  | 2024-09-30
113 | SD | Collection target Report | 1 | SOW | Report | 2 | GO LIVE | Medium | Arjeet | 2024-09-23 |  | 2024-09-24 |  |  |  |  | 2024-09-26 |  |  | 2024-09-28
114 | SD | Scrap Report | 1 | SOW | Report | 2 | GO LIVE | Complex | Arjeet | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30
115 | SD | Asset Sale Report Resale Report | 1 | SOW | Report | 2 | GO LIVE | Complex | Arjeet | 2024-09-24 |  | 2024-09-25 |  |  |  |  | 2024-09-27 |  |  | 2024-09-30
Formulas:
Planned Submission = [RGS]+1
Planned Approval = [Planned Submission]+2
FS = [Planned Approval]+2
RGS = [RGS, row above]+1