## Sheet1
HCC - SF Implementation - Plan
Task Name | Duration | Start | Finish | Predecessors | Text1 | % Completion | Remark
SF- HCC | 625 days | Mon 07-11-22 | Tue 08-04-25 |  |  | 100%
Prepare | 511 days | Mon 07-11-22 | Wed 23-10-24 |  |  | 100%
Kick off | 1 day | Mon 14-10-24 | Mon 14-10-24 |  |  | 100%
Project Plan | 6 days | Tue 15-10-24 | Tue 22-10-24 |  |  | 100%
Onboarding of Team | 1 day | Tue 22-10-24 | Tue 22-10-24 |  |  | 100%
Project preparation phase sign off by HCC | 1 day | Wed 23-10-24 | Wed 23-10-24 | 13 | HCC & HBT | 100%
Deliverables | 510 days | Mon 07-11-22 | Tue 22-10-24 |  |  | 100%
SF-EC-RCM-PMGM | 116 days | Tue 22-10-24 | Tue 08-04-25 |  |  | 100%
PMGM- Perfomance & Goal Management | 94 days | Tue 22-10-24 | Fri 07-03-25
Explore - Workbook Workshop | 20 days | Tue 22-10-24 | Wed 20-11-24
Requirement gathering | 4 days | Tue 22-10-24 | Fri 25-10-24 | 12SS | HBT | 100%
Prepare Workbooks | 3 days | Mon 28-10-24 | Wed 30-10-24 | 21 | HBT | 100%
Review Workbooks with CTM & BPO | 3 days | Wed 06-11-24 | Fri 08-11-24 | 22FS+2 days | HBT & HCC | 100%
Incorporate changes suggested | 3 days | Wed 06-11-24 | Fri 08-11-24 | 23SS | HBT | 100%
Busienss Process walkthrough | 1 day | Mon 11-11-24 | Mon 11-11-24 | 24 | HBT | 100%
Incorporate changes & submit final BBP | 1 day | Tue 12-11-24 | Tue 12-11-24 | 25 | HBT | 100%
Approval & signoff of Workbook | 3 days | Wed 13-11-24 | Fri 15-11-24 | 26 | HCC | 100%
Explain master data & cutover data Template | 2 days | Mon 18-11-24 | Tue 19-11-24 | 27 | HBT | 100%
Circulate Master Data Template | 1 day | Tue 19-11-24 | Tue 19-11-24 | 28FF | HBT | 100%
Explore Phase Completion | 1 day | Wed 20-11-24 | Wed 20-11-24 | 29 | HBT & HCC
Deliverables | 3 days | Mon 18-11-24 | Wed 20-11-24
D: Filled Workbook | 1 day | Mon 18-11-24 | Mon 18-11-24 | 27 | HBT | 100%
D: Data Template | 1 day | Wed 20-11-24 | Wed 20-11-24 | 29 | HBT | 100%
Realize | 41 days | Tue 19-11-24 | Fri 17-01-25
System Configuration | 21 days | Tue 19-11-24 | Tue 17-12-24
Configuration of finalized business process | 15 days | Tue 19-11-24 | Mon 09-12-24 | 27FS+1 day | HBT | 100%
Custom Development | 15 days | Tue 19-11-24 | Mon 09-12-24 | 27FS+1 day |  | 100%
Data / Test Template Walkthrough | 1 day | Tue 10-12-24 | Tue 10-12-24 | 36 |  | 100%
Unit Testing by HBT | 5 days | Wed 11-12-24 | Tue 17-12-24 | 38 | HBT | 100%
Iteration | 7 days | Wed 18-12-24 | Fri 27-12-24
Solution Walkthrough | 7 days | Wed 18-12-24 | Fri 27-12-24 | 39 | TE & HBT
Solution Document Update | 2 days | Wed 18-12-24 | Thu 19-12-24 | 39 | HBT
Solution Rework | 2 days | Fri 20-12-24 | Mon 23-12-24 | 42 | TE & HBT
QA System Setup | 11 days | Tue 24-12-24 | Thu 09-01-25 |  | HBT
QA System Setup - Integration | 4 days | Tue 24-12-24 | Mon 30-12-24 | 43 | HBT
QA Setup - SF | 7 days | Tue 31-12-24 | Thu 09-01-25 | 45 | HCC
Training | 7 days | Tue 24-12-24 | Fri 03-01-25
Prepare manuals & Submit | 2 days | Tue 24-12-24 | Thu 26-12-24 | 43
Training Plan Preparation & Submission | 2 days | Fri 27-12-24 | Mon 30-12-24 | 48 | HBT
Conduct Training | 3 days | Tue 31-12-24 | Fri 03-01-25 | 49 | TE
Testing | 16 days | Tue 24-12-24 | Fri 17-01-25
Prepare Test Scripts | 3 days | Tue 24-12-24 | Fri 27-12-24 | 43 | HBT & TE
Conduct UAT | 10 days | Mon 30-12-24 | Mon 13-01-25 | 52 | HBT
Issue Resolution & Re Testing | 2 days | Tue 14-01-25 | Thu 16-01-25 | 53
UAT Sign off | 1 day | Fri 17-01-25 | Fri 17-01-25 | 54 | HBT
Deliverables | 16 days | Tue 24-12-24 | Fri 17-01-25
D: Updated workbook | 1 day | Tue 24-12-24 | Tue 24-12-24 | 43 | HBT
D: UAT | 1 day | Fri 17-01-25 | Fri 17-01-25 | 54 | HBT
D: User Manuals | 1 day | Fri 27-12-24 | Fri 27-12-24 | 48 | HBT
Deploy | 52 days | Wed 20-11-24 | Tue 04-02-25
Transport request to Production | 1 day | Mon 20-01-25 | Mon 20-01-25 | 55 | HBT
Conduct end user training | 7 days | Tue 21-01-25 | Wed 29-01-25 | 61 | TE
Provide & check roles & authorization | 3 days | Mon 20-01-25 | Wed 22-01-25 | 61SS | HBT
Receipt of master data | 43 days | Wed 20-11-24 | Wed 22-01-25 | 29 | TE
Upload master data in Production | 3 days | Thu 23-01-25 | Mon 27-01-25 | 64 | HBT & TE
Receipt of cutover data | 3 days | Thu 23-01-25 | Mon 27-01-25 | 64 | TE
Upload cutover data in production | 4 days | Tue 28-01-25 | Fri 31-01-25 | 66 | HBT & TE
GO-Live | 1 day | Mon 03-02-25 | Mon 03-02-25 | 67 | TE & HBT
Deliverables | 4 days | Thu 30-01-25 | Tue 04-02-25
D: End user training guide | 1 day | Thu 30-01-25 | Thu 30-01-25 | 62 | HBT
D: Go Live signoff | 1 day | Tue 04-02-25 | Tue 04-02-25 | 68 | HBT
Go Live | 1 day | Tue 04-02-25 | Tue 04-02-25 | 68 | HCC & HBT
Stabilization | 23 days | Wed 05-02-25 | Fri 07-03-25
Employee central & Recruitment | 109 days | Mon 04-11-24 | Tue 08-04-25
Explore - Workbook Workshop | 27 days | Mon 04-11-24 | Tue 10-12-24
Requirement gathering | 7 days | Mon 04-11-24 | Tue 12-11-24 |  | HBT | 100%
Prepare Workbooks | 3 days | Wed 13-11-24 | Fri 15-11-24 | 77 | HBT | 100%
Review Workbooks with CTM & BPO | 7 days | Wed 20-11-24 | Thu 28-11-24 | 78FS+2 days | HBT & HCC | 100%
Incorporate changes suggested | 7 days | Wed 20-11-24 | Thu 28-11-24 | 79SS | HBT | 100%
Busienss Process walkthrough | 1 day | Fri 29-11-24 | Fri 29-11-24 | 80 | HBT | 100%
Incorporate changes & submit final BBP | 1 day | Mon 02-12-24 | Mon 02-12-24 | 81 | HBT | 100%
Approval & signoff of Workbook | 3 days | Tue 03-12-24 | Thu 05-12-24 | 82 | HCC | 100%
Explain master data & cutover data Template | 2 days | Fri 06-12-24 | Mon 09-12-24 | 83 | HBT | 100%
Circulate Master Data Template | 1 day | Mon 09-12-24 | Mon 09-12-24 | 84FF | HBT | 100%
Explore Phase Completion | 1 day | Tue 10-12-24 | Tue 10-12-24 | 85 | HBT & HCC
Deliverables | 3 days | Fri 06-12-24 | Tue 10-12-24
D: Filled Workbook | 1 day | Fri 06-12-24 | Fri 06-12-24 | 83 | HBT | 100%
D: Data Template | 1 day | Tue 10-12-24 | Tue 10-12-24 | 85 | HBT | 100%
Realize | 56 days | Mon 09-12-24 | Thu 27-02-25
System Configuration | 31 days | Mon 09-12-24 | Thu 23-01-25
Configuration of finalized business process | 25 days | Mon 09-12-24 | Tue 14-01-25 | 83FS+1 day | HBT | 30% | In Process
Custom Development | 25 days | Mon 09-12-24 | Tue 14-01-25 | 83FS+1 day
Data / Test Template Walkthrough | 1 day | Thu 16-01-25 | Thu 16-01-25 | 92
Unit Testing by HBT | 5 days | Fri 17-01-25 | Thu 23-01-25 | 94 | HBT
Iteration | 7 days | Fri 24-01-25 | Mon 03-02-25
Solution Walkthrough | 7 days | Fri 24-01-25 | Mon 03-02-25 | 95 | TE & HBT
Solution Document Update | 2 days | Fri 24-01-25 | Mon 27-01-25 | 95 | HBT
Solution Rework | 2 days | Tue 28-01-25 | Wed 29-01-25 | 98 | TE & HBT
QA System Setup | 11 days | Thu 30-01-25 | Thu 13-02-25 |  | HBT
QA System Setup - Integration | 4 days | Thu 30-01-25 | Tue 04-02-25 | 99 | HBT
QA Setup - SF | 7 days | Wed 05-02-25 | Thu 13-02-25 | 101 | TE
Training | 7 days | Thu 30-01-25 | Fri 07-02-25
Prepare manuals & Submit | 2 days | Thu 30-01-25 | Fri 31-01-25 | 99
Training Plan Preparation & Submission | 2 days | Mon 03-02-25 | Tue 04-02-25 | 104 | HBT
Conduct Training | 3 days | Wed 05-02-25 | Fri 07-02-25 | 105 | TE
Testing | 21 days | Thu 30-01-25 | Thu 27-02-25
Prepare Test Scripts | 3 days | Thu 30-01-25 | Mon 03-02-25 | 99 | HBT & TE
Conduct UAT | 15 days | Tue 04-02-25 | Mon 24-02-25 | 108 | HBT
Issue Resolution & Re Testing | 2 days | Tue 25-02-25 | Wed 26-02-25 | 109
UAT Sign off | 1 day | Thu 27-02-25 | Thu 27-02-25 | 110 | HBT
Deliverables | 21 days | Thu 30-01-25 | Thu 27-02-25
D: Updated workbook | 1 day | Thu 30-01-25 | Thu 30-01-25 | 99 | HBT
D: UAT | 1 day | Thu 27-02-25 | Thu 27-02-25 | 110 | HBT
D: User Manuals | 1 day | Mon 03-02-25 | Mon 03-02-25 | 104 | HBT
Deploy | 64 days | Tue 10-12-24 | Wed 12-03-25
Transport request to Production | 1 day | Fri 28-02-25 | Fri 28-02-25 | 111 | HBT
Conduct end user training | 7 days | Mon 03-03-25 | Tue 11-03-25 | 117 | TE
Provide & check roles & authorization | 3 days | Fri 28-02-25 | Tue 04-03-25 | 117SS | HBT
Receipt of master data | 43 days | Tue 10-12-24 | Tue 11-02-25 | 85 | TE
Upload master data in Production | 4 days | Wed 12-02-25 | Mon 17-02-25 | 120 | HBT & TE
Receipt of cutover data | 4 days | Tue 18-02-25 | Fri 21-02-25 | 121 | TE
Upload cutover data in production | 7 days | Mon 24-02-25 | Tue 04-03-25 | 122 | HBT & TE
GO-Live | 1 day | Wed 05-03-25 | Wed 05-03-25 | 123 | TE & HBT
Deliverables | 5 days | Thu 06-03-25 | Wed 12-03-25
D: End user training guide | 1 day | Wed 12-03-25 | Wed 12-03-25 | 118 | HBT
D: Go Live signoff | 1 day | Thu 06-03-25 | Thu 06-03-25 | 124 | HBT
Go Live | 1 day | Thu 06-03-25 | Thu 06-03-25 | 124 | TE & HBT
Stabilization | 23 days | Fri 07-03-25 | Tue 08-04-25
Hand holding & issue resolution | 23 days | Fri 07-03-25 | Tue 08-04-25 | 128 | HBT