## Slide 1: HCC SF IMPLEMENTATION
WSR Report – 16/12/2024 – 24/12/2024.

## Slide 2: Agenda
Status Update & Work Stream Status
1
Activities Completed
2
Activities In Progress
3

## Slide 3: Project status summary – Phase Wise
Project Phases
Deliverables
Remarks
Prepare
Requirement Gathering Sessions.
Workbook review
Workbook Share with HCC.
Project Plan Review & Signoff
To Do
In Progress
Completed
Explore
EC , PMGM and RCM Workshop session
PMGM and RCM workbook sign off
Leave policy finalized by HCC Team
Workbook sign off is in progress
.
Decision taken
Time Sheet will not be part of Implementation confirmed by HCC Team.
Realize
PMGM Iteration 1 completed
EC, RCM Configuration is on track
Iteration 1 to be done in January mid week.

## Slide 4: EC – Status Report
Completed Activities:
Time Off Management: Worked on the development and refinement of time-off policies and processes.
Current Activity:
Additional Requirements: Successfully addressed and completed additional requirements discussed in the recent meeting, ensuring timely resolution of outstanding items.
Planned Activities for Next Week:
Pay Structure: Develop and finalize the company’s pay structure, ensuring alignment with compensation policies.
Company Structure Definition: Completed the definition of the company’s organizational structure, ensuring alignment with business goals and operational needs.
Business Rules Definition: Defined and documented key business rules to support operational workflows and ensure compliance with organizational standards.
Position Upload: Work on the upload of position data, ensuring correct mapping of roles to organizational structure.
Time Off Rule Development: Continue refining and finalizing time-off rules to ensure consistency and compliance across the organization.
Employee Data Upload: Begin preparations for the employee data upload, ensuring accuracy and completeness of all relevant information.
Module Status – On Track

## Slide 5: PMGM – Status Report
Completed Activity:
The workbook has been submitted to the business team and is now signed off by them on 06-Nov-24.
This Week:
System Configuration changes as per discussion during Iteration.
Planned Activities for next Week:
System demonstration to HCC team with changes captured during Iteration to take the Iteration signoff.
Iteration is completed on 19th Of December.
Module Status – On Track

## Slide 6: RCM – Status Report
Completed Activities in this week:
Finalized and uploaded the job requisition template in the provisioning section of Recruitment Management (RCM).
This Week:
Configured recruiting settings.
Planned activities for next week.
Application Field labels
Completed and uploaded the offer details template in the provisioning section of Recruitment Management (RCM).
Completed and uploaded the Application template in the provisioning section of Recruitment Management (RCM).
Developed the route map based on customer specifications.
Finalized and uploaded the candidate profile template in the provisioning section of Recruitment Management (RCM).
Set up recruiting team settings
Recruiting email triggers
Offer Letter Template
Configured the form template settings.
Created the rating scale according to customer requirements.
Set up position management settings.
Integrated positions with requisitions.
Manage email templates
Job req field labels
Module Status – On Track

## Slide 7: Overall Progress.
 | Prepare Phase 07-Nov-22 / 23-Oct-23 |  | Explore Phase 04-Nov-24 / 10-Dec-24 |  | Realize Phase 11-Dec-24 / 27-Feb-25 |  |  |  | Deploy 27-Feb-25 / 06-Mar-25 |  | Run 06-Mar-25 / 06-Mar-25
 | Kick-off | Preparation | Analyse & Solution Configuration | System Preparation | Business Unit Tests | Key-User Tests | UAT Test | Regression Analyse | Cut-Over | Handover | Go-Live
Employee Central | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
RCM | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started

## Slide 8: Overall Progress.
 | Prepare Phase 07-Nov-22 / 23-Oct-23 |  | Explore Phase 22-Oct-24 / 31-Dec-24 |  | Realize Phase 01-Jan-25 / 17-Jan-25 |  |  |  | Deploy 17-Jan-24 / 04-Feb-25 |  | Run 04-Feb-25 / 04-Feb-25
 | Kick-off | Preparation | Analyse & Solution Configuration | System Preparation | Business Unit Tests | Key-User Tests | UAT Test | Regression Analyse | Cut-Over | Handover | Go-Live
PMGM | Completed | Completed | Completed | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started

## Slide 9: Thanks