## ESS
ESS 2nd & 3rd Phase Go-Live 26 August 2024
Module | Development Status | Func Testing | UAT | Department
Claim-Transport/Vehicle/CDA Allowance | Complete | Pending | Pending | Fianance & HR
Claim-Laptop/Mobile | Complete | Pending | Pending | Fianance & HR
Reuimbersement Medical - PreIntimation Form | Complete | Not Yet Started | Pending | Fianance & HR
Reuimbersement Medical - MediClaim Form | In Process | Not Yet Started | Pending | Fianance & HR
Resignation | Complete | Not Yet Started | Pending | Fianance & HR
IT Declaration | Complete | Complete | Pending | Fianance
Loans(3rd Phase Go-Live) | Complete | Complete | Pending | Fianance & HR Intrgartion in SAP
Leave | In Process | In Process | Pending | Fianance & HR
Leave Encashment | In Process | In Process | Pending | Fianance & HR
Claim - LTC | In Process | In Process | Pending | Fianance & HR
TaxForeCast - 80C,80D,89A other incude from SAP Side(3 rd phase Go-Live) | Pending | Pending | Pending | SAP Note to be implemented for New Annexture as Directed by Finance Minister of India
ESS 1st Phase Go Live -22-Aug-2024
Employee Training
Employee Details
Birthday & Work Anniversary
Claim - Breif Case,Camp Office,Composite Transfer Grant,Electricity Bill,Shifting,Wireless Communication
Policy Details
Holiday Details
NOC
Employee Directory
PaySlip
Form16
Annoucement Creation