## SIT (hidden)
Sr No | Module | Object No | Development Description | WRICEF Category | Priority | Complexity | Functional Consultant | RGS Planned Date | RGS Actual Date | RGS Status | FS Planned Date | FS Actual Date | FS Status | Technical Consultant | Developement Planned start Date | Developemnt Actual Start Date | Developemnt Planned Finish Date | Development Actual Finish Date | Development Status | HBT Testing Status | CTM Testing Status | UAT Sign OFF | BPO / CTM Signature | PRD Status | Department | Remark
1 | PS | KCC_CN_PS_02 | Base Planning Object Upload | Conversion | SIT | Medium | Pranay Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
2 | PS | KCC_CN_PS_03 | Execution BOQ Master Upload | Conversion | SIT | Medium | Pranay Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
3 | PS | KCC_CN_PS_04 | Cost Plan Upload | Conversion | SIT | Complex | Pranay Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
4 | PS | KCC_EN_PS_05 | Work Plan | Enhancement | SIT | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
5 | PS | KCC_EN_PS_09 | DPR Entry | Enhancement | SIT | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
6 | PS | KCC_RP_PS_11 | Cost Plan version Comparison with Actual (Qty & Amount) | Report | Go Live | Complex | Pranay Reddy | 2022-07-27 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
7 | PS | KCC_EN_PS_15 | Conversion of Work order line items to Client bill Qty Through coefficient in DPR report | Enhancement | Go Live | Medium | Pranay Reddy | 2022-07-27 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
8 | PS | KCC_WF_PS_16 | DPR has an Workflow of Approval | Workflow | SIT | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
9 | FI | KCC_EN_FI_01 | Validation on GSTN Number in Vendor Master | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
10 | FI | KCC_EN_FI_04 | Additional Tab in GL Master data | Enhancement | SIT | Complex | Venkat Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
11 | FI | KCC_EN_FI_07 | Capture GSTN Number in FB70 Screen | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
12 | FI | KCC_EN_FI_09 | Validation on un-registered vendor invoice(Limit-20L) | Enhancement | SIT | Simple | Venkat Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
13 | FI | KCC_EN_FI_10 | Validation on without PAN Vendor Payment(Limit-50K):F-53 | Enhancement | SIT | Simple | Venkat Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
14 | FI | KCC_EN_FI_11 | Validation on one time vendor invoice(Limit-10K) | Enhancement | SIT | Simple | Venkat Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
15 | FI | KCC_EN_FI_12 | Display GSTN Number in FB60 Screen | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
16 | FI | KCC_EN_FI_13 | Display GSTN Number in MIRO Screen | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
17 | FI | KCC_EN_FI_14 | Validation on composition vendor invoice bookings | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
18 | FI | KCC_EN_FI_16 | Validation/Check for duplicate vendor invoice(FB60/MIRO) | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
19 | FI | KCC_RP_FI_24 | Tax Code Change Restriction on MIRO | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
20 | MM | KCC_FM_MM_01 | Purchase requisition Print | Form | SIT | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
21 | MM | KCC_FM_MM_03 | Service PO | Form | SIT | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
22 | MM | KCC_FM_MM_04 | Service/Work order PR print | Form | Go Live | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
23 | MM | KCC_FM_MM_06 | Work Order Print | Form | SIT | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
24 | MM | KCC_EN_MM_07 | WO terms & condition Header | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
25 | MM | KCC_EN_MM_08 | Materials _T&C_Materials to be issued & Recovery | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
26 | MM | KCC_EN_MM_09 | Advance request & its recovery | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
27 | MM | KCC_EN_MM_10 | Wo Terms & condition _Item Condition(Escalation) | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
28 | MM | KCC_EN_MM_11 | RA BILL Preparation_Work done quantity confirmation against Work order with SES posting | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
29 | MM | KCC_EN_MM_13 | Material recovery against Work done | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
30 | MM | KCC_EN_MM_16 | Posting of invoice,recovery,debit note,credit note,etc document along with Payment abstract screen | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
31 | MM | KCC_EN_MM_18 | Work order & vendor entry while material issue to Subcon & Restrict material issue against WO | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
32 | MM | KCC_EN_MM_24 | In Migo Screen Input In Goods Receipt Note(GRN) at MIGO screen Required Fields are Royalty No, Royalty Date-Item Wise, Royality Qty, Royality Location, E-way Bill No,E-way Bill date, LR Number, LR Date, Security Gate Entry Number, Gate Entry Number date, DMR Number, DMR Date , Custom field for Rack & Bin, Challan no., challan date, Invoice no., invoice date, RST No. | Enhancement | SIT | Simple | Abhishek Godse | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
33 | MM | KCC_EN_MM_25 | DMR Entry process | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-26 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
34 | MM | KCC_EN_MM_27 | Material reservation Process required Supplier code | Enhancement | Go Live | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
35 | MM | KCC_EN_MM_35 | Quantity check valiadtion in PR with WBS | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
36 | MM | KCC_EN_MM_36 | Stock overview at PR screen | Enhancement | SIT | Medium | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
37 | MM | KCC_EN_MM_39 | Custom Workflow for PR | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase/Store
38 | MM | KCC_EN_MM_42 | Item text field mandatory for the material for which technical specifications are required in PR | Enhancement | SIT | Medium | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
39 | MM | KCC_EN_MM_44 | Notifiction if class A materials stock falls below defined safety level along with screen. | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
40 | MM | KCC_EN_MM_50 | Addition fields in PO to capture FOC value | Enhancement | SIT | Medium | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase /P&M
41 | MM | KCC_WF_MM_52 | Custom Workflow for PO | Workflow | SIT | Medium | Abhishek Godse | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
42 | HCM | KCC_IN_HCM_11 | RFC SAP to Time Watch | Interface | SIT | Simple | Muzammil Ansari | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
43 | HCM | KCC_IN_HCM_12 | RFC Time Watch to SAP | Interface | SIT | Simple | Muzammil Ansari | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
44 | SD | KCC_WF_SD_01 | Sales Order approval Process | Workflow | Go Live | Medium | Nitin Kumar | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Client Billing
45 | PM | KCC_EN_PM_02 | Custom screen for installation and dismantle of Tyre and battery | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-26 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
46 | PM | KCC_EN_PM_03 | New custom fields (Requested Plant, Transfer/Hire/Purchase etc ) are required in notification screen | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
47 | PM | KCC_RP_PM_09 | Equipment & Plant Utilization, Performance & Cost Analysis Based upon the Log Entry of equipments, Utilization (Productivity) & performance report will be required to generate. Period wise for a Plant, group of Plants & for individual Equipment. | Report | Go Live | Complex | Prateek Srivastav | 2022-07-27 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
48 | PM | KCC_EN_PM_10 | Auto assignment of Settlement Rule in Equipment Consumption Order as per Equipment Log Entry (CO Entry posting WBS wise ) | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-25 |  | Not Submitted | 2022-07-25 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
49 | PM | KCC_EN_PM_11 | A common Log Entry (Plant/Equipment) screen for capturing Hours, KM, Energy Hour Meter reading etc. of own equipments & Plant & LMV | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-28 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
50 | PM | KCC_EN_PM_12 | Auto Creation of Consumption order | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
51 | PM | KCC_EN_PM_14 | Custom table to maintain the hiring rates and condition | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-26 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
52 | PM | KCC_EN_PM_15 | Module Pool for Maintainance Plan | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-27 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
53 | PM | KCC_EN_PM_16 | Scheduling of Maintainace Plan | Enhancement | SIT | Medium | Prateek Srivastav | 2022-07-28 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
54 | PM | KCC_EN_PM_17 | Auto Generation of Maintainance Order from Maintainance Plan | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-28 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical

## Go Live (hidden)
Sr No | Module | Object No | Development Description | WRICEF Category | Priority | Complexity | Functional Consultant | RGS Planned Date | RGS Actual Date | RGS Status | FS Planned Date | FS Actual Date | FS Status | Technical Consultant | Developement Planned start Date | Development Actual Start Date | Developemnt Planned Finish Date | Development Actual Finish Date | Development Status | HBT Testing Status | CTM Testing Status | CTM Testing Status | UAT Sign OFF | BPO / CTM Signature | PRD Status | Department | Remark
1 | PS | KCC_EN_PS_17 | DPR punching Qty will be Validated against Balance Work order Qty +PR Qty | Enhancement | Go Live | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-08-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Planning
2 | FI | KCC_IN_FI_21 | Payment Interface | Interface | Go Live | Complex | Venkat Reddy | 2022-08-06 |  | Not Submitted | 2022-08-06 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
3 | FI | KCC_RP_FI_22 | Payment Interface Report | Report | Go Live | Complex | Venkat Reddy | 2022-08-06 |  | Not Submitted | 2022-08-09 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
4 | FI | KCC_RP_FI_26 | GST Credit Report | Report | Go Live | Medium | Venkat Reddy | 2022-08-02 |  | Not Submitted | 2022-08-03 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
5 | FI | KCC_RP_FI_26 | Vendor Payment Process | Report | Go Live | Complex | Venkat Reddy | 2022-08-03 |  | Not Submitted | 2022-08-07 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
6 | FI | KCC_RP_FI_27 | Trial Balance report | Report | Go Live | Complex | Venkat Reddy | 2022-08-06 |  | Not Submitted | 2022-08-10 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
7 | FI | KCC_RP_FI_30 | Invoice Print (FB70) | Enhancement | Go Live | Simple | Venkat Reddy | 2022-08-01 |  | Not Submitted | 2022-08-03 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
8 | MM | KCC_FM_MM_02 | Purchase Order Print | Form | Go Live | Simple | Abhishek Godse | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Purchase
9 | MM | KCC_FM_MM_15 | Material Issue & Return (Loan Basis) | Form | Go Live | Complex | Abhishek Godse | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Store
10 | MM | KCC_FM_MM_17 | Transportation PO | Form | Go Live | Simple | Abhishek Godse | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Purchase
11 | MM | KCC_FM_MM_22 | Material Rejection Note | Form | Go Live | Simple | Abhishek Godse | 2022-08-03 |  | Not Submitted | 2022-08-04 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Store
12 | MM | KCC_FM_MM_51 | QR code print for Materials | Form | Go Live | Medium | Abhishek Godse | 2022-08-03 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Store
13 | HCM | KCC_RP_HCM_13 | Salary Register Report | Report | Go Live | Medium | Muzammil Ansari | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
14 | HCM | KCC_RP_HCM_14 | Salary Hold/Release Report | Report | Go Live | Simple | Muzammil Ansari | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
15 | HCM | KCC_RP_HCM_15 | Bank Csv file report | Report | Go Live | Medium | Muzammil Ansari | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
16 | HCM | KCC_CN_HCM_16 | Earning & Deduction Upload | Conversion | Go Live | Simple | Muzammil Ansari | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
17 | HCM | KCC_RP_HCM_17 | Attendance Report | Report | Go Live | Simple | Muzammil Ansari | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
18 | HCM | KCC_FM_HCM_18 | Form 16 | Form | Go Live | Simple | Muzammil Ansari | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
19 | SD | KCC_FM_SD_02 | Project Sale Invoice Print (EPC,Item Rate, HAM Contract) | Form | Go Live | Medium | Nitin Kumar | 2022-07-27 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
20 | SD | KCC_FM_SD_03 | Scrap Sale Inovice Print | Form | Go Live | Medium | Nitin Kumar | 2022-07-27 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
21 | SD | KCC_FM_SD_04 | Asset Sale Invoice Print | Form | Go Live | Medium | Nitin Kumar | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
22 | SD | KCC_FM_SD_05 | Material Sale Invoice Print | Form | Go Live | Medium | Nitin Kumar | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
23 | PM | KCC_RP_PM_01 | Tyre and Battery history report | Report | Go Live | Medium | Prateek Srivastav | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical
24 | PM | KCC_FM_PM_04 | Print for Multiple Equipment request | Form | Go Live | Simple | Prateek Srivastav | 2022-08-05 |  | Not Submitted | 2022-08-06 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical
25 | PM | KCC_FM_PM_05 | Reservation Print | Form | Go Live | Simple | Prateek Srivastav | 2022-08-02 |  | Not Submitted | 2022-08-03 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical
26 | PM | KCC_FM_PM_13 | Print for Hired Equipment daily uses and fuel qty | Form | Go Live | Simple | Prateek Srivastav | 2022-08-07 |  | Not Submitted | 2022-08-08 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical

## Post Go Live (hidden)
Sr No | Module | Object No | Development Description | WRICEF Category | Priority | Complexity | Functional Consultant | RGS Planned Date | RGS Actual Date | RGS Status | FS Planned Date | FS Actual Date | FS Status | Technical Consultant | Developement Planned start Date | Development Actual Start Date | Developemnt Planned Finish Date | Development Actual Finish Date | Development Status | HBT Testing Status | CTM Testing Status | UAT Sign OFF | BPO / CTM Signature | PRD Status | Department | Remark
1 | PS | KCC_RP_PS_06 | Planned Monthly Material Report | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
2 | PS | KCC_RP_PS_07 | Planned Monthly Equipment/Labour Report | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
3 | PS | KCC_RP_PS_08 | Planned Monthly Service Report | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
4 | PS | KCC_RP_PS_10 | DPR Detailed report | Report | Post Go Live | Medium | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
5 | PS | KCC_RP_PS_12 | Major material required Vs issued against Subcon work order line item. | Report | Post Go Live | Medium | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
6 | PS | KCC_RP_PS_13 | Unit Rate Comparison BPO Vs Actual | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
7 | PS | KCC_RP_PS_14 | DPR Vs IPC Vs Subcon | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
8 | QM | KCC_EN_QM_01 | Email trigger for the inspection lot rejection | Enhancement | Post Go Live | Simple | Vijay Dhembare |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | QS
9 | QM | KCC_FM_QM_03 | Customized Inspection Form | Form | Post Go Live | Simple | Vijay Dhembare |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | QS
10 | QM | KCC_FM_QM_04 | Quality Certificate | Form | Post Go Live | Simple | Vijay Dhembare |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | QS
11 | FI | KCC_EN_FI_02 | Additional Tab in Asset Master data | Enhancement | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
12 | FI | KCC_RP_FI_06 | BG Report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
13 | FI | KCC_RP_FI_18 | Asset report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
14 | FI | KCC_EN_FI_19 | Upload Program for BRS | Conversion | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
15 | FI | KCC_FM_FI_20 | Multiple Cheque Printing | Form | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
16 | FI | KCC_RP_FI_23 | GSTR1 (Sales Register) | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
17 | FI | KCC_RP_FI_24 | GSTR2 (Purchase Register) | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
18 | FI | KCC_RP_FI_25 | GST E-Invoice extract report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
19 | FI | KCC_RP_FI_23 | MSME Vendor Reports | Report | Post Go Live | Medium | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
20 | FI | KCC_RP_FI_25 | LC report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
21 | FI | KCC_RP_FI_28 | Balance Sheet Report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
22 | FI | KCC_RP_FI_29 | Cashflow Report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
23 | MM | KCC_RP_MM_05 | Purchase Register required with PR to Payment process. | Report | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
24 | MM | KCC_FM_MM_12 | Payment abstract Print | Form | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
25 | MM | KCC_RP_MM_14 | Inventory Analysis report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
26 | MM | KCC_RP_MM_19 | PR to Payment abstract Report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
27 | MM | KCC_FM_MM_20 | RA Bill Print | Form | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
28 | MM | KCC_FM_MM_21 | NON RETURNABLE/ RETURNABLE GATE PASS | Form | Post Go Live | Simple | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
29 | MM | KCC_FM_MM_23 | Backdated PR not to be created (validation on Delivery Date) | Enhancement | Post Go Live | Simple | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
30 | MM | KCC_RP_MM_26 | Asset Spares tracking report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
31 | MM | KCC_EN_MM_28 | Develop RFC to push master data in WBMS - Material | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
32 | MM | KCC_IN_MM_29 | Develop RFC to push master data in WBMS - Vendor (Supplier, Transporter, Subcontractor etc) | Interface | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
33 | MM | KCC_IN_MM_30 | Develop RFC to push master data in WBMS - Plant/Project codes | Interface | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
34 | MM | KCC_IN_MM_31 | Develop RFC to push master data in WBMS - Storage location | Interface | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
35 | MM | KCC_IN_MM_32 | Develop RFC to receive transaction data to SAP | Interface | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
36 | MM | KCC_RP_MM_33 | Store Inventory Report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
37 | MM | KCC_FM_MM_34 | HSD Register Print | Form | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
38 | MM | KCC_EN_MM_37 | Mass PO short closure | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
39 | MM | KCC_EN_MM_38 | PR auto deletion if no action taken for 30 days from the creation date | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
40 | MM | KCC_WF_MM_40 | Validation not to allow backdated PO to be created (expect some users) | Workflow | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
41 | MM | KCC_EN_MM_41 | Notification if no action is taken against the PR for more than 72 hrs from the date of final release | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
42 | MM | KCC_EN_MM_43 | RFQ Comparison screen | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
43 | MM | KCC_EN_MM_45 | Adding custom fields in standard stock reports | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
44 | MM | KCC_EN_MM_46 | Mail to vendor along with RFQ print | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
45 | MM | KCC_FM_MM_47 | RFQ Print | Form | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
46 | MM | KCC_EN_MM_48 | Reminder to vendor (RFQ) | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
47 | MM | KCC_RP_MM_49 | Material Aging report | Report | Post Go Live | Simple | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
48 | MM | KCC_EN_MM_53 | Enhancement in MIGO Screen to update the data from Wigh Bridge | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
49 | HCM | KCC_FM_HCM_01 | Increment Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
50 | HCM | KCC_FM_HCM_02 | Promotion Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
51 | HCM | KCC_FM_HCM_03 | Reliving Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
52 | HCM | KCC_FM_HCM_04 | Experience Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
53 | HCM | KCC_FM_HCM_05 | Disciplinary Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
54 | HCM | KCC_FM_HCM_06 | Offer Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
55 | HCM | KCC_FM_HCM_07 | Appointment Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
56 | HCM | KCC_EN_HCM_08 | Pop up for Driving License | Enhancement | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
57 | HCM | KCC_EN_HCM_09 | Pop for Confirmation | Enhancement | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
58 | HCM | KCC_EN_HCM_10 | Pop for Retirement | Enhancement | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
59 | SD | KCC_EN_SD_06 | Validation in Scrap Sale for Hazard material to Customer | Enhancement | Post Go Live | Medium | Nitin Kumar |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Client Billing
60 | PM | KCC_WF_PM_06 | Breakdown Mail | Workflow | Post Go Live | Simple | Prateek Srivastav |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
61 | PM | KCC_RP_PM_07 | Schedule Maintenance - Service Schedule Report | Report | Post Go Live | Complex | Prateek Srivastav |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
62 | PM | KCC_RP_PM_08 | RTO Permit and Insurance schedule report | Report | Post Go Live | Simple | Prateek Srivastav |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical

## Plan vs Actual (hidden)
SIT |  | As On Date | 2022-09-03
Module | Total | Hold | Cancelled | Balance | RGS Status till 3rd Sep |  | FS Status till 3rd Sep |  | Development Status till 3rd Sep |  | Functional testing Status till 3rd Sep |  | CTM testing Status till 3rd Sep
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Go Live |  | As On Date | 2022-09-03
Module | Total | Hold | Cancelled | Balance | RGS Status |  | FS Status |  | Development Status till 25th Aug |  | Functional testing Status till 22nd Aug |  | CTM testing Status till 22nd Aug
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a
Post Go Live |  | As On Date | 2022-09-01
Module | Total | Hold | Cancelled | Balance | RGS Status |  | FS Status |  | Development Status till 25th Aug |  | Functional testing Status till 22nd Aug |  | CTM testing Status till 22nd Aug
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall
Module | Total | Hold | Cancelled | Balance | RGS Status |  | FS Status |  | Development Status |  | Functional testing Status till 22nd Aug |  | CTM testing Status till 22nd Aug
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 11 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Wave1B Plan
| Project : SRC Infra Developers_Rise with SAP S/4HA Implementation | [6 empty] | As On: | 2024-08-02
Complexity |  |  |  |  | MM |  | PS | QM | DMS | FICO | SD |  |  | Cancelled | Grand Total
Complex |  |  |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0
Medium |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Simple |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Grand Total |  |  |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0
[11 empty] | RGS | [5 empty] | FS |  |  |  | Configuration |  |  | ABAP Development | [7 empty] | HBT Testing | [7 empty] | CTM Testing | [8 empty] | UAT Sign Off |  |  |  | Go-Live |  |  |  | Reusability
Sr No | Module | BBP Process | New Development Comments | Development Description | Scope | FRICE Category | Priority | Priority | Complexity | Functional Consultant | Planned Approval | Revised -Actual Date | Revised Approval | Actual Submission | Actual Approval | RGS Status | Planned Date | Revised Date | Actual Date | FS Status | Planned Date | Actual Date | Status | Plan ABAP Consultant | Actual ABAP Consultant | Duration | Planned Start | Planned Finish | Actual Start | Actual Finish | Development Status | UT-SIT Test Scripts Planned Finish | UT-SIT Test Scripts Actual Finish | Testing Planned Start | Testing Planned Finish | Testing Planned Duration | Testing Actual Start | Testing Actual Finish | HBT Testing Status | CTM Name | CTM Name | Training Finish | Duration | Planned Start | Planned Finish | Actual Start | Actual Finish | CTM Testing Status | Fil Test Script Submission Date | UAT Planned Date | UAT Actual Date | UAT Status | PRD Status | Duration | Go-Live Planned Date | Go-Live Actual Date | Reusable Object | Reusable Client me | HBT Remarks | Remarks | Additiol Efforts
1 | PS/SD | Financial Progress |  | Financial Progress | SOW | Report | 1 | Post Go Live | Complex | Sameer/Aditi | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Nikhil |  | 7 | 2024-08-09 | 2024-08-16 | [5 empty] | 2024-08-17 | 2024-08-18 | 1 |  |  |  | Usman |  |  | 1 | 2024-08-19 | 2024-08-20 | [8 empty] | 3 | 2024-08-23
2 | PS | Planned vs Achieved Revenue |  | Planned vs Achieved Revenue | SOW | Report | 2 | Post Go Live | Complex | Sameer | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Nikhil |  | 6 | 2024-08-17 | 2024-08-23 | [5 empty] | 2024-08-24 | 2024-08-25 | 1 |  |  |  | Usman |  |  | 1 | 2024-08-26 | 2024-08-27 | [8 empty] | 3 | 2024-08-30
3 | PS | Planned Qty vs Actual Qty |  | Planned Qty vs Actual Qty | SOW | Report | 3 | Post Go Live | Complex | Sameer | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Nikhil |  | 6 | 2024-08-24 | 2024-08-30 | [5 empty] | 2024-08-31 | 2024-09-01 | 1 |  |  |  | Usman |  |  | 1 | 2024-09-02 | 2024-09-03 | [8 empty] | 3 | 2024-09-06
4 | PM | Equipment Utilization |  | Equipment Utilization | SOW | Report | 4 | Post Go Live | Complex | Imtiyaz | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Nikhil |  | 5 | 2024-08-31 | 2024-09-05 | [5 empty] | 2024-09-06 | 2024-09-07 | 1 |  |  |  | Tejas |  |  | 1 | 2024-09-08 | 2024-09-09 | [8 empty] | 3 | 2024-09-12
5 | FI | Advance Repayment |  | Advance Repayment | SOW | Report | 5 | Post Go Live | Complex | Akhil | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Mandhar |  | 7 | 2024-08-09 | 2024-08-16 | [5 empty] | 2024-08-17 | 2024-08-18 | 1 |  |  |  | Shravani |  |  | 1 | 2024-08-19 | 2024-08-20 | [8 empty] | 3 | 2024-08-23
6 | FI | Asset Details |  | Asset Details | SOW | Report | 6 | Post Go Live | Complex | Akhil | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Mandhar |  | 6 | 2024-08-17 | 2024-08-23 | [5 empty] | 2024-08-24 | 2024-08-25 | 1 |  |  |  | Shravani |  |  | 1 | 2024-08-26 | 2024-08-27 | [8 empty] | 3 | 2024-08-30
7 | FI | Liability Details |  | Liability Details | SOW | Report | 7 | Post Go Live | Complex | Akhil | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Mandhar |  | 6 | 2024-08-24 | 2024-08-30 | [5 empty] | 2024-08-31 | 2024-09-01 | 1 |  |  |  | Shravani |  |  | 1 | 2024-09-02 | 2024-09-03 | [8 empty] | 3 | 2024-09-06
8 | FI | Turnover Vs Liability |  | Turnover Vs Liability | SOW | Report | 8 | Post Go Live | Complex | Akhil | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Rishabh |  | 7 | 2024-08-09 | 2024-08-16 | [5 empty] | 2024-08-17 | 2024-08-18 | 1 |  |  |  | Shravani |  |  | 1 | 2024-08-19 | 2024-08-20 | [8 empty] | 3 | 2024-08-23
9 | FI | Turnover Vs Direct Cost |  | Turnover Vs Direct Cost | SOW | Report | 9 | Post Go Live | Complex | Akhil | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Rishabh |  | 6 | 2024-08-17 | 2024-08-23 | [5 empty] | 2024-08-24 | 2024-08-25 | 1 |  |  |  | Shravani |  |  | 1 | 2024-08-26 | 2024-08-27 | [8 empty] | 3 | 2024-08-30
10 | FI/MM | Inventory |  | Inventory | SOW | Report | 10 | Post Go Live | Complex | Akhil/Nihar | 2024-08-07 | [5 empty] | 2024-08-09 | [6 empty] | Rishabh |  | 6 | 2024-08-24 | 2024-08-30 | [5 empty] | 2024-08-31 | 2024-09-01 | 1 |  |  |  | Shravani |  |  | 1 | 2024-09-02 | 2024-09-03 | [8 empty] | 3 | 2024-09-06
Formulas:
Testing Planned Start = 1+[Planned Finish]
Testing Planned Finish = [Testing Planned Start]+1
Planned Start = [Testing Planned Finish]+[Duration]
Planned Finish = [Planned Start]+1
Go-Live Planned Date = [Duration]+[Planned Finish]

## Sheet1 (hidden)
Module | Development description | WRICEF Type | Priority | Complexity | Reusability | Project | Priority 2
PS | WBS, Network, Activity, Mileston Upload Program | Conversion | Go-Live | Simple | YES | Mecon | Must Have
PS | BPO Upload Program | Conversion | Go-Live | Simple | YES | Sunteck | Must Have
PS | Unit Cost Plan Upload Program | Conversion | Go-Live | Simple | YES | Sunteck | Must Have
PS | Budget Approval Procedure & document attachment compulsary | Workflow | SIT | Complex |  |  | Must Have
PS | Budget Exceed mail trigger | Enhancement | Go-Live | Medium | YES | Sunteck
PS | Milestone Confimation Mail Notification with completion Image & architect certificate attachement | Enhancement | SIT | Complex | YES | Sunteck | Must Have
PS | Project & Work Breakdown Structure sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | WBS & Milestones (Payment milestones plans) sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | Budget sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | Budget Updates / Transfer sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | Link BOQ to WBS in SAP then sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
DMS | All attached documents in SAP to view in Contentverse DMS | Interface | Go-Live | Complex |  |  | Must Have
FICO | Vendor master upload | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | Asset Cutover upload Program | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | Cutover Template | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | GSTR1 | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | GSTR2 | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | Customer Ageing | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | Vendor Ageing | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | Bank Reco Upload Program | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | Bank Payment Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Bank Receipt Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Cash Payment Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Cash Receipt Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Journal Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Customer Tax Invoice (Interest) | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Customer Receipt Screen | Enhancement | Go-Live | Complex |  |  | Must Have
FICO | Customer Receipt List | Enhancement | Go-Live | Complex |  |  | Must Have
FICO | Project & Plants Mapping table | Enhancement | SIT | Complex |  |  | Must Have
FICO | Interest waiver report | Report | Go-Live | Complex |  |  | Must Have
FICO | Cheque Print | Form | Go-Live | Complex |  |  | Must Have
FICO | Related Party or Intercompany | Report | Post Go-Live | Complex |  |  | Must Have
FICO | Token Amount SFDC-SAP | Interface | SIT | Complex |  |  | Must Have
FICO | Customer Receipts (SFDC) | Interface | SIT | Complex |  |  | Must Have
FICO | Interest Waiver | Interface | SIT | Complex |  |  | Must Have
FICO | GST ASP/GSP | Interface | Go-Live | Complex |  |  | Must Have
FICO | HDFC NEFT Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | HDFC RTGS Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | ICICI NEFT Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | ICICI RTGS Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | INDUSIND RTGS Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | INDUSIND NEFT Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | KOKAT Bulk NEFT Format | Report | Go-Live | Medium |  |  | Good to Have
SD | Unit Upload Program | Conversion | Go-Live | Medium | YES | M3M | Must Have
SD | Other Charges Upload Program | Conversion | Go-Live | Medium | YES | M3M
SD | Customer creation Program | Conversion | Go-Live | Simple | YES | M3M | Must Have
SD | Unit availability report | Report | SIT | Complex | YES | M3M | Must Have
SD | Unit Status (Sold /unsold/reserved) | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Sales Order creation Program | Conversion | Go-Live | Complex | YES | M3M | Must Have
SD | Mass Demand creation Program | Report | Go-Live | Medium | YES | Sunteck | Must Have
SD | Auto Debit /Credit Note Program | Enhancement | Go-Live | Complex
SD | Car Parking program | Enhancement | SIT | Complex | YES | Sunteck | Must Have
SD | Sales order mail trigger at the different approval level | Enhancement | Go-Live | Complex
SD | Additional Custom tab in SO (Additional Field) | Enhancement | SIT | Medium | YES | Sunteck
SD | Price custom routine 1(land abatment) for Unit | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Price custom routine 2(Net of land abatment) for Unit | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Price custom routine for discount calculation for Unit | Enhancement | SIT | Complex |  |  | Must Have
SD | Price custom routine for GST % After OC Receive for Unit | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Price custom routine for GST % After OC Receive for other charges | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Car Parking status report | Report | SIT | Simple | YES | M3M
SD | Milestone wise demand report(Amout vs actual receipt amount)/MIS Sales | Report | SIT | Medium | YES | M3M | Must Have
SD | Welcome letter | Form | SIT | Medium | YES | M3M | Must Have
SD | Booking Form | Form | SIT | Medium | YES | M3M | Must Have
SD | Reminder letter1 | Form | SIT | Simple | YES | M3M | Must Have
SD | Reminder letter2 | Form | SIT | Simple | YES | M3M | Must Have
SD | Termination Form | Form | SIT | Complex | YES | Sunteck | Must Have
SD | Agreement Form | Form | SIT | Complex | YES | Sunteck | Must Have
SD | Application form | Form | SIT | Complex |  |  | Must Have
SD | Demand form | Form | SIT | Complex | YES | Sunteck | Must Have
SD | Customer ledger | Form | SIT | Complex | YES | M3M
SD | Email trigger demand and 7 days of reminder1 & 7days of reminder 2 | Report | SIT | Complex | YES | Sunteck | Must Have
SD | Unit Transfer Process with Work flow(Approval process) | Report | SIT | Complex | YES | Sunteck | Must Have
SD | Unit Cancallation Process with workflow(Approval process) | Report | SIT | Complex | YES | M3M | Must Have
SD | Unit Cancallation Reports | Report | SIT | Medium | YES | Sunteck | Must Have
SD | Brokerage payout Process | Report | SIT | Complex | YES | Sunteck | Must Have
SD | Brokerage payout Report | Report | SIT | Medium | YES | Sunteck | Must Have
SD | Unit Master sync with SFDC | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Unit master Stauts(Two way) | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Customer master amendment | Interface | SIT | Complex |  |  | Must Have
SD | Broker Creation from SFDC to SAP | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Broker Invoice creation from SAP to SFDC | Interface | SIT | Complex |  |  | Must Have
SD | Broker payment SAP-SFDC | Interface | SIT | Complex |  |  | Must Have
SD | Booking creation SFDC-SAP | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Booking amendment | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Demand information sync to SFDC | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Debit note - wrt Demand no | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Credit note - wrt Demand no | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Unit Transfer | Interface | SIT | Complex |  |  | Must Have
SD | Unit Cancellation | Interface | SIT | Complex |  |  | Must Have
SD | E invoicing & E Way Bill | Interface | SIT | Complex |  |  | Must Have
SD | Post Possession clearance | Interface | SIT | Complex |  |  | Must Have
SD | Mail intimation during 10 % of agreement amount receipt | Enhancement | SIT | Medium
MM | Material Master Upload Program | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | Service Master Upload Program | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | HSN Master Upload-LSMW | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | Cutover Purchase Order Upload Program | Conversion | Go-Live | Complex | YES | RDPL | Must Have
MM | Cutover Work Order Upload Program | Conversion | Go-Live | Complex | YES | RDPL | Must Have
MM | Initial Stock Upload Program | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | Indent Print | Form | Post Go-Live | Simple
MM | Indent Amendment | Form | Post Go-Live | Complex
MM | Store Requistion | Form | Post Go-Live | Simple
MM | Purchase Order Print | Form | SIT | Simple | YES | RDPL | Must Have
MM | Purchase Order Amendment | Form | SIT | Complex |  |  | Must Have
MM | Work Order Print | Form | SIT | Simple | YES | RDPL | Must Have
MM | Work Order Amendment | Form | SIT | Complex |  |  | Must Have
MM | GRN Print Form | Form | Post Go-Live | Simple
MM | GRN Interloc | Form | Post Go-Live | Simple
MM | Workdone Print | Form | SIT | Complex |  |  | Must Have
MM | Goods Issue Slip | Form | Post Go-Live | Simple
MM | Goods Issue Return Slip | Form | Post Go-Live | Simple
MM | Stock Adjustment | Form | Post Go-Live | Simple
MM | Stock Out Form | Form | Post Go-Live | Simple
MM | Transfer(Issue) to Contractor | Form | Post Go-Live | Simple
MM | Purchase (Material) Debit Note | Form | Post Go-Live | Simple
MM | Purchase (Service) Debit Note | Form | Post Go-Live | Simple
MM | Purchase Enquiry | Form | Post Go-Live | Simple
MM | Bill Inward Print | Form | SIT | Simple
MM | RA Bill Certificate of Payment | Form | SIT | Complex |  |  | Must Have
MM | RA Bill Item Rate | Form | SIT | Complex
MM | Purchase Bill | Form | SIT | Simple |  |  | Must Have
MM | Non-Store Puchase Bill | Form | SIT | Simple |  |  | Must Have
MM | Payment Request | Form | SIT | Simple
MM | Vendor Onboading | Form | Post Go-Live | Simple
MM | Purchase Register - Indent to Payment | Report | Post Go-Live | Complex
MM | PR Mandatory for PO | Enhancement | SIT | Simple | YES | RDPL | Must Have
MM | Work Order Amendment Enhancement | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Release Strategy mandatory for PO/WO saving | Enhancement | SIT | Simple | YES | RDPL | Must Have
MM | Release Strategy Reset with Version Management | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Good Receipt Screen Enhacement for Gate Entry | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Transfer Posting 311Q to Contractor w.r.t. WO | Enhancement | SIT | Complex |  |  | Must Have
MM | Types of WO Advance Tagging | Enhancement | SIT | Simple |  |  | Must Have
MM | WO Advance Approval Workflow | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Bill Inward with Workflow | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Material Reconcilation | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Price Escalation | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Validation on HSN in PO while creating Docket No. in Bill Inward. | Enhancement | SIT | Simple | YES | RDPL | Must Have
MM | PO/WO Intergration with Smart App for DPR | Interface | SIT | Complex |  |  | Must Have
MM | PR Integration with Smart App | Interface | SIT | Complex |  |  | Must Have
MM | Material and Service Procurement Bidding Intergration with Smart App | Interface | SIT | Complex |  |  | Must Have
QM | ASG_QM01 - Inspection Plan Upload | Conversion | Go-Live | Medium
QM | ASG_QM02 - MIC Quantitative | Conversion | Go-Live | Medium | YES | M3M | Must Have
QM | ASG_QM03 - Sampling Procedure | Conversion | Go-Live | Medium
QM | ASG_QM04 - Catalog | Conversion | Go-Live | Medium
QM | ASG_QM04 - If the material was rejected, Mail alert should be triggered to concern person (Store person/ Construction person) | Enhancement | SIT | Complex | YES | Al - Ali | Must Have
QM | ASG_QM05 - Result Record Report - Smartform | Report | SIT | Simple | YES | M3M | Must Have
QM | ASG_QM06 - After GRN - Quality Material Mail alert should be trigger to corcern person ( 2 Mails - Third party vendor / Store peron, Contracter) | Enhancement | SIT | Complex | YES | Indinfravit | Must Have
QM | ASG_QM07 - Result Record Mail Trigger for all the Inspection Lot Number | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Cost Plan reference rate in Work Order/Purchase Order and warning message on higher rate than cost plan rate in purchasing | Enhancement | Post Go-Live | Simple | YES | RDPL
MM | Restricting Goods Receipt against Multiple Purchase order in One GRN Document | Enhancement | SIT | Simple |  |  | Must Have
MM | While Transfer Posting to Contractor Storage, debitable materials (Non-FOC) has to be captured for deductions from RA Bill | Enhancement | SIT | Complex |  |  | Must Have
MM | Quantity Validation for Project Material PR (Doc type ZPPR) | Enhancement | SIT | Simple |  |  | Must Have
MM | Restricting final RA Bill against Work order if any surplus material for the WBS is present in stock | Enhancement | Post Go-Live | Simple |  |  | Must Have
MM | Debit head of one contractor to be tagged to work order of other contractor | Enhancement | Post Go-Live | Complex |  |  | Must Have
MM | Custom Table and Validation on ITC and Non-ITC Tax Code in Purchase order. | Enhancement | SIT | Simple |  |  | Must Have

## ABAP Week Target (hidden)
| ABAP Week Target |  | 2023-09-04 | 2023-09-09
Sr No | Module | Development Description | Scope | FRICE Category | Priority | Priority | Complexity | Functional Consultant | Planned Approval | RGS Status | Planned Date | Actual Date | FS Status | Actual ABAP Consultant | Planned Start | Planned Finish | Actual Start | Actual Finish | Development Status
#NAME?

## ABAP Target (hidden)
[8 empty] | AS On: | 2024-08-02
This Week Plan
Sr. No. | ABAP Resource | User ID | Module | Object No | Development Description | FRICE-W | Functional | Planned |  | Actual |  |  | Status | Remarks
[8 empty] | Start Date | Finish Date | Start Date | Finish Date | Delay
1 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[16 empty] | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
#NAME?
2 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
3 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
#NAME?
4 | [13 empty] | FIORI issues rasied with BASIS & FIORI Consultant. | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
5 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
6 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?