## Project Plan (2)
WBS | Task Name | Duration |  | Start | Start | Finish | Finish | Predecessors | Responsibility | Status | Milestones | Milestones
1 | SAP Implementation at ASHWIN SHETH GROUP | 140 | days | Mon | 2024-01-22 | Wed | 2024-07-17
1.2.1 | Wave 2: Dashboard Power BI | 121 | days | Wed | 2024-03-20 | Mon | 2024-08-19
1.2.1.1 | SAP Dashboard | 121 | days | Wed | 2024-03-20 | Mon | 2024-08-19
1.2.1.1.1 | Explore | 114 | days | Wed | 2024-03-20 | Fri | 2024-08-09
1.2.1.1.2 | Requirement gathering | 80 | days | Wed | 2024-03-20 | Fri | 2024-06-28 | 64 | HBT | Completed
1.2.1.1.3 | Prepare Blue print/prototype of dashboards | 4 | days | Thu | 2024-08-01 | Mon | 2024-08-05 | 170 | HBT | WIP
1.2.1.1.4 | Submit & Review final Blue print/prototype of dashboard | 3 | day | Thu | 2024-08-06 | Thu | 2024-08-08 | 173 | HBT/ASG | Not Started
1.2.1.1.5 | Approval & signoff by ASG | 1 | day | Fri | 2024-08-09 | Fri | 2024-08-09 | 174 | ASG | Not Started | On Kick off & On Completion of Explore phase | 20% & 25%
1.2.1.2 | Realize | 30 | days | Tue | 2024-07-09 | Thu | 2024-08-15 |  |  | Not Started
1.2.1.2.1 | Install DBC Connector | 8 | days | Wed | 2024-07-31 | Sat | 2024-08-10 | 177 | HBT | Not Started
1.2.1.2.2 | Testing of 10 CDS view dashboards | 24 | days | Wed | 2024-07-10 | Sat | 2024-08-10 | 177 | HBT | WIP | On release of 5 dashboards for UAT | 20%
1.2.1.2.3 | UAT sign off 5 CDS view Dashboards | 4 | day | Wed | 2024-08-11 | Wed | 2024-08-14 | 180 | ASG | Not Started
1.2.1.2.4 | Testing of Balance 10 CDS view dashboards | 25 | days | Wed | 2024-07-10 | Sat | 2024-08-10 | 178 | HBT | WIP | On Release of balance 5 dashboards for UAT | 15%
1.2.1.2.5 | Final UAT Signoff of CDS view dashboards | 2 | days | Wed | 2024-08-14 | Thu | 2024-08-15 | 184 | ASG | Not Started | On UAT Sign off | 10%
1.2.1.3 | Deploy | 3 | days | Fri | 2024-08-16 | Mon | 2024-08-19 |  |  | Not Started
1.2.1.3.1 | Production readiness | 1 | day | Fri | 2024-08-16 | Fri | 2024-08-16 | 185 | HBT | Not Started
1.2.1.3.2 | Transport final Customization (Dashboards) | 1 | day | Sat | 2024-08-17 | Sat | 2024-08-17 | 187 | HBT | Not Started | On Completion of Final preparation & Go Live Phase | 5%
1.2.1.4 | GO LIVE
1.2.1.5 | Run | 30 | days | Fri | 2024-08-16 | Mon | 2024-09-16 |  |  | Not Started
1.2.1.5.1 | Post Go live Support | 30 | days | Fri | 2024-08-16 | Fri | 2024-09-16 | 185 | HBT | Not Started | On Completion of Post Go Live Support | 5%

## Project Plan
WBS | Task Name | Duration | Start | Finish | Predecessors | Responsibility
1 | SAP Implementation at ASHWIN SHETH GROUP | 140 days | Mon 22-01-24 | Wed 17-07-24
1.1 | Wave 1: S4 HANA Implementation | 140 days | Mon 22-01-24 | Wed 17-07-24
1.1.1 | Implementation | 140 days | Mon 22-01-24 | Wed 17-07-24
1.1.1.1 | Prepare | 7 days | Mon 22-01-24 | Wed 31-01-24
1.1.1.1.1 | Project Plan | 5 days | Mon 22-01-24 | Mon 29-01-24
1.1.1.1.1.1 | Prepare & submit Initial project plan | 1 day | Mon 22-01-24 | Mon 22-01-24 |  | HBT
1.1.1.1.1.2 | Review project plan | 1 day | Mon 22-01-24 | Mon 22-01-24 | 6FF | ASG
1.1.1.1.1.3 | Submit Revised plan | 1 day | Thu 25-01-24 | Thu 25-01-24 | 7FS+2 days | ASG
1.1.1.1.1.4 | Apporval of project plan by ASG | 1 day | Mon 29-01-24 | Mon 29-01-24 | 8 | ASG
1.1.1.1.2 | Kick Off | 1 day | Tue 23-01-24 | Tue 23-01-24
1.1.1.1.2.1 | Prepare kickoff presentation in consultation with ASG | 1 day | Tue 23-01-24 | Tue 23-01-24 | 7 | HBT
1.1.1.1.2.2 | Review & finalize kickoff presentation | 1 day | Tue 23-01-24 | Tue 23-01-24 | 11FF | ASG
1.1.1.1.2.3 | Project Kick off with Key stakeholders | 1 day | Tue 23-01-24 | Tue 23-01-24 | 12FF | ASG & HBT
1.1.1.1.3 | Training Plan | 3 days | Mon 29-01-24 | Wed 31-01-24
1.1.1.1.3.1 | Prepare & Review Training plan | 1 day | Mon 29-01-24 | Mon 29-01-24 | 8 | ASG & HBT
1.1.1.1.3.2 | Submit Training Plan | 1 day | Tue 30-01-24 | Tue 30-01-24 | 15 | ASG & HBT
1.1.1.1.3.3 | Project preparation phase sign off by ASG | 1 day | Wed 31-01-24 | Wed 31-01-24 | 16 | ASG
1.1.1.1.4 | Deliverables | 5 days | Wed 24-01-24 | Wed 31-01-24
1.1.1.1.4.1 | D: Baseline Project Plan | 1 day | Mon 29-01-24 | Mon 29-01-24 | 9FF | HBT
1.1.1.1.4.2 | D: Project kickoff presentation | 1 day | Wed 24-01-24 | Wed 24-01-24 | 13 | HBT
1.1.1.1.4.3 | D: Training Plan | 1 day | Wed 31-01-24 | Wed 31-01-24 | 16 | HBT
1.1.1.2 | Explore | 53 days | Wed 24-01-24 | Mon 01-04-24
1.1.1.2.1 | Requirement gathering & Conceptual design | 5 days | Wed 24-01-24 | Wed 31-01-24
1.1.1.2.1.1 | Circulation of AS IS Template & Tree | 1 day | Wed 24-01-24 | Wed 24-01-24 | 13 | HBT
1.1.1.2.1.2 | Preparation of AS IS Tree | 1 day | Thu 25-01-24 | Thu 25-01-24 | 24 | ASG
1.1.1.2.1.3 | AS IS discussion & review | 3 days | Mon 29-01-24 | Wed 31-01-24 | 25 | ASG & HBT
1.1.1.2.1.4 | Update AS IS document as per discussion | 3 days | Mon 29-01-24 | Wed 31-01-24 | 26SS | ASG
1.1.1.2.2 | Level 1 training - L1 | 2 days | Thu 01-02-24 | Fri 02-02-24
1.1.1.2.2.1 | Making necessary training preparation and Plan | 1 day | Thu 01-02-24 | Thu 01-02-24 | 21 | HBT
1.1.1.2.2.2 | Conducting level-1 training (SAP Overview) | 1 day | Fri 02-02-24 | Fri 02-02-24 | 29 | HBT
1.1.1.2.3 | Business Process definition | 48 days | Thu 01-02-24 | Mon 01-04-24
1.1.1.2.3.1 | Enterprise structure | 3 days | Thu 01-02-24 | Sat 03-02-24
1.1.1.2.3.1.1 | Define Org structure | 1 day | Thu 01-02-24 | Thu 01-02-24 | 27 | HBT
1.1.1.2.3.1.2 | Review & discuss Org Structure with ASG | 1 day | Thu 01-02-24 | Thu 01-02-24 | 33SS | ASG & HBT
1.1.1.2.3.1.3 | Finalize & submit Org structure | 1 day | Fri 02-02-24 | Fri 02-02-24 | 34 | HBT
1.1.1.2.3.1.4 | Sign off on Org structure by ASG | 1 day | Sat 03-02-24 | Sat 03-02-24 | 35 | ASG
1.1.1.2.3.2 | Business Blueprint | 25 days | Fri 02-02-24 | Mon 04-03-24
1.1.1.2.3.2.1 | Prepare Business blueprint document & KDS | 5 days | Fri 02-02-24 | Wed 07-02-24 | 34 | HBT
1.1.1.2.3.2.2 | Review Gap analysis, propose workaround, identify development list | 2 days | Thu 08-02-24 | Fri 09-02-24 | 38 | HBT
1.1.1.2.3.2.3 | Submit BBP to CTM | 1 day | Mon 12-02-24 | Mon 12-02-24 | 39 | HBT
1.1.1.2.3.2.4 | Review BBP with CTM | 4 days | Mon 12-02-24 | Thu 15-02-24 | 40SS | ASG & HBT
1.1.1.2.3.2.5 | Incorporate changes suggested | 1 day | Fri 16-02-24 | Fri 16-02-24 | 41 | HBT
1.1.1.2.3.2.6 | Third Party Interface discussion Smart Apps, SFDC, Payroll, e-invoice | 4 days | Fri 16-02-24 | Tue 20-02-24 | 41 | ASG & HBT
1.1.1.2.3.2.7 | Submit Integration document | 1 day | Tue 20-02-24 | Tue 20-02-24 | 43FF | ASG & HBT
1.1.1.2.3.2.8 | Submit final BBP | 2 days | Sat 17-02-24 | Mon 19-02-24 | 42 | HBT
1.1.1.2.3.2.9 | BBP solution workshop for Management | 1 day | Sat 02-03-24 | Sat 02-03-24 |  | ASG (Management) & HBT
1.1.1.2.3.2.10 | BBP sign off by ASG | 1 day | Mon 04-03-24 | Mon 04-03-24 | 46 | ASG
1.1.1.2.3.2.11 | Completion of Business Blueprint Phase | 1 day | Mon 04-03-24 | Mon 04-03-24 | 47FF | ASG
1.1.1.2.3.3 | Master Data | 3 days | Tue 20-02-24 | Thu 22-02-24
1.1.1.2.3.3.1 | Identify master data requirement | 1 day | Tue 20-02-24 | Tue 20-02-24 | 45 | HBT
1.1.1.2.3.3.2 | Prepare & explain master data template | 1 day | Wed 21-02-24 | Wed 21-02-24 | 50 | HBT
1.1.1.2.3.3.3 | Circulate master data template | 1 day | Thu 22-02-24 | Thu 22-02-24 | 51 | HBT
1.1.1.2.3.4 | SAP Cloud Server | 8 days | Fri 22-03-24 | Mon 01-04-24
1.1.1.2.3.4.1 | SAP cloud server Availability | 1 day | Fri 22-03-24 | Fri 22-03-24 |  | ASG
1.1.1.2.3.4.2 | SAP Server readiness | 7 days | Mon 25-03-24 | Mon 01-04-24 | 54 | HBT
1.1.1.2.3.5 | Deliverables | 3 days | Wed 06-03-24 | Fri 08-03-24
1.1.1.2.3.5.1 | D: BBP document | 1 day | Wed 06-03-24 | Wed 06-03-24 | 47 | HBT
1.1.1.2.3.5.2 | D: Gap Analysis | 1 day | Wed 06-03-24 | Wed 06-03-24 | 47 | HBT
1.1.1.2.3.5.3 | D: Core team training presentation | 1 day | Wed 06-03-24 | Wed 06-03-24 | 30 | HBT
1.1.1.2.3.5.4 | D: Final WRICEF list | 1 day | Fri 08-03-24 | Fri 08-03-24 | 47 | HBT
1.1.1.2.3.5.5 | D: Initial master data templates | 1 day | Wed 06-03-24 | Wed 06-03-24 | 52FF | HBT
1.1.1.3 | Realize | 66 days | Wed 06-03-24 | Tue 28-05-24
1.1.1.3.1 | Requirement gathering sheet (RGS) | 4 days | Mon 11-03-24 | Thu 14-03-24
1.1.1.3.1.1 | Prepare RGS | 3 days | Mon 11-03-24 | Wed 13-03-24 | 45FS+7 days | HBT
1.1.1.3.1.2 | Submit RGS | 1 day | Thu 14-03-24 | Thu 14-03-24 | 64 | HBT
1.1.1.3.2 | Functional Specifications | 14 days | Fri 15-03-24 | Mon 01-04-24
1.1.1.3.2.1 | Prepare functional specfications | 14 days | Fri 15-03-24 | Mon 01-04-24 | 65 | HBT
1.1.1.3.2.2 | Finalize development tracker | 1 day | Thu 21-03-24 | Thu 21-03-24 | 67FS-2 days | HBT
1.1.1.3.3 | Configure and Validate Baseline | 10 days | Wed 06-03-24 | Mon 18-03-24
1.1.1.3.3.1 | Configure Processes and Functions in Interim Server | 5 days | Wed 06-03-24 | Tue 12-03-24 |  | HBT
1.1.1.3.3.2 | Transfer of Configuration to Dev testing | 1 day | Wed 13-03-24 | Wed 13-03-24 | 70 | HBT
1.1.1.3.3.3 | Unit testing-1 (Consultant) | 3 days | Thu 14-03-24 | Sat 16-03-24 | 71 | HBT
1.1.1.3.3.4 | Document and Resolve Issues | 3 days | Thu 14-03-24 | Sat 16-03-24 | 72SS | HBT
1.1.1.3.3.5 | Submit Unit Testing result & completion of baseline config | 1 day | Mon 18-03-24 | Mon 18-03-24 | 73 | HBT
1.1.1.3.4 | Core team training | 5 days | Mon 18-03-24 | Fri 22-03-24
1.1.1.3.4.1 | Plan for Level-2 training (CTM) | 1 day | Mon 18-03-24 | Mon 18-03-24 | 74SS | HBT
1.1.1.3.4.2 | Making necessery training arrangement - PPT + tutorial | 2 days | Tue 19-03-24 | Wed 20-03-24 | 76 | HBT
1.1.1.3.4.3 | Conducting Level-2 Training (Module wise) | 2 days | Thu 21-03-24 | Fri 22-03-24 | 77 | HBT
1.1.1.3.5 | Interim Server | 10 days | Tue 02-04-24 | Fri 12-04-24
1.1.1.3.5.1 | Copy Configuration to golden master (100) ASG server | 2 days | Tue 02-04-24 | Wed 03-04-24 | 55
1.1.1.3.5.2 | Check and validate Configuration | 1 day | Thu 04-04-24 | Thu 04-04-24 | 80
1.1.1.3.5.3 | Unit testing-1 (Consultant) | 2 days | Fri 05-04-24 | Sat 06-04-24 | 81
1.1.1.3.5.4 | Re-Test Development | 5 days | Mon 08-04-24 | Fri 12-04-24 | 82
1.1.1.3.6 | System Integration Test | 37 days | Tue 02-04-24 | Fri 17-05-24
1.1.1.3.6.1 | Integration test Plan | 3 days | Tue 02-04-24 | Thu 04-04-24
1.1.1.3.6.1.1 | Identify scenerios for Integration test | 3 days | Tue 02-04-24 | Thu 04-04-24 | 66SS+14 days | HBT
1.1.1.3.6.1.2 | Write scripts for Integration test | 2 days | Tue 02-04-24 | Wed 03-04-24 | 86SS | HBT
1.1.1.3.6.2 | User Creation | 6 days | Thu 04-04-24 | Wed 10-04-24
1.1.1.3.6.2.1 | Finalize list of users for Qualtiy enviornment | 3 days | Thu 04-04-24 | Sat 06-04-24 | 87
1.1.1.3.6.2.2 | Provide & Check roles and authorization | 3 days | Mon 08-04-24 | Wed 10-04-24 | 89
1.1.1.3.6.3 | Conduct System integration test | 13 days | Thu 02-05-24 | Fri 17-05-24
1.1.1.3.6.3.1 | Perform Integration testing by Consultant | 5 days | Thu 02-05-24 | Tue 07-05-24 | 100 | HBT
1.1.1.3.6.3.2 | Perform User Acceptance test - CTM | 7 days | Wed 08-05-24 | Thu 16-05-24 | 92 | ASG
1.1.1.3.6.3.3 | Resolving the issues, if any | 5 days | Wed 08-05-24 | Tue 14-05-24 | 93SS | HBT
1.1.1.3.6.3.4 | Retesting of scenarios | 2 days | Wed 15-05-24 | Thu 16-05-24 | 94 | ASG
1.1.1.3.6.3.5 | UAT (by CTM) signoff | 1 day | Fri 17-05-24 | Fri 17-05-24 | 95 | ASG
1.1.1.3.7 | ABAP Development - SIT critical | 42 days | Wed 13-03-24 | Fri 03-05-24
1.1.1.3.7.1 | Develop reports | 25 days | Wed 13-03-24 | Thu 11-04-24 | 70 | HBT
1.1.1.3.7.2 | Testing by consultant | 25 days | Fri 29-03-24 | Mon 29-04-24 | 98SS+13 days | HBT
1.1.1.3.7.3 | Testing by CTM | 7 days | Tue 23-04-24 | Wed 01-05-24 | 99FS-5 days | ASG
1.1.1.3.7.4 | Sign off Development | 2 days | Thu 02-05-24 | Fri 03-05-24 | 100 | ASG
1.1.1.3.8 | Third Party Interface | 42 days | Fri 05-04-24 | Tue 28-05-24
1.1.1.3.8.1 | Smart Apps, SFDC, DMS, E-Invoice | 25 days | Fri 05-04-24 | Mon 06-05-24 | 86 | HBT
1.1.1.3.8.2 | Testing by consultant | 25 days | Mon 22-04-24 | Wed 22-05-24 | 103SS+13 days | HBT
1.1.1.3.8.3 | Testing by CTM | 7 days | Fri 17-05-24 | Fri 24-05-24 | 104FS-5 days | ASG
1.1.1.3.8.4 | Sign off Development | 2 days | Mon 27-05-24 | Tue 28-05-24 | 105 | ASG
1.1.1.3.9 | Cutover Strategy | 3 days | Mon 08-04-24 | Wed 10-04-24
1.1.1.3.9.1 | Discussion on cutover strategy | 2 days | Mon 08-04-24 | Tue 09-04-24 | 89 | ASG & HBT
1.1.1.3.9.2 | Cutover & data responsibility Plan | 1 day | Wed 10-04-24 | Wed 10-04-24 | 108 | ASG & HBT
1.1.1.3.9.3 | Communication to Organisation for Cutover | 1 day | Wed 10-04-24 | Wed 10-04-24 | 109FF | ASG
1.1.1.3.10 | End user training plan | 8 days | Sat 18-05-24 | Tue 28-05-24
1.1.1.3.10.1 | Preparation of End User training plan | 2 days | Sat 18-05-24 | Mon 20-05-24 | 96 | ASG & HBT
1.1.1.3.10.2 | Communicate plan to ASG | 1 day | Mon 20-05-24 | Mon 20-05-24 | 112FF | ASG
1.1.1.3.10.3 | Completion of Realization Phase | 1 day | Tue 28-05-24 | Tue 28-05-24 | 101FF,106FF | ASG
1.1.1.3.11 | Deliverables | 49 days | Mon 18-03-24 | Fri 17-05-24
1.1.1.3.11.1 | D: Test scripts | 1 day | Thu 04-04-24 | Thu 04-04-24 | 87 | HBT
1.1.1.3.11.2 | D: Unit test result document | 1 day | Mon 18-03-24 | Mon 18-03-24 | 72 | HBT
1.1.1.3.11.3 | D: Integration testing document | 1 day | Wed 08-05-24 | Wed 08-05-24 | 92 | HBT
1.1.1.3.11.4 | D: User Acceptance testing document | 1 day | Fri 17-05-24 | Fri 17-05-24 | 96FF | HBT
1.1.1.3.11.5 | D: Final master data templates | 1 day | Wed 10-04-24 | Wed 10-04-24 | 110FF | HBT
1.1.1.3.11.6 | D: Data migration strategy document | 1 day | Wed 10-04-24 | Wed 10-04-24 | 110FF | HBT
1.1.1.4 | Deploy | 60 days | Tue 02-04-24 | Sat 15-06-24
1.1.1.4.1 | Coordinate ABAP Development Pre Go Live | 43 days | Fri 12-04-24 | Wed 05-06-24
1.1.1.4.1.1 | Develop reports | 30 days | Fri 12-04-24 | Mon 20-05-24 | 98 | HBT
1.1.1.4.1.2 | Testing by consultant | 30 days | Wed 17-04-24 | Thu 23-05-24 | 124SS+3 days | HBT
1.1.1.4.1.3 | Testing by CTM | 15 days | Thu 16-05-24 | Mon 03-06-24 | 125FS-7 days | ASG
1.1.1.4.1.4 | Sign off Development | 2 days | Tue 04-06-24 | Wed 05-06-24 | 126 | ASG
1.1.1.4.2 | End User Training | 6 days | Tue 21-05-24 | Tue 28-05-24
1.1.1.4.2.1 | Prepare end user training manual | 1 day | Tue 21-05-24 | Tue 21-05-24 | 112 | HBT
1.1.1.4.2.2 | Conduct end user training | 4 days | Wed 22-05-24 | Mon 27-05-24 | 129 | ASG
1.1.1.4.2.3 | Conduct training to HODs/Management | 1 day | Tue 28-05-24 | Tue 28-05-24 | 130 | ASG
1.1.1.4.3 | Production Environment Preparation | 5 days | Sat 18-05-24 | Thu 23-05-24
1.1.1.4.3.1 | Transport final configurations | 1 day | Sat 18-05-24 | Sat 18-05-24 | 96 | HBT
1.1.1.4.3.2 | Maintain number ranges | 2 days | Mon 20-05-24 | Tue 21-05-24 | 133 | HBT
1.1.1.4.3.3 | Maintain client specific data | 2 days | Wed 22-05-24 | Thu 23-05-24 | 134 | HBT
1.1.1.4.4 | User creation | 7 days | Sat 18-05-24 | Mon 27-05-24
1.1.1.4.4.1 | Finalize list of users for production enviornment | 2 days | Sat 18-05-24 | Mon 20-05-24 | 113FF | ASG & HBT
1.1.1.4.4.2 | Finalise Authorization Matrix | 2 days | Tue 21-05-24 | Wed 22-05-24 | 137 | ASG & HBT
1.1.1.4.4.3 | Check roles and authorization | 3 days | Thu 23-05-24 | Mon 27-05-24 | 138 | ASG & HBT
1.1.1.4.5 | Data preparation and upload | 60 days | Tue 02-04-24 | Sat 15-06-24
1.1.1.4.5.1 | Receipt of master data | 45 days | Tue 02-04-24 | Tue 28-05-24 | 52FS+30 days | ASG
1.1.1.4.5.2 | Validate & cleanse master data | 2 days | Wed 29-05-24 | Thu 30-05-24 | 141 | ASG
1.1.1.4.5.3 | Upload master data in Production | 5 days | Fri 31-05-24 | Wed 05-06-24 | 142 | ASG & HBT
1.1.1.4.5.4 | Confirm uploaded master data | 1 day | Thu 06-06-24 | Thu 06-06-24 | 143 | ASG
1.1.1.4.5.5 | Receipt of cutover data | 10 days | Mon 20-05-24 | Fri 31-05-24 | 130FS-6 days | ASG
1.1.1.4.5.6 | Validate & cleanse cutover data | 3 days | Thu 06-06-24 | Mon 10-06-24 | 127 | ASG
1.1.1.4.5.7 | Upload cutover data in production | 4 days | Tue 11-06-24 | Fri 14-06-24 | 146 | ASG & HBT
1.1.1.4.5.8 | Check and validate uploaded data | 1 day | Sat 15-06-24 | Sat 15-06-24 | 147 | ASG
1.1.1.4.5.9 | Black Out Period | 12 days | Sat 01-06-24 | Sat 15-06-24 | 145
1.1.1.4.6 | Deliverables | 14 days | Tue 21-05-24 | Thu 06-06-24
1.1.1.4.6.1 | D: End user training manual | 1 day | Wed 22-05-24 | Wed 22-05-24 | 129 | HBT
1.1.1.4.6.2 | D: Data migration plan & checklist | 1 day | Wed 29-05-24 | Wed 29-05-24 | 141 | HBT
1.1.1.4.6.3 | D: Master data upload programs | 1 day | Thu 06-06-24 | Thu 06-06-24 | 143 | HBT
1.1.1.4.6.4 | D: Sample data upload validation | 1 day | Thu 06-06-24 | Thu 06-06-24 | 143 | HBT
1.1.1.4.6.5 | D: Final SAP Authorization matrix | 1 day | Tue 21-05-24 | Tue 21-05-24 | 137 | HBT
1.1.1.4.7 | Obtain Approval & phase Sign Off | 1 day | Sat 15-06-24 | Sat 15-06-24
1.1.1.4.7.1 | Deploy signoff | 1 day | Sat 15-06-24 | Sat 15-06-24 | 149FF | ASG
1.1.1.4.7.2 | Completion of Final Preparation (Deploy) Phase | 1 day | Sat 15-06-24 | Sat 15-06-24 | 157FF | ASG
1.1.1.5 | Go Live | 1 day | Mon 17-06-24 | Mon 17-06-24 | 157 | ASG & HBT
1.1.1.6 | Run | 24 days | Tue 18-06-24 | Wed 17-07-24
1.1.1.6.1 | Post Go live Stabilization | 24 days | Tue 18-06-24 | Wed 17-07-24 | 159 | ASG & HBT
1.1.1.6.2 | Deliverables | 1 day | Wed 17-07-24 | Wed 17-07-24
1.1.1.6.2.1 | D: Issue list with resolution status | 1 day | Wed 17-07-24 | Wed 17-07-24 | 161FF | HBT
1.1.1.6.2.2 | D: Configuration documents | 1 day | Wed 17-07-24 | Wed 17-07-24 | 161FF | HBT
1.1.1.6.2.3 | D: FS & TS | 1 day | Wed 17-07-24 | Wed 17-07-24 | 161FF | HBT
1.1.1.6.2.4 | D: Core team training document | 1 day | Wed 17-07-24 | Wed 17-07-24 | 161FF | HBT
1.2 | SAP Dashboard | 121 days | Wed 20-03-24 | Mon 19-08-24
| Explore | 114 days | Wed 20-03-24 | Fri 09-08-24
| Requirement gathering | 80 days | Wed 20-03-24 | Fri 28-06-24 | 64 | HBT
| Prepare Blue print/prototype of dashboards | 4 days | Thu 01-08-24 | Mon 05-08-24 | 170 | HBT
| Demonstrate to ASG | 1 day | Tue 06-08-24 | Tue 06-08-24 | 171 | HBT
| Incorporate changes syggested | 1 day | Wed 07-08-24 | Wed 07-08-24 | 172 | HBT
| Submit final dashboard prototypes to ASG | 1 day | Thu 08-08-24 | Thu 08-08-24 | 173 | HBT
| Approval & signoff by ASG | 1 day | Fri 09-08-24 | Fri 09-08-24 | 174 | ASG
| Realize | 30 days | Tue 09-07-24 | Thu 15-08-24
| Design of dashboards | 18 days | Tue 09-07-24 | Wed 31-07-24 | 175FS+10 days | HBT
| Testing of dashboards | 8 days | Wed 10-07-24 | Sat 10-08-24 | 177 | HBT
| Demonstrate dashboards to ASG | 1 day | Mon 12-08-24 | Mon 12-08-24 | 178 | HBT
| Incoporate changes suggested | 1 day | Tue 13-08-24 | Tue 13-08-24 | 179 | ASG
| UAT sign off 5 Dashboards | 1 day | Wed 14-08-24 | Wed 14-08-24 | 180
| Testing of dashboards | 25 days | Wed 10-07-24 | Sat 10-08-24 | 178 | HBT
| Demonstrate dashboards to ASG | 1 day | Mon 12-08-24 | Mon 12-08-24 | 182 | HBT
| Incoporate changes suggested | 1 day | Tue 13-08-24 | Tue 13-08-24 | 183 | ASG
| Final UAT Signoff of 10 dashboards | 2 days | Wed 14-08-24 | Thu 15-08-24 | 184 | ASG
| Deploy | 3 days | Fri 16-08-24 | Mon 19-08-24
| Production readiness | 1 day | Fri 16-08-24 | Fri 16-08-24 | 185 | HBT
| Transport final Customization (Dashboards) | 1 day | Sat 17-08-24 | Sat 17-08-24 | 187 | HBT
| End user training | 1 day | Mon 19-08-24 | Mon 19-08-24 | 188 | HBT

## Project Plan R1 (hidden)
WBS | Task Name | Duration | Start | Finish | Predecessors | Responsibility | Remarks | Level
1 | SAP Implementation at ASHWIN SHETH GROUP | 133 days | Mon 22-01-24 | Mon 08-07-24 |  |  |  | 1
1.1 | Wave 1: S4 HANA Implementation | 133 days | Mon 22-01-24 | Mon 08-07-24 |  |  |  | 2
1.1.1 | Implementation | 133 days | Mon 22-01-24 | Mon 08-07-24 |  |  |  | 3
1.1.1.1 | Prepare | 7 days | Mon 22-01-24 | Wed 31-01-24 |  |  |  | 4
1.1.1.1.1 | Project Plan | 5 days | Mon 22-01-24 | Mon 29-01-24 |  |  |  | 5
1.1.1.1.1.1 | Prepare & submit Initial project plan | 1 day | Mon 22-01-24 | Mon 22-01-24 |  | HBT |  | 6
1.1.1.1.1.2 | Review project plan | 1 day | Mon 22-01-24 | Mon 22-01-24 | 6FF | ASG |  | 6
1.1.1.1.1.3 | Submit Revised plan | 1 day | Thu 25-01-24 | Thu 25-01-24 | 7FS+2 days | ASG |  | 6
1.1.1.1.1.4 | Apporval of project plan by ASG | 1 day | Mon 29-01-24 | Mon 29-01-24 | 8 | ASG |  | 6
1.1.1.1.2 | Kick Off | 1 day | Tue 23-01-24 | Tue 23-01-24 |  |  |  | 5
1.1.1.1.2.1 | Prepare kickoff presentation in consultation with ASG | 1 day | Tue 23-01-24 | Tue 23-01-24 | 7 | HBT |  | 6
1.1.1.1.2.2 | Review & finalize kickoff presentation | 1 day | Tue 23-01-24 | Tue 23-01-24 | 11FF | ASG |  | 6
1.1.1.1.2.3 | Project Kick off with Key stakeholders | 1 day | Tue 23-01-24 | Tue 23-01-24 | 12FF | ASG & HBT |  | 6
1.1.1.1.3 | Training Plan | 3 days | Mon 29-01-24 | Wed 31-01-24 |  |  |  | 5
1.1.1.1.3.1 | Prepare & Review Training plan | 1 day | Mon 29-01-24 | Mon 29-01-24 | 8 | ASG & HBT |  | 6
1.1.1.1.3.2 | Submit Training Plan | 1 day | Tue 30-01-24 | Tue 30-01-24 | 15 | ASG & HBT |  | 6
1.1.1.1.3.3 | Project preparation phase sign off by ASG | 1 day | Wed 31-01-24 | Wed 31-01-24 | 16 | ASG |  | 6
1.1.1.1.4 | Deliverables | 5 days | Wed 24-01-24 | Wed 31-01-24 |  |  |  | 5
1.1.1.1.4.1 | D: Baseline Project Plan | 1 day | Mon 29-01-24 | Mon 29-01-24 | 9FF | HBT |  | 6
1.1.1.1.4.2 | D: Project kickoff presentation | 1 day | Wed 24-01-24 | Wed 24-01-24 | 13 | HBT |  | 6
1.1.1.1.4.3 | D: Training Plan | 1 day | Wed 31-01-24 | Wed 31-01-24 | 16 | HBT |  | 6
1.1.1.2 | Explore | 27 days | Wed 24-01-24 | Wed 28-02-24 |  |  |  | 4
1.1.1.2.1 | Requirement gathering & Conceptual design | 5 days | Wed 24-01-24 | Wed 31-01-24 |  |  |  | 5
1.1.1.2.1.1 | Circulation of AS IS Template & Tree | 1 day | Wed 24-01-24 | Wed 24-01-24 | 13 | HBT |  | 6
1.1.1.2.1.2 | Preparation of AS IS Tree | 1 day | Thu 25-01-24 | Thu 25-01-24 | 24 | ASG |  | 6
1.1.1.2.1.3 | AS IS discussion & review | 3 days | Mon 29-01-24 | Wed 31-01-24 | 25 | ASG & HBT |  | 6
1.1.1.2.1.4 | Update AS IS document as per discussion | 3 days | Mon 29-01-24 | Wed 31-01-24 | 26SS | ASG |  | 6
1.1.1.2.2 | Level 1 training - L1 | 2 days | Thu 01-02-24 | Fri 02-02-24 |  |  |  | 5
1.1.1.2.2.1 | Making necessary training preparation and Plan | 1 day | Thu 01-02-24 | Thu 01-02-24 | 21 | HBT |  | 6
1.1.1.2.2.2 | Conducting level-1 training (SAP Overview) | 1 day | Fri 02-02-24 | Fri 02-02-24 | 29 | HBT |  | 6
1.1.1.2.3 | Business Process definition | 25 days | Mon 29-01-24 | Wed 28-02-24 |  |  |  | 5
1.1.1.2.3.1 | Enterprise structure | 3 days | Thu 01-02-24 | Sat 03-02-24 |  |  |  | 6
1.1.1.2.3.1.1 | Define Org structure | 1 day | Thu 01-02-24 | Thu 01-02-24 | 27 | HBT |  | 7
1.1.1.2.3.1.2 | Review & discuss Org Structure with ASG | 1 day | Thu 01-02-24 | Thu 01-02-24 | 33SS | ASG & HBT |  | 7
1.1.1.2.3.1.3 | Finalize & submit Org structure | 1 day | Fri 02-02-24 | Fri 02-02-24 | 34 | HBT |  | 7
1.1.1.2.3.1.4 | Sign off on Org structure by ASG | 1 day | Sat 03-02-24 | Sat 03-02-24 | 35 | ASG |  | 7
1.1.1.2.3.2 | Business Blueprint | 18 days | Fri 02-02-24 | Fri 23-02-24 |  |  |  | 6
1.1.1.2.3.2.1 | Prepare Business blueprint document & KDS | 5 days | Fri 02-02-24 | Wed 07-02-24 | 34 | HBT |  | 7
1.1.1.2.3.2.2 | Review Gap analysis, propose workaround, identify development list | 2 days | Thu 08-02-24 | Fri 09-02-24 | 38 | HBT |  | 7
1.1.1.2.3.2.3 | Submit BBP to CTM | 1 day | Mon 12-02-24 | Mon 12-02-24 | 39 | HBT |  | 7
1.1.1.2.3.2.4 | Review BBP with CTM | 4 days | Mon 12-02-24 | Thu 15-02-24 | 40SS | ASG & HBT |  | 7
1.1.1.2.3.2.5 | Incorporate changes suggested | 1 day | Fri 16-02-24 | Fri 16-02-24 | 41 | HBT |  | 7
1.1.1.2.3.2.6 | Third Party Interface discussion Smart Apps, SFDC, Payroll, e-invoice | 4 days | Fri 16-02-24 | Tue 20-02-24 | 41 | ASG & HBT |  | 7
1.1.1.2.3.2.7 | Submit Integration document | 1 day | Tue 20-02-24 | Tue 20-02-24 | 43FF | ASG & HBT | Integration Submission by 23rd Feb '23 | 7
1.1.1.2.3.2.8 | Submit final BBP | 2 days | Sat 17-02-24 | Mon 19-02-24 | 42 | HBT |  | 7
1.1.1.2.3.2.9 | BBP solution workshop for Management | 3 days | Tue 20-02-24 | Thu 22-02-24 | 45 | ASG (Management) & HBT | BBP Workshop date to be finalized by ASG. Proposed date 28th / 29th Feb | 7
1.1.1.2.3.2.10 | BBP sign off by ASG | 1 day | Fri 23-02-24 | Fri 23-02-24 | 46 | ASG |  | 8
1.1.1.2.3.2.11 | Completion of Business Blueprint Phase | 1 day | Fri 23-02-24 | Fri 23-02-24 | 47FF | ASG |  | 8
1.1.1.2.3.3 | Master Data | 3 days | Tue 20-02-24 | Thu 22-02-24 |  |  |  | 6
1.1.1.2.3.3.1 | Identify master data requirement | 1 day | Tue 20-02-24 | Tue 20-02-24 | 45 | HBT |  | 7
1.1.1.2.3.3.2 | Prepare & explain master data template | 1 day | Wed 21-02-24 | Wed 21-02-24 | 50 | HBT | Master data explantion by 23rd Feb '23 | 7
1.1.1.2.3.3.3 | Circulate master data template | 1 day | Thu 22-02-24 | Thu 22-02-24 | 51 | HBT | Master data circulation 24th Feb '23 | 7
1.1.1.2.3.4 | SAP Cloud Server | 25 days | Mon 29-01-24 | Wed 28-02-24 |  |  |  | 6
1.1.1.2.3.4.1 | SAP cloud server Availability | 15 days | Mon 29-01-24 | Thu 15-02-24 | 13FS+2 days | ASG |  | 7
1.1.1.2.3.4.2 | SAP Server readiness | 10 days | Fri 16-02-24 | Wed 28-02-24 | 54 | HBT |  | 7
1.1.1.2.3.5 | Deliverables | 18 days | Sat 03-02-24 | Mon 26-02-24 |  |  |  | 6
1.1.1.2.3.5.1 | D: BBP document | 1 day | Mon 26-02-24 | Mon 26-02-24 | 47 | HBT |  | 7
1.1.1.2.3.5.2 | D: Gap Analysis | 1 day | Mon 26-02-24 | Mon 26-02-24 | 47 | HBT |  | 7
1.1.1.2.3.5.3 | D: Core team training presentation | 1 day | Sat 03-02-24 | Sat 03-02-24 | 30 | HBT |  | 7
1.1.1.2.3.5.4 | D: Final WRICEF list | 1 day | Mon 26-02-24 | Mon 26-02-24 | 47 | HBT |  | 7
1.1.1.2.3.5.5 | D: Initial master data templates | 1 day | Thu 22-02-24 | Thu 22-02-24 | 52FF | HBT |  | 7
1.1.1.3 | Realize | 59 days | Tue 20-02-24 | Fri 03-05-24 |  |  |  | 4
1.1.1.3.1 | Requirement gathering sheet (RGS) | 4 days | Tue 20-02-24 | Fri 23-02-24 |  |  |  | 5
1.1.1.3.1.1 | Prepare RGS | 2 days | Tue 20-02-24 | Wed 21-02-24 | 45 | HBT | RGS preparation and submission by 02nd Mar '23 | 6
1.1.1.3.1.2 | Submit RGS | 2 days | Thu 22-02-24 | Fri 23-02-24 | 64 | HBT |  | 6
1.1.1.3.2 | Functional Specifications | 6 days | Mon 26-02-24 | Sat 02-03-24 |  |  |  | 5
1.1.1.3.2.1 | Prepare functional specfications | 5 days | Mon 26-02-24 | Fri 01-03-24 | 65 | HBT | FS of SIT/Go live critical objects to be prepared by 09th Mar '23 | 6
1.1.1.3.2.2 | Finalize development tracker | 3 days | Thu 29-02-24 | Sat 02-03-24 | 67FS-2 days | HBT | Development tracker preparation by 02nd Mar '23 | 6
1.1.1.3.3 | Configure and Validate Baseline | 10 days | Fri 01-03-24 | Wed 13-03-24 |  |  |  | 5
1.1.1.3.3.1 | Configure Processes and Functions in golden master (100) | 5 days | Fri 01-03-24 | Wed 06-03-24 | 55FS+1 day | HBT |  | 6
1.1.1.3.3.2 | Transfer of Configuration to Dev testing | 1 day | Thu 07-03-24 | Thu 07-03-24 | 70 | HBT |  | 6
1.1.1.3.3.3 | Unit testing-1 (Consultant) | 3 days | Fri 08-03-24 | Tue 12-03-24 | 71 | HBT |  | 6
1.1.1.3.3.4 | Document and Resolve Issues | 3 days | Fri 08-03-24 | Tue 12-03-24 | 72SS | HBT |  | 6
1.1.1.3.3.5 | Submit Unit Testing result & completion of baseline config | 1 day | Wed 13-03-24 | Wed 13-03-24 | 73 | HBT |  | 6
1.1.1.3.4 | Core team training & UT | 5 days | Wed 13-03-24 | Mon 18-03-24 |  |  |  | 5
1.1.1.3.4.1 | Plan for Level-2 training (CTM) | 1 day | Wed 13-03-24 | Wed 13-03-24 | 74SS | HBT |  | 6
1.1.1.3.4.2 | Making necessery training arrangement - PPT + tutorial | 2 days | Thu 14-03-24 | Fri 15-03-24 | 76 | HBT |  | 6
1.1.1.3.4.3 | Conducting Level-2 Training (Module wise) | 2 days | Sat 16-03-24 | Mon 18-03-24 | 77 | HBT |  | 6
1.1.1.3.5 | System Integration Test | 38 days | Thu 14-03-24 | Tue 30-04-24 |  |  |  | 5
1.1.1.3.5.1 | Integration test Plan | 2 days | Thu 14-03-24 | Fri 15-03-24 |  |  |  | 6
1.1.1.3.5.1.1 | Identify scenerios for Integration test | 1 day | Thu 14-03-24 | Thu 14-03-24 | 74 | HBT | Scenarios listing for UT/SIT/UAT by 14th Mar '23 | 7
1.1.1.3.5.1.2 | Write scripts for Integration test | 2 days | Thu 14-03-24 | Fri 15-03-24 | 81SS | HBT |  | 7
1.1.1.3.5.2 | User Creation | 8 days | Wed 10-04-24 | Fri 19-04-24 |  |  |  | 6
1.1.1.3.5.2.1 | Finalize list of users for Qualtiy enviornment | 5 days | Wed 10-04-24 | Tue 16-04-24 | 82FS+20 days |  | Users list for Roles and Authorization to be finlaized by 18th Mar '23 | 7
1.1.1.3.5.2.2 | Provide & Check roles and authorization | 3 days | Wed 17-04-24 | Fri 19-04-24 | 84 |  |  | 7
1.1.1.3.5.3 | Conduct System integration test | 13 days | Mon 15-04-24 | Tue 30-04-24 |  |  |  | 6
1.1.1.3.5.3.1 | Perform Integration testing by Consultant | 5 days | Mon 15-04-24 | Fri 19-04-24 | 95 | HBT |  | 7
1.1.1.3.5.3.2 | Perform User Acceptance test - CTM | 7 days | Sat 20-04-24 | Mon 29-04-24 | 87 | ASG |  | 7
1.1.1.3.5.3.3 | Resolving the issues, if any | 5 days | Sat 20-04-24 | Thu 25-04-24 | 88SS | HBT |  | 7
1.1.1.3.5.3.4 | Retesting of scenarios | 2 days | Fri 26-04-24 | Mon 29-04-24 | 89 | ASG |  | 7
1.1.1.3.5.3.5 | UAT (by CTM) signoff | 1 day | Tue 30-04-24 | Tue 30-04-24 | 90 | ASG |  | 7
1.1.1.3.6 | ABAP Development - SIT critical | 32 days | Thu 07-03-24 | Tue 16-04-24 |  |  |  | 5
1.1.1.3.6.1 | Develop reports | 25 days | Thu 07-03-24 | Sat 06-04-24 | 70 | HBT |  | 6
1.1.1.3.6.2 | Testing by consultant | 25 days | Tue 12-03-24 | Wed 10-04-24 | 93SS+3 days | HBT |  | 6
1.1.1.3.6.3 | Testing by CTM | 7 days | Fri 05-04-24 | Fri 12-04-24 | 94FS-5 days | ASG |  | 6
1.1.1.3.6.4 | Sign off Development | 2 days | Mon 15-04-24 | Tue 16-04-24 | 95 | ASG |  | 6
1.1.1.3.7 | Third Party Interface | 32 days | Thu 07-03-24 | Tue 16-04-24 |  |  |  | 5
1.1.1.3.7.1 | Smart Apps, SFDC, DMS, E-Invoice | 25 days | Thu 07-03-24 | Sat 06-04-24 | 70 | HBT |  | 6
1.1.1.3.7.2 | Testing by consultant | 25 days | Tue 12-03-24 | Wed 10-04-24 | 98SS+3 days | HBT |  | 6
1.1.1.3.7.3 | Testing by CTM | 7 days | Fri 05-04-24 | Fri 12-04-24 | 99FS-5 days | ASG |  | 6
1.1.1.3.7.4 | Sign off Development | 2 days | Mon 15-04-24 | Tue 16-04-24 | 100 | ASG |  | 6
1.1.1.3.8 | Cutover Strategy | 3 days | Wed 01-05-24 | Fri 03-05-24 |  |  |  | 5
1.1.1.3.8.1 | Discussion on cutover strategy | 2 days | Wed 01-05-24 | Thu 02-05-24 | 91 | ASG & HBT |  | 6
1.1.1.3.8.2 | Cutover & data responsibility Plan | 1 day | Fri 03-05-24 | Fri 03-05-24 | 103 | ASG & HBT |  | 6
1.1.1.3.8.3 | Communication to Organisation for Cutover | 1 day | Fri 03-05-24 | Fri 03-05-24 | 104FF | ASG |  | 6
1.1.1.3.9 | End user training plan | 14 days | Tue 16-04-24 | Thu 02-05-24 |  |  |  | 5
1.1.1.3.9.1 | Preparation of End User training plan | 2 days | Wed 01-05-24 | Thu 02-05-24 | 91 | ASG & HBT |  | 6
1.1.1.3.9.2 | Communicate plan to ASG | 1 day | Thu 02-05-24 | Thu 02-05-24 | 107FF | ASG |  | 6
1.1.1.3.9.3 | Completion of Realization Phase | 1 day | Tue 16-04-24 | Tue 16-04-24 | 96FF,101FF | ASG |  | 6
1.1.1.3.10 | Deliverables | 42 days | Wed 13-03-24 | Fri 03-05-24 |  |  |  | 5
1.1.1.3.10.1 | D: Test scripts | 1 day | Sat 16-03-24 | Sat 16-03-24 | 82 | HBT |  | 7
1.1.1.3.10.2 | D: Unit test result document | 1 day | Wed 13-03-24 | Wed 13-03-24 | 72 | HBT |  | 7
1.1.1.3.10.3 | D: Integration testing document | 1 day | Sat 20-04-24 | Sat 20-04-24 | 87 | HBT |  | 7
1.1.1.3.10.4 | D: User Acceptance testing document | 1 day | Tue 30-04-24 | Tue 30-04-24 | 91FF | HBT |  | 7
1.1.1.3.10.5 | D: Final master data templates | 1 day | Fri 03-05-24 | Fri 03-05-24 | 105FF | HBT |  | 7
1.1.1.3.10.6 | D: Data migration strategy document | 1 day | Fri 03-05-24 | Fri 03-05-24 | 105FF | HBT |  | 7
1.1.1.4 | Deploy | 68 days | Thu 14-03-24 | Thu 06-06-24 |  |  |  | 4
1.1.1.4.1 | Coordinate ABAP Development Pre Go Live | 43 days | Mon 08-04-24 | Fri 31-05-24 |  |  |  | 5
1.1.1.4.1.1 | Develop reports | 30 days | Mon 08-04-24 | Wed 15-05-24 | 93,98 | HBT |  | 6
1.1.1.4.1.2 | Testing by consultant | 30 days | Thu 11-04-24 | Sat 18-05-24 | 119SS+3 days | HBT |  | 6
1.1.1.4.1.3 | Testing by CTM | 15 days | Fri 10-05-24 | Wed 29-05-24 | 120FS-7 days | ASG |  | 6
1.1.1.4.1.4 | Sign off Development | 2 days | Thu 30-05-24 | Fri 31-05-24 | 121 | ASG |  | 6
1.1.1.4.2 | End User Training | 6 days | Fri 03-05-24 | Thu 09-05-24 |  |  |  | 5
1.1.1.4.2.1 | Prepare end user training manual | 1 day | Fri 03-05-24 | Fri 03-05-24 | 107 | HBT |  | 6
1.1.1.4.2.2 | Conduct end user training | 4 days | Sat 04-05-24 | Wed 08-05-24 | 124 | ASG |  | 6
1.1.1.4.2.3 | Conduct training to HODs/Management | 1 day | Thu 09-05-24 | Thu 09-05-24 | 125 | ASG |  | 6
1.1.1.4.3 | Production Environment Preparation | 5 days | Wed 01-05-24 | Mon 06-05-24 |  |  |  | 5
1.1.1.4.3.1 | Transport final configurations | 1 day | Wed 01-05-24 | Wed 01-05-24 | 91 | HBT |  | 6
1.1.1.4.3.2 | Maintain number ranges | 2 days | Thu 02-05-24 | Fri 03-05-24 | 128 | HBT |  | 6
1.1.1.4.3.3 | Maintain client specific data | 2 days | Sat 04-05-24 | Mon 06-05-24 | 129 | HBT |  | 6
1.1.1.4.4 | User creation | 7 days | Wed 01-05-24 | Wed 08-05-24 |  |  |  | 5
1.1.1.4.4.1 | Finalize list of users for production enviornment | 2 days | Wed 01-05-24 | Thu 02-05-24 | 108FF | ASG & HBT |  | 6
1.1.1.4.4.2 | Finalise Authorization Matrix | 2 days | Fri 03-05-24 | Sat 04-05-24 | 132 | ASG & HBT | Authorization Matrix finalization by 23rd Mar '23 | 6
1.1.1.4.4.3 | Check roles and authorization | 3 days | Mon 06-05-24 | Wed 08-05-24 | 133 | ASG & HBT |  | 6
1.1.1.4.5 | Data preparation and upload | 68 days | Thu 14-03-24 | Thu 06-06-24 |  |  |  | 5
1.1.1.4.5.1 | Receipt of master data | 60 days | Thu 14-03-24 | Tue 28-05-24 | 52FS+15 days | ASG |  | 6
1.1.1.4.5.2 | Validate & cleanse master data | 2 days | Wed 29-05-24 | Thu 30-05-24 | 136 | ASG |  | 6
1.1.1.4.5.3 | Upload master data in Production | 5 days | Fri 31-05-24 | Wed 05-06-24 | 137 | ASG & HBT |  | 6
1.1.1.4.5.4 | Confirm uploaded master data | 1 day | Thu 06-06-24 | Thu 06-06-24 | 138 | ASG |  | 6
1.1.1.4.5.5 | Receipt of cutover data | 10 days | Mon 20-05-24 | Fri 31-05-24 | 105SS+13 days | ASG |  | 6
1.1.1.4.5.6 | Validate & cleanse cutover data | 3 days | Wed 29-05-24 | Fri 31-05-24 | 140FF | ASG |  | 6
1.1.1.4.5.7 | Upload cutover data in production | 4 days | Sat 01-06-24 | Wed 05-06-24 | 140 | ASG & HBT |  | 6
1.1.1.4.5.8 | Check and validate uploaded data | 1 day | Thu 06-06-24 | Thu 06-06-24 | 142 | ASG |  | 6
1.1.1.4.5.9 | Black Out Period | 7 days | Thu 30-05-24 | Thu 06-06-24 | 141FS-2 days |  |  | 6
1.1.1.4.6 | Deliverables | 28 days | Fri 03-05-24 | Thu 06-06-24 |  |  |  | 5
1.1.1.4.6.1 | D: End user training manual | 1 day | Sat 04-05-24 | Sat 04-05-24 | 124 | HBT |  | 6
1.1.1.4.6.2 | D: Data migration plan & checklist | 1 day | Wed 29-05-24 | Wed 29-05-24 | 136 | HBT |  | 6
1.1.1.4.6.3 | D: Master data upload programs | 1 day | Thu 06-06-24 | Thu 06-06-24 | 138 | HBT |  | 6
1.1.1.4.6.4 | D: Sample data upload validation | 1 day | Thu 06-06-24 | Thu 06-06-24 | 138 | HBT |  | 6
1.1.1.4.6.5 | D: Final SAP Authorization matrix | 1 day | Fri 03-05-24 | Fri 03-05-24 | 132 | HBT |  | 6
1.1.1.4.7 | Obtain Approval & phase Sign Off | 1 day | Thu 06-06-24 | Thu 06-06-24 |  |  |  | 5
1.1.1.4.7.1 | Deploy signoff | 1 day | Thu 06-06-24 | Thu 06-06-24 | 144FF | ASG |  | 6
1.1.1.4.7.2 | Completion of Final Preparation (Deploy) Phase | 1 day | Thu 06-06-24 | Thu 06-06-24 | 152FF | ASG |  | 6
1.1.1.5 | Go Live | 1 day | Fri 07-06-24 | Fri 07-06-24 | 152 | ASG & HBT |  | 4
1.1.1.6 | Run | 24 days | Mon 10-06-24 | Mon 08-07-24 |  |  |  | 4
1.1.1.6.1 | Post Go live Stabilization | 24 days | Mon 10-06-24 | Mon 08-07-24 | 154 | ASG & HBT |  | 5
1.1.1.6.2 | Deliverables | 1 day | Mon 08-07-24 | Mon 08-07-24 |  |  |  | 5
1.1.1.6.2.1 | D: Issue list with resolution status | 1 day | Mon 08-07-24 | Mon 08-07-24 | 156FF | HBT |  | 6
1.1.1.6.2.2 | D: Configuration documents | 1 day | Mon 08-07-24 | Mon 08-07-24 | 156FF | HBT |  | 6
1.1.1.6.2.3 | D: FS & TS | 1 day | Mon 08-07-24 | Mon 08-07-24 | 156FF | HBT |  | 6
1.1.1.6.2.4 | D: Core team training document | 1 day | Mon 08-07-24 | Mon 08-07-24 | 156FF | HBT |  | 6
1.2 | Wave 2: Dashboard Power BI | 126 days | Thu 01-02-24 | Mon 08-07-24
1.2.1 | SAP Dshboard | 126 days | Thu 01-02-24 | Mon 08-07-24
1.2.1.1 | Explore | 21 days | Thu 01-02-24 | Tue 27-02-24
1.2.1.1.1 | Requirement gathering | 10 days | Thu 01-02-24 | Tue 13-02-24 | 27 | HBT
1.2.1.1.2 | Prepare prototype of dashboards | 5 days | Wed 14-02-24 | Mon 19-02-24 | 165 | HBT
1.2.1.1.3 | Demonstrate to ASG | 2 days | Tue 20-02-24 | Wed 21-02-24 | 166 | HBT
1.2.1.1.4 | Incorporate changes syggested | 2 days | Thu 22-02-24 | Fri 23-02-24 | 167 | HBT
1.2.1.1.5 | Submit final dashboard prototypes to ASG | 1 day | Mon 26-02-24 | Mon 26-02-24 | 168 | HBT
1.2.1.1.6 | Approval & signoff by ASG | 1 day | Tue 27-02-24 | Tue 27-02-24 | 169 | ASG
1.2.1.2 | Realize | 56 days | Wed 28-02-24 | Tue 07-05-24
1.2.1.2.1 | Design of dashboards | 15 days | Wed 28-02-24 | Sat 16-03-24 | 170 | HBT
1.2.1.2.2 | Testing of dashboards | 15 days | Mon 18-03-24 | Thu 04-04-24 | 172 | HBT
1.2.1.2.3 | Demonstrate dashboards to ASG | 2 days | Fri 05-04-24 | Sat 06-04-24 | 173 | HBT
1.2.1.2.4 | Incoporate changes suggested | 7 days | Mon 08-04-24 | Tue 16-04-24 | 174 | ASG
1.2.1.2.5 | UAT sign off 5 Dashboards | 1 day | Wed 17-04-24 | Wed 17-04-24 | 175
1.2.1.2.6 | Testing of dashboards | 15 days | Fri 05-04-24 | Tue 23-04-24 | 173 | HBT
1.2.1.2.7 | Demonstrate dashboards to ASG | 2 days | Wed 24-04-24 | Thu 25-04-24 | 177 | HBT
1.2.1.2.8 | Incoporate changes suggested | 7 days | Fri 26-04-24 | Sat 04-05-24 | 178 | ASG
1.2.1.2.9 | Final UAT Signoff of 10 dashboards | 2 days | Mon 06-05-24 | Tue 07-05-24 | 179 | ASG
1.2.1.3 | Deploy | 7 days | Wed 08-05-24 | Thu 16-05-24
1.2.1.3.1 | Production readiness | 3 days | Wed 08-05-24 | Fri 10-05-24 | 180 | HBT
1.2.1.3.2 | Transport final Customization (Dashboards) | 1 day | Mon 13-05-24 | Mon 13-05-24 | 182 | HBT
1.2.1.3.3 | End user training | 3 days | Tue 14-05-24 | Thu 16-05-24 | 183 | HBT
1.2.1.4 | Go Live | 1 day | Fri 07-06-24 | Fri 07-06-24 | 154SS | ASG & HBT
1.2.1.5 | Run | 24 days | Mon 10-06-24 | Mon 08-07-24 | 185 | HBT
1.2.1.5.1 | Post Go live stabilization | 24 days | Mon 10-06-24 | Mon 08-07-24

## Sheet1
WBS | Task Name | Duration | Start | Finish | Responsibility | Remarks | Level
1 | SAP Implementation at ASHWIN SHETH GROUP | 133 days | Mon 22-01-24 | Mon 08-07-24 |  |  | 1
1.1 | Wave 1: S4 HANA Implementation | 133 days | Mon 22-01-24 | Mon 08-07-24 |  |  | 2
1.1.1 | Implementation | 133 days | Mon 22-01-24 | Mon 08-07-24 |  |  | 3
1.1.1.1 | Prepare | 7 days | Mon 22-01-24 | Wed 31-01-24 |  |  | 4
1.1.1.2 | Explore | 27 days | Wed 24-01-24 | Wed 28-02-24 |  |  | 4
1.1.1.2.3.2.7 | Submit Integration document | 1 day | Tue 20-02-24 | Tue 20-02-24 | ASG & HBT | Integration Submission by 23rd Feb '24 | 7
1.1.1.2.3.2.9 | BBP solution workshop for Management | 3 days | Tue 20-02-24 | Thu 22-02-24 | ASG (Management) & HBT | BBP Workshop date to be finalized by ASG. Proposed date 28th / 29th Feb '24 | 7
1.1.1.2.3.3.1 | Identify master data requirement | 1 day | Tue 20-02-24 | Tue 20-02-24 | HBT |  | 7
1.1.1.2.3.3.2 | Prepare & explain master data template | 1 day | Wed 21-02-24 | Wed 21-02-24 | HBT | Master data explantion by 23rd Feb '24 | 7
1.1.1.2.3.3.3 | Circulate master data template | 1 day | Thu 22-02-24 | Thu 22-02-24 | HBT | Master data circulation 24th Feb '24 | 7
1.1.1.3 | Realize | 59 days | Tue 20-02-24 | Fri 03-05-24 |  |  | 4
1.1.1.3.1.1 | Prepare RGS | 2 days | Tue 20-02-24 | Wed 21-02-24 | HBT | RGS preparation and submission by 02nd Mar '24 | 6
1.1.1.3.1.2 | Submit RGS | 2 days | Thu 22-02-24 | Fri 23-02-24 | HBT | RGS preparation and submission by 02nd Mar '24 | 6
1.1.1.3.2.1 | Prepare functional specfications | 5 days | Mon 26-02-24 | Fri 01-03-24 | HBT | FS of SIT/Go live critical objects to be prepared by 09th Mar '24 | 6
1.1.1.3.2.2 | Finalize development tracker | 3 days | Thu 29-02-24 | Sat 02-03-24 | HBT | Development tracker preparation by 02nd Mar '24 | 6
1.1.1.3.5.1.1 | Identify scenerios for Integration test | 1 day | Thu 14-03-24 | Thu 14-03-24 | HBT | Scenarios listing for UT/SIT/UAT by 14th Mar '24 | 7
1.1.1.3.5.2.1 | Finalize list of users for Qualtiy enviornment | 5 days | Wed 10-04-24 | Tue 16-04-24 |  | Users list for Roles and Authorization to be finlaized by 18th Mar '24 | 7
1.1.1.4 | Deploy | 68 days | Thu 14-03-24 | Thu 06-06-24 |  |  | 4
1.1.1.4.4.2 | Finalise Authorization Matrix | 2 days | Fri 03-05-24 | Sat 04-05-24 | ASG & HBT | Authorization Matrix finalization by 23rd Mar '24 | 6
1.2 | Wave 2: Dashboard Power BI | 126 days | Thu 01-02-24 | Mon 08-07-24
1.2.1 | SAP Dshboard | 126 days | Thu 01-02-24 | Mon 08-07-24
1.2.1.1 | Explore | 21 days | Thu 01-02-24 | Tue 27-02-24
1.2.1.1.1 | Requirement gathering | 10 days | Thu 01-02-24 | Tue 13-02-24 | HBT
1.2.1.1.2 | Prepare prototype of dashboards | 5 days | Wed 14-02-24 | Mon 19-02-24 | HBT | RGS preparation and submission by 02nd Mar '24
1.2.1.1.3 | Demonstrate to ASG | 2 days | Tue 20-02-24 | Wed 21-02-24 | HBT | FS of Dashboards to be prepared by 09th Mar '24
1.2.1.1.4 | Incorporate changes syggested | 2 days | Thu 22-02-24 | Fri 23-02-24 | HBT
1.2.1.1.5 | Submit final dashboard prototypes to ASG | 1 day | Mon 26-02-24 | Mon 26-02-24 | HBT
1.2.1.1.6 | Approval & signoff by ASG | 1 day | Tue 27-02-24 | Tue 27-02-24 | ASG | Approval and Sign off by ASG 27th Feb '24