## WRICEF Development List (2) (hidden)
SL No. | Module | Development Description | RICEFW | Priority | TE Priority | TE Remarks | Remark | Reusability | Project
1 | MM | Component Library | Interface | UAT | UAT |  |  | No
2 | MM | Open PR report for blocked materials | Report | Go Live | Go Live |  |  | Yes | ONX
3 | MM | Field for selecting material brand name in PR | Enhancement | UAT | UAT |  |  | No
4 | MM | Exceptional Workflow - Rate exceeds CL rate | Workflow | Go Live | UAT |  |  | No
5 | MM | Reason for rejection in PR and PO | Enhancement | UAT | UAT | Obj. 5 & 7 is merged |  | Yes | ONX
6 | MM | Release Stratgy as per Vertical heads | Enhancement | Go Live | UAT |  |  | Yes | ONX
7 | MM | PR rejection mail notification | Enhancement | Post Go Live |  | This should be along with #5 |  | No
8 | MM | Workflow for reservation | Workflow | SIT | SIT |  |  | No
9 | MM | Auto short closure of PR quantity post validity period of PR + 6 months. | Enhancement | Post Go Live | Post Go Live |  |  | Yes | Patel
10 | MM | E-Design | Interface | Go Live | UAT |  |  | No
11 | MM | PR to Payment Report (along with lead time) | Report | Go Live | Go Live |  |  | Yes | ONX
12 | MM | Purchase Order Print form | Form | SIT | SIT |  |  | No
13 | MM | Version Management at PO | Enhancement | Go Live | UAT | Obj. 13 & 22 is merged together |  | Yes | Runwal
14 | MM | PO Terms and conditions for Advance, BG..etc | Enhancement | UAT | UAT | Obj. 14 & 16 is merged together |  | Yes | M3M
15 | MM | Auto split of PO advances in ME2DP | Enhancement | Go Live | Go Live |  |  | No
16 | MM | PO document date to be greyed out. | Enhancement | SIT |  | This should be along with #14 |  | Yes | ONX
17 | MM | Report for hold/draft PO's | Report | Go Live | UAT |  |  | Yes | ONX
18 | MM | Report for Plan date vs actual delivery date of goods | Report | Go Live | Go Live |  |  | Yes | ONX
19 | MM | Short close of PO on Delivery completion Indicator | Enhancement | Post Go Live | Post Go Live |  |  | Yes | ONX
20 | MM | If Free of charge is checked in PO the PR should not be mandatory. | Enhancement | Post Go Live | Post Go Live |  |  | No
21 | MM | If release stg not defined the PO should give error during creation | Enhancement | SIT |  | This should be along with #13 |  | Yes | ONX
22 | MM | Service activity Price auto fetch from service master in PR | Enhancement | Go Live | UAT |  |  | No
23 | MM | custom fields required in Service entry sheet | Enhancement | SIT | SIT |  |  | No
24 | MM | GRN Print out | Form | SIT | SIT |  |  | No
25 | MM | Auto closure of expired reservation. | Enhancement | Post Go Live | Post Go Live |  |  | No
26 | MM | Material issue slip (MIS) | Form | UAT | SIT |  |  | No
27 | MM | Custom fields in MIGO screen for Goods issue | Enhancement | SIT | SIT | Report also to be included in this. |  | Yes | M3M
28 | FICO, CM | Validation on Duplicate Vendor | Enhancement | SIT | SIT | SL No. 76 merged with SL No. 31 |  | Yes | Janapriya
29 | FICO, CM | Vendor Ageing | Report | Go Live | Go Live |  |  | Yes | Janapriya
30 | FICO, CM | Vendor Ledger Statement (report) | Report | Post Go Live | Go Live |  |  | Yes | M3M
31 | FICO, CM | Payment advice (for vendor) | Form | UAT | UAT | SL No. 43 is merged with SL No.33 |  | Yes | M3M
32 | FICO, CM | MSME payment reminders | Enhancement | UAT | UAT |  |  | Yes | Max Estates
33 | FICO, CM | Bank Integration with SBI (Incoming & Outgoing) | Interface | UAT | UAT |  |  | No
34 | FICO, CM | Multiple cheque printing | Form | UAT | UAT |  |  | No
35 | FICO, CM | Bulk uploader for MIR7 | Conversion | Go Live |  | Needs discussion with CTMs | Needs discussion with CTMs | No
36 | FICO, CM | Bulk uploader to park petty cash invoices (FV60) | Conversion | Go Live | UAT |  |  | No
37 | FICO, CM | BG screen to capture BG details | Enhancement | UAT | UAT | Cover BG detailed report (#42) under this |  | No
38 | FICO, CM | BG detailed report | Report | UAT |  | Considered in #41 |  | No
39 | FICO, CM | Payment information to be mailed to the stake holders (PO creator, payment initiator etc) | Enhancement | Go Live |  | Can be covered under #35. Merged with SL No. 35 |  | No
40 | FICO, CM | Planned invoice reminders for insurance kind of transactions. | Enhancement | Post Go Live |  | This can be covered under Standard feature. Pls check. |  | No
41 | FICO, CM | Validation of Rs. 9,999 per day, per transaction & per vendor. | Enhancement | UAT | UAT |  |  | Yes | Max Estate, Kinjal
42 | FICO, CM | Success and failure report of E-Invoice | Report | UAT |  | Can be covered under #47 |  | Yes | Aparna
43 | FICO, CM | Mail trigger on Success and failure report of E-Invoice | Enhancement | UAT | UAT | SL No. 46 is merged with SL No.47 |  | No
44 | FICO, CM | Debtors aging report | Report | Post Go Live | Go Live |  |  | Yes | Patel, Sunteck, Alkhailfa
45 | FICO, CM | Deferred revenue report | Report | Post Go Live | Go Live |  |  | No
46 | FICO, CM | Customer receipt entry posting through SFDC | Interface | UAT | UAT |  |  | No
47 | FICO, CM | Customer ledger | Report | UAT | UAT | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | Yes | Aparna
48 | FICO, CM | Customer Invoice | Form | UAT | UAT | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | No
49 | FICO, CM | Daily collection upload, collection posting, unaccounted receipt report | Enhancement | Go Live |  | Not required right now. |  | No
50 | FICO, CM | Project wise inter-company and bank transaction report | Report | UAT | UAT |  |  | No
51 | FICO, CM | TDS uploader | Conversion | Go Live | UAT | Discuss with CTM | Discuss with CTM | Yes | Janapriya
52 | FICO, CM | Uploader for salary postings | Conversion | Go Live | UAT | Vendor wise posting |  | No
53 | FICO, CM | Project wise petty cash report | Conversion | Go Live |  | Can be done using standard features |  | No
54 | FICO, CM | GL – PF, PT report | Report | Go Live | Go Live |  |  | No
55 | FICO, CM | Bulk Payment Uploader | Conversion | Go Live | UAT | Discuss with CTM | Discuss with CTM | No
56 | FICO, CM | E-BRS | Interface | UAT | UAT |  |  | No
57 | FICO, CM | Maintenance of authorized signatory in respect to bank accounts & approval flow required for changes into it. Mail should be triggered for notification. | Enhancement | Go Live | Go Live |  |  | No
58 | FICO, CM | Fixed asset register is required | Report | Go Live | Go Live |  |  | Yes | Alkifah, KCC
59 | FICO, CM | TDS report | Report | Go Live | Go Live |  |  | Yes | Aparna
60 | FICO, CM | TDS expense report | Report | Go Live | Go Live |  |  | Yes | ASG
61 | FICO, CM | GST Reports | Report | Go Live | Go Live |  |  | Yes | URC, M3M, Max Estate
62 | FICO, CM | Validation to restirct wrong tax codes based on specified combination. | Enhancement | UAT | UAT |  |  | No
63 | FICO, CM | Special characters should not be allowed in HSN, GSTIN fields. | Enhancement | UAT |  | Can be covered under duplicate vendor check (#31) |  | No
64 | FICO, CM | Validation for foreign vendor account group mapping. | Enhancement | UAT | UAT | Schema group, country and currency validation |  | No
65 | FICO, CM | Consolidated trial balance | Report | Go Live | Go Live | Format to be shared by Ravi |  | No
66 | FICO, CM | Revenue recognition report | Report | Go Live | Go Live | Format to be shared by Ravi |  | Yes | Lodha
67 | PM | Equipment Logbook | Enhancement | UAT | SIT |  |  | Yes | HGIEL , KCC, Aparna, URC
68 | PM | Equipment Logbook Report | Report | SIT | SIT | This should be part of #81 |  | yes | HGIEL , KCC, Aparna, URC
69 | REFX | Upload of the contracts | Conversion | Go Live |  | This is not part of WRICEF list. It is a one time activity | Need to discuss with Shrikant | Yes | ESAG
70 | REFX | Upload of unit master data | Conversion | Go Live | Go Live |  |  | Yes | Max
71 | REFX | Contract workflow matrix table | Workflow | SIT |  | This should be part of #87. |  | Yes | ESAG
72 | REFX | Contract workflow | Workflow | SIT | SIT | SL No. 86 & 87 is merged |  | Yes | ESAG
73 | REFX | Contract workflow report | Report | SIT | SIT |  |  | Yes | Max
74 | REFX | Contract screen enhancement | Enhancement | SIT | SIT |  |  | Yes | Max
75 | REFX | Readings upload into the contract | Enhancement | SIT | SIT |  |  | Yes | Max
76 | REFX | Utility verification report | Report | SIT | SIT |  |  | Yes | Max
77 | REFX | Rental invoice form | Form | SIT | SIT |  |  | No
78 | REFX | Utility invoice form | Form | SIT | SIT |  |  | No
79 | REFX | Statement of account form | Form | SIT | SIT |  |  | No
80 | REFX | Clear tax integration | Interface | SIT |  | How is this different from Cleartax interface under SD module | Need to discuss with Client | No
81 | REFX | Average rental rate report | Report | SIT | SIT |  |  | No
82 | REFX | Invoice register report | Report | SIT | SIT |  |  | Yes | Max
83 | REFX | Asset management contract process combined report | Report | SIT | SIT | Needs discussion with CTMs | Needs discussion with CTMs | No
84 | PP | BOM creation from upload tool | Conversion | Go Live | UAT | BOM upload Tool | added | Yes | ONX
85 | SD | Customer Master API required in SAP. | Interface | UAT | UAT | 85 and 87 can be covered in same program |  | Yes | ASG
86 | SD | Customer Master uploader required. | Conversion | Go Live |  | This should not be part of WRICEF list. This is a one time activity. | Need to discuss with Shrikant | Yes | ASG
87 | SD | Customer Master update API required. | Interface | UAT |  | Covered in 85 |  | No | No
88 | SD | Channel Partner Creation API required. | Interface | UAT | UAT |  |  | Yes | ASG
89 | SD | Open Booking uploader for legacy data required. | Conversion | Go Live |  | This should not be part of WRICEF list. | Need to discuss with Shrikant | Yes | ASG
90 | SD | Booking creation API required. | Interface | UAT | UAT |  |  | Yes | ASG
91 | SD | Land abetement required during boking process and pricing and tax calculate accordingly in SAP. | Enhancement | UAT |  | This should be covered under #113 | Need to discuss with Shrikant | Yes | ASG
92 | SD | Broker Payout Process. | Enhancement | UAT | UAT | Needs discussion with CTMs | Need to discuss with AP CTM Tapas | Yes | ASG
93 | SD | Create demand of open milestone | Interface | UAT | UAT |  |  | No | No
94 | SD | Legacy Demands uploader required. | Conversion | Go Live |  | This should not be part of WRICEF list. | Need to discuss with AP CTM Tapas | Yes | ASG
95 | SD | Credit Note API required. | Interface | UAT | UAT | 95 and 96 is merged |  | Yes | ASG
96 | SD | Debit Note API required. | Interface | UAT |  | This should be covered under 95 |  | Yes | ASG
97 | SD | Unit cancellation program required for GST reversal. | Enhancement | UAT | UAT | Discuss with Soum about impact on books | Discuss with Soum about impact on books | Yes | ASG
98 | SD | Scrap Invoice Printout required. | Form | Go Live | Go Live | 98 and 101 is merged |  | No | No
99 | SD | Service Invoice Printout required | Form | Go Live | UAT | 99 and 102 is merged |  | No | No
100 | SD | Customer Service report required | Report | UAT | UAT | PMD |  | No | No
101 | SD | Asset Invoice Printout required | Form | Go Live |  | This should be covered under #98 in single smartform |  | No | No
102 | SD | STO / Intercompany Invoice Printout required | Form | UAT |  | This should be covered under #99 in single smartform |  | No | No
103 | SD | Export Invoice Printout | Form | UAT | UAT | Shipping note is required with export invoice | Need to discuss with @Prasanna Sir & @Ramya (TEMC) | No | No
104 | SD | Sales MIS / Sales Register required. | Report | Go Live | Go Live | TEMC |  | No | No
105 | SD | E-Inovice Creation & Cancellation Integration with ClearTax | Interface | UAT | UAT |  |  | Yes | ASG
106 | SD | E-Way Bill Creation & Cancellation Integration with ClearTax | Interface | UAT | UAT | 106 and 107 is merged |  | Yes | ASG
107 | SD | Get E-Way Bill Printout from ClearTax | Interface | UAT |  | This should be covered under #107 |  | Yes | ASG
108 | SD | OC Concept Build for Bookings (New Added) | Enhancement | UAT |  |  | Object Added | No | No
109 | SD | PMD Job Work Estimate Printout (New Added) | Form | UAT |  |  | Object Added | No | No
110 | SD | Booking Update API (New Added) | Interface | UAT |  |  | Object Added | No | No
111 | PM | Automatic Consumption Order | Enhancement | UAT | UAT | Needs discussion with CTMs | Not Required | No | No
112 | PM | Interface with BMS system (Not in Scope) | Interface |  | Post Go Live |  | Added(Post Go-Live ) | No | No
113 | PS | Project structure WBS upload program | Conversion | Go Live | UAT | 144 & 143 is merged |  | Yes | ASG
114 | PS | Project Networks/Activity upload program | Conversion | Go Live |  | This should be along with #143 |  | Yes | ASG
115 | PS | Heirarchial Cost plan upload program | Conversion | Go Live | UAT | 145 & 146 is merged |  | Yes | ASG
116 | PS | Unit Cost Plan Upload Program | Conversion | Go Live |  | This should be along with #145. Need download option for cost plan. |  | No | No
117 | PS | Budget approval from CEO for Budget supplement & Internal HOD approval for Budget Transfer | Workflow | UAT | UAT |  | Priority to be moved to SIT | Yes | Bajel
118 | PS | Budget exceed mail trigger to the multiple users | Enhancement | UAT | UAT | Balance budget, % budget consumed report is required which will be emailed to users. Category will be report. |  | No | No
119 | PS | Quantity Validation for materials in project | Enhancement | UAT | UAT |  |  | No | No
120 | PS | Plan vs Actual Qty for material against work done | Report | UAT |  | This should be along with #148 | 148 & 150 is merged | No | No
121 | PS | Budget remaining percentage report | Report | UAT |  |  | Object Added | No | No

## FS Sheet
SL No. | Module | Development Description | RICEFW | Priority | FS Status | TE Remarks | Remark | Reusability | Project
1 | MM | Component Library | Interface | UAT |  |  |  | No
2 | MM | Open PR report for blocked materials | Report | Go Live |  |  |  | Yes | ONX
3 | MM | Field for selecting material brand name in PR | Enhancement | UAT |  |  |  | No
4 | MM | Exceptional Workflow - Rate exceeds CL rate | Workflow | Go Live |  |  |  | No
5 | MM | Reason for rejection in PR and PO | Enhancement | UAT |  | Obj. 5 & 7 is merged |  | Yes | ONX
6 | MM | Release Stratgy as per Vertical heads | Enhancement | Go Live |  |  |  | Yes | ONX
7 | MM | PR rejection mail notification | Enhancement | Post Go Live |  | This should be along with #5 |  | No
8 | MM | Workflow for reservation | Workflow | SIT |  |  |  | No
9 | MM | Auto short closure of PR quantity post validity period of PR + 6 months. | Enhancement | Post Go Live |  |  |  | Yes | Patel
10 | MM | E-Design | Interface | Go Live |  |  |  | No
11 | MM | PR to Payment Report (along with lead time) | Report | Go Live |  |  |  | Yes | ONX
12 | MM | Purchase Order Print form | Form | SIT |  |  |  | No
13 | MM | Version Management at PO | Enhancement | Go Live |  | Obj. 13 & 22 is merged together |  | Yes | Runwal
14 | MM | PO Terms and conditions for Advance, BG..etc | Enhancement | UAT |  | Obj. 14 & 16 is merged together |  | Yes | M3M
15 | MM | Auto split of PO advances in ME2DP | Enhancement | Go Live |  |  |  | No
16 | MM | PO document date to be greyed out. | Enhancement | SIT |  | This should be along with #14 |  | Yes | ONX
17 | MM | Report for hold/draft PO's | Report | Go Live |  |  |  | Yes | ONX
18 | MM | Report for Plan date vs actual delivery date of goods | Report | Go Live |  |  |  | Yes | ONX
19 | MM | Short close of PO on Delivery completion Indicator | Enhancement | Post Go Live |  |  |  | Yes | ONX
20 | MM | If Free of charge is checked in PO the PR should not be mandatory. | Enhancement | Post Go Live |  |  |  | No
21 | MM | If release stg not defined the PO should give error during creation | Enhancement | SIT |  | This should be along with #13 |  | Yes | ONX
22 | MM | Service activity Price auto fetch from service master in PR | Enhancement | Go Live |  |  |  | No
23 | MM | custom fields required in Service entry sheet | Enhancement | SIT |  |  |  | No
24 | MM | GRN Print out | Form | SIT |  |  |  | No
25 | MM | Auto closure of expired reservation. | Enhancement | Post Go Live |  |  |  | No
26 | MM | Material issue slip (MIS) | Form | UAT |  |  |  | No
27 | MM | Custom fields in MIGO screen for Goods issue | Enhancement | SIT |  | Report also to be included in this. |  | Yes | M3M
28 | FICO, CM | Validation on Duplicate Vendor | Enhancement | SIT |  | SL No. 76 merged with SL No. 31 |  | Yes | Janapriya
29 | FICO, CM | Vendor Ageing | Report | Go Live |  |  |  | Yes | Janapriya
30 | FICO, CM | Vendor Ledger Statement (report) | Report | Post Go Live |  |  |  | Yes | M3M
31 | FICO, CM | Payment advice (for vendor) | Form | UAT |  | SL No. 43 is merged with SL No.33 |  | Yes | M3M
32 | FICO, CM | MSME payment reminders | Enhancement | UAT |  |  |  | Yes | Max Estates
33 | FICO, CM | Bank Integration with SBI (Incoming & Outgoing) | Interface | UAT |  |  |  | No
34 | FICO, CM | Multiple cheque printing | Form | UAT |  |  |  | No
35 | FICO, CM | Bulk uploader for MIR7 | Conversion | Go Live |  | Needs discussion with CTMs | Needs discussion with CTMs | No
36 | FICO, CM | Bulk uploader to park petty cash invoices (FV60) | Conversion | Go Live |  |  |  | No
37 | FICO, CM | BG screen to capture BG details | Enhancement | UAT |  | Cover BG detailed report (#42) under this |  | No
38 | FICO, CM | BG detailed report | Report | UAT |  | Considered in #41 |  | No
39 | FICO, CM | Payment information to be mailed to the stake holders (PO creator, payment initiator etc) | Enhancement | Go Live |  | Can be covered under #35. Merged with SL No. 35 |  | No
40 | FICO, CM | Planned invoice reminders for insurance kind of transactions. | Enhancement | Post Go Live |  | This can be covered under Standard feature. Pls check. |  | No
41 | FICO, CM | Validation of Rs. 9,999 per day, per transaction & per vendor. | Enhancement | UAT |  |  |  | Yes | Max Estate, Kinjal
42 | FICO, CM | Success and failure report of E-Invoice | Report | UAT |  | Can be covered under #47 |  | Yes | Aparna
43 | FICO, CM | Mail trigger on Success and failure report of E-Invoice | Enhancement | UAT |  | SL No. 46 is merged with SL No.47 |  | No
44 | FICO, CM | Debtors aging report | Report | Post Go Live |  |  |  | Yes | Patel, Sunteck, Alkhailfa
45 | FICO, CM | Deferred revenue report | Report | Post Go Live |  |  |  | No
46 | FICO, CM | Customer receipt entry posting through SFDC | Interface | UAT |  |  |  | No
47 | FICO, CM | Customer ledger | Report | UAT |  | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | Yes | Aparna
48 | FICO, CM | Customer Invoice | Form | UAT |  | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | No
49 | FICO, CM | Daily collection upload, collection posting, unaccounted receipt report | Enhancement | Go Live |  | Not required right now. |  | No
50 | FICO, CM | Project wise inter-company and bank transaction report | Report | UAT |  |  |  | No
51 | FICO, CM | TDS uploader | Conversion | Go Live |  | Discuss with CTM | Discuss with CTM | Yes | Janapriya
52 | FICO, CM | Uploader for salary postings | Conversion | Go Live |  | Vendor wise posting |  | No
53 | FICO, CM | Project wise petty cash report | Conversion | Go Live |  | Can be done using standard features |  | No
54 | FICO, CM | GL – PF, PT report | Report | Go Live |  |  |  | No
55 | FICO, CM | Bulk Payment Uploader | Conversion | Go Live |  | Discuss with CTM | Discuss with CTM | No
56 | FICO, CM | E-BRS | Interface | UAT |  |  |  | No
57 | FICO, CM | Maintenance of authorized signatory in respect to bank accounts & approval flow required for changes into it. Mail should be triggered for notification. | Enhancement | Go Live |  |  |  | No
58 | FICO, CM | Fixed asset register is required | Report | Go Live |  |  |  | Yes | Alkifah, KCC
59 | FICO, CM | TDS report | Report | Go Live |  |  |  | Yes | Aparna
60 | FICO, CM | TDS expense report | Report | Go Live |  |  |  | Yes | ASG
61 | FICO, CM | GST Reports | Report | Go Live |  |  |  | Yes | URC, M3M, Max Estate
62 | FICO, CM | Validation to restirct wrong tax codes based on specified combination. | Enhancement | UAT |  |  |  | No
63 | FICO, CM | Special characters should not be allowed in HSN, GSTIN fields. | Enhancement | UAT |  | Can be covered under duplicate vendor check (#31) |  | No
64 | FICO, CM | Validation for foreign vendor account group mapping. | Enhancement | UAT |  | Schema group, country and currency validation |  | No
65 | FICO, CM | Consolidated trial balance | Report | Go Live |  | Format to be shared by Ravi |  | No
66 | FICO, CM | Revenue recognition report | Report | Go Live |  | Format to be shared by Ravi |  | Yes | Lodha
67 | PM | Equipment Logbook | Enhancement | UAT |  |  |  | Yes | HGIEL , KCC, Aparna, URC
68 | PM | Equipment Logbook Report | Report | SIT |  | This should be part of #81 |  | yes | HGIEL , KCC, Aparna, URC
69 | REFX | Upload of the contracts | Conversion | Go Live |  | This is not part of WRICEF list. It is a one time activity | Need to discuss with Shrikant | Yes | ESAG
70 | REFX | Upload of unit master data | Conversion | Go Live |  |  |  | Yes | Max
71 | REFX | Contract workflow matrix table | Workflow | SIT |  | This should be part of #87. |  | Yes | ESAG
72 | REFX | Contract workflow | Workflow | SIT |  | SL No. 86 & 87 is merged |  | Yes | ESAG
73 | REFX | Contract workflow report | Report | SIT |  |  |  | Yes | Max
74 | REFX | Contract screen enhancement | Enhancement | SIT |  |  |  | Yes | Max
75 | REFX | Readings upload into the contract | Enhancement | SIT |  |  |  | Yes | Max
76 | REFX | Utility verification report | Report | SIT |  |  |  | Yes | Max
77 | REFX | Rental invoice form | Form | SIT |  |  |  | No
78 | REFX | Utility invoice form | Form | SIT |  |  |  | No
79 | REFX | Statement of account form | Form | SIT |  |  |  | No
80 | REFX | Clear tax integration | Interface | SIT |  | How is this different from Cleartax interface under SD module | Need to discuss with Client | No
81 | REFX | Average rental rate report | Report | SIT |  |  |  | No
82 | REFX | Invoice register report | Report | SIT |  |  |  | Yes | Max
83 | REFX | Asset management contract process combined report | Report | SIT |  | Needs discussion with CTMs | Needs discussion with CTMs | No
84 | PP | BOM creation from upload tool | Conversion | Go Live |  | BOM upload Tool | added | Yes | ONX
85 | SD | Customer Master API required in SAP. | Interface | UAT |  | 85 and 87 can be covered in same program |  | Yes | ASG
86 | SD | Customer Master uploader required. | Conversion | Go Live |  | This should not be part of WRICEF list. This is a one time activity. | Need to discuss with Shrikant | Yes | ASG
87 | SD | Customer Master update API required. | Interface | UAT |  | Covered in 85 |  | No | No
88 | SD | Channel Partner Creation API required. | Interface | UAT |  |  |  | Yes | ASG
89 | SD | Open Booking uploader for legacy data required. | Conversion | Go Live |  | This should not be part of WRICEF list. | Need to discuss with Shrikant | Yes | ASG
90 | SD | Booking creation API required. | Interface | UAT |  |  |  | Yes | ASG
91 | SD | Land abetement required during boking process and pricing and tax calculate accordingly in SAP. | Enhancement | UAT |  | This should be covered under #113 | Need to discuss with Shrikant | Yes | ASG
92 | SD | Broker Payout Process. | Enhancement | UAT |  | Needs discussion with CTMs | Need to discuss with AP CTM Tapas | Yes | ASG
93 | SD | Create demand of open milestone | Interface | UAT |  |  |  | No | No
94 | SD | Legacy Demands uploader required. | Conversion | Go Live |  | This should not be part of WRICEF list. | Need to discuss with AP CTM Tapas | Yes | ASG
95 | SD | Credit Note API required. | Interface | UAT |  | 95 and 96 is merged |  | Yes | ASG
96 | SD | Debit Note API required. | Interface | UAT |  | This should be covered under 95 |  | Yes | ASG
97 | SD | Unit cancellation program required for GST reversal. | Enhancement | UAT |  | Discuss with Soum about impact on books | Discuss with Soum about impact on books | Yes | ASG
98 | SD | Scrap Invoice Printout required. | Form | Go Live |  | 98 and 101 is merged |  | No | No
99 | SD | Service Invoice Printout required | Form | Go Live |  | 99 and 102 is merged |  | No | No
100 | SD | Customer Service report required | Report | UAT |  | PMD |  | No | No
101 | SD | Asset Invoice Printout required | Form | Go Live |  | This should be covered under #98 in single smartform |  | No | No
102 | SD | STO / Intercompany Invoice Printout required | Form | UAT |  | This should be covered under #99 in single smartform |  | No | No
103 | SD | Export Invoice Printout | Form | UAT |  | Shipping note is required with export invoice | Need to discuss with @Prasanna Sir & @Ramya (TEMC) | No | No
104 | SD | Sales MIS / Sales Register required. | Report | Go Live |  | TEMC |  | No | No
105 | SD | E-Inovice Creation & Cancellation Integration with ClearTax | Interface | UAT |  |  |  | Yes | ASG
106 | SD | E-Way Bill Creation & Cancellation Integration with ClearTax | Interface | UAT |  | 106 and 107 is merged |  | Yes | ASG
107 | SD | Get E-Way Bill Printout from ClearTax | Interface | UAT |  | This should be covered under #107 |  | Yes | ASG
108 | SD | OC Concept Build for Bookings (New Added) | Enhancement | UAT |  |  | Object Added | No | No
109 | SD | PMD Job Work Estimate Printout (New Added) | Form | UAT |  |  | Object Added | No | No
110 | SD | Booking Update API (New Added) | Interface | UAT |  |  | Object Added | No | No
111 | PM | Automatic Consumption Order | Enhancement | UAT |  | Needs discussion with CTMs | Not Required | No | No
112 | PM | Interface with BMS system (Not in Scope) | Interface | Post Go Live |  |  | Added(Post Go-Live ) | No | No
113 | PS | Project structure WBS upload program | Conversion | Go Live |  | 144 & 143 is merged |  | Yes | ASG
114 | PS | Project Networks/Activity upload program | Conversion | Go Live |  | This should be along with #143 |  | Yes | ASG
115 | PS | Heirarchial Cost plan upload program | Conversion | Go Live |  | 145 & 146 is merged |  | Yes | ASG
116 | PS | Unit Cost Plan Upload Program | Conversion | Go Live |  | This should be along with #145. Need download option for cost plan. |  | No | No
117 | PS | Budget approval from CEO for Budget supplement & Internal HOD approval for Budget Transfer | Workflow | UAT |  |  | Priority to be moved to SIT | Yes | Bajel
118 | PS | Budget exceed mail trigger to the multiple users | Enhancement | UAT |  | Balance budget, % budget consumed report is required which will be emailed to users. Category will be report. |  | No | No
119 | PS | Quantity Validation for materials in project | Enhancement | UAT |  |  |  | No | No
120 | PS | Plan vs Actual Qty for material against work done | Report | UAT |  | This should be along with #148 | 148 & 150 is merged | No | No
121 | PS | Budget remaining percentage report | Report | UAT |  |  | Object Added | No | No

## WRICEF Development List
SL No. | Module | Development Description | RICEFW | Priority | TE Priority | TE Remarks | Remark | Reusability | Project
1 | MM | Component Library | Interface | UAT | UAT |  |  | No
2 | MM | Open PR report for blocked materials | Report | Go Live | Go Live |  |  | Yes | ONX
3 | MM | Field for selecting material brand name in PR | Enhancement | UAT | UAT |  |  | No
4 | MM | Exceptional Workflow - Rate exceeds CL rate | Workflow | Go Live | UAT |  |  | No
5 | MM | Reason for rejection in PR and PO | Enhancement | UAT | UAT | Obj. 5 & 7 is merged |  | Yes | ONX
6 | MM | Release Stratgy as per Vertical heads | Enhancement | Go Live | UAT |  |  | Yes | ONX
7 | MM | PR rejection mail notification | Enhancement | Post Go Live |  | This should be along with #5 |  | No
8 | MM | Workflow for reservation | Workflow | SIT | SIT |  |  | No
9 | MM | Auto short closure of PR quantity post validity period of PR + 6 months. | Enhancement | Post Go Live | Post Go Live |  |  | Yes | Patel
10 | MM | E-Design | Interface | Go Live | UAT |  |  | No
11 | MM | PR to Payment Report (along with lead time) | Report | Go Live | Go Live |  |  | Yes | ONX
12 | MM | Purchase Order Print form | Form | SIT | SIT |  |  | No
13 | MM | Version Management at PO | Enhancement | Go Live | UAT | Obj. 13 & 22 is merged together |  | Yes | Runwal
14 | MM | PO Terms and conditions for Advance, BG..etc | Enhancement | UAT | UAT | Obj. 14 & 16 is merged together |  | Yes | M3M
15 | MM | Auto split of PO advances in ME2DP | Enhancement | Go Live | Go Live |  |  | No
16 | MM | PO document date to be greyed out. | Enhancement | SIT | Go Live | This should be along with #14 |  | Yes | ONX
17 | MM | Report for hold/draft PO's | Report | Go Live | UAT |  |  | Yes | ONX
18 | MM | Report for Plan date vs actual delivery date of goods | Report | Go Live | Go Live |  |  | Yes | ONX
19 | MM | Short close of PO on Delivery completion Indicator | Enhancement | Post Go Live | Post Go Live |  |  | Yes | ONX
20 | MM | If Free of charge is checked in PO the PR should not be mandatory. | Enhancement | Post Go Live | Post Go Live |  |  | No
21 | MM | If release stg not defined the PO should give error during creation | Enhancement | SIT | Go Live | This should be along with #13 |  | Yes | ONX
22 | MM | Service activity Price auto fetch from service master in PR | Enhancement | Go Live | UAT |  |  | No
23 | MM | custom fields required in Service entry sheet | Enhancement | SIT | SIT |  |  | No
24 | MM | GRN Print out | Form | SIT | SIT |  |  | No
25 | MM | Auto closure of expired reservation. | Enhancement | Post Go Live | Post Go Live |  |  | No
26 | MM | Material issue slip (MIS) | Form | UAT | SIT |  |  | No
27 | MM | Custom fields in MIGO screen for Goods issue | Enhancement | SIT | SIT | Report also to be included in this. |  | Yes | M3M
28 | FICO, CM | Validation on Duplicate Vendor | Enhancement | SIT | SIT | SL No. 76 merged with SL No. 31 |  | Yes | Janapriya
29 | FICO, CM | Vendor Ageing | Report | Go Live | Go Live |  |  | Yes | Janapriya
30 | FICO, CM | Vendor Ledger Statement (report) | Report | Post Go Live | Go Live |  |  | Yes | M3M
31 | FICO, CM | Payment advice (for vendor) | Form | UAT | UAT | SL No. 43 is merged with SL No.33 |  | Yes | M3M
32 | FICO, CM | MSME payment reminders | Enhancement | UAT | UAT |  |  | Yes | Max Estates
33 | FICO, CM | Bank Integration with SBI (Incoming & Outgoing) | Interface | UAT | UAT |  |  | No
34 | FICO, CM | Multiple cheque printing | Form | UAT | UAT |  |  | No
35 | FICO, CM | Bulk uploader for MIR7 | Conversion | Go Live |  | Needs discussion with CTMs | Needs discussion with CTMs | No
36 | FICO, CM | Bulk uploader to park petty cash invoices (FV60) | Conversion | Go Live | UAT |  |  | No
37 | FICO, CM | BG screen to capture BG details | Enhancement | UAT | UAT | Cover BG detailed report (#42) under this |  | No
38 | FICO, CM | BG detailed report | Report | UAT |  | Considered in #41 |  | No
39 | FICO, CM | Payment information to be mailed to the stake holders (PO creator, payment initiator etc) | Enhancement | Go Live |  | Can be covered under #35. Merged with SL No. 35 |  | No
40 | FICO, CM | Planned invoice reminders for insurance kind of transactions. | Enhancement | Post Go Live |  | This can be covered under Standard feature. Pls check. |  | No
41 | FICO, CM | Validation of Rs. 9,999 per day, per transaction & per vendor. | Enhancement | UAT | UAT |  |  | Yes | Max Estate, Kinjal
42 | FICO, CM | Success and failure report of E-Invoice | Report | UAT |  | Can be covered under #47 |  | Yes | Aparna
43 | FICO, CM | Mail trigger on Success and failure report of E-Invoice | Enhancement | UAT | UAT | SL No. 46 is merged with SL No.47 |  | No
44 | FICO, CM | Debtors aging report | Report | Post Go Live | Go Live |  |  | Yes | Patel, Sunteck, Alkhailfa
45 | FICO, CM | Deferred revenue report | Report | Post Go Live | Go Live |  |  | No
46 | FICO, CM | Customer receipt entry posting through SFDC | Interface | UAT | UAT |  |  | No
47 | FICO, CM | Customer ledger | Report | UAT | UAT | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | Yes | Indinfravit/Sunteck
48 | FICO, CM | Customer Invoice | Form | UAT | UAT | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | No
49 | FICO, CM | Daily collection upload, collection posting, unaccounted receipt report | Enhancement | Go Live |  | Not required right now. |  | No
50 | FICO, CM | Project wise inter-company and bank transaction report | Report | UAT | UAT |  |  | No
51 | FICO, CM | TDS uploader | Conversion | Go Live | UAT | Discuss with CTM | Discuss with CTM | Yes | Janapriya
52 | FICO, CM | Uploader for salary postings | Conversion | Go Live | UAT | Vendor wise posting |  | No
53 | FICO, CM | Project wise petty cash report | Conversion | Go Live |  | Can be done using standard features |  | No
54 | FICO, CM | GL – PF, PT report | Report | Go Live | Go Live |  |  | No
55 | FICO, CM | Bulk Payment Uploader | Conversion | Go Live | UAT | Discuss with CTM | Discuss with CTM | No
56 | FICO, CM | E-BRS | Interface | UAT | UAT |  |  | No
57 | FICO, CM | Maintenance of authorized signatory in respect to bank accounts & approval flow required for changes into it. Mail should be triggered for notification. | Enhancement | Go Live | Go Live |  |  | No
58 | FICO, CM | Fixed asset register is required | Report | Go Live | Go Live |  |  | Yes | Alkifah, KCC
59 | FICO, CM | TDS report | Report | Go Live | Go Live |  |  | Yes | ASG
60 | FICO, CM | TDS expense report | Report | Go Live | Go Live |  |  | Yes | ASG
61 | FICO, CM | GST Reports | Report | Go Live | Go Live |  |  | Yes | URC, M3M, Max Estate
62 | FICO, CM | Validation to restirct wrong tax codes based on specified combination. | Enhancement | UAT | UAT |  |  | No
63 | FICO, CM | Special characters should not be allowed in HSN, GSTIN fields. | Enhancement | UAT |  | Can be covered under duplicate vendor check (#31) |  | No
64 | FICO, CM | Validation for foreign vendor account group mapping. | Enhancement | UAT | UAT | Schema group, country and currency validation |  | No
65 | FICO, CM | Consolidated trial balance | Report | Go Live | Go Live | Format to be shared by Ravi |  | No
66 | FICO, CM | Revenue recognition report | Report | Go Live | Go Live | Format to be shared by Ravi |  | Yes | Lodha
67 | PM | Equipment Logbook | Enhancement | UAT | SIT |  |  | Yes | HGIEL , KCC, Aparna, URC
68 | PM | Equipment Logbook Report | Report | SIT | SIT | This should be part of #81 |  | yes | HGIEL , KCC, Aparna, URC
69 | REFX | Upload of the contracts | Conversion | Go Live |  | This is not part of WRICEF list. It is a one time activity | Need to discuss with Shrikant | Yes | ESAG
70 | REFX | Upload of unit master data | Conversion | Go Live | Go Live |  |  | Yes | Max
71 | REFX | Contract workflow matrix table | Workflow | SIT |  | This should be part of #87. |  | Yes | ESAG
72 | REFX | Contract workflow | Workflow | SIT | SIT | SL No. 86 & 87 is merged |  | Yes | ESAG
73 | REFX | Contract workflow report | Report | SIT | SIT |  |  | Yes | Max
74 | REFX | Contract screen enhancement | Enhancement | SIT | SIT |  |  | Yes | Max
75 | REFX | Readings upload into the contract | Enhancement | SIT | SIT |  |  | Yes | Max
76 | REFX | Utility verification report | Report | SIT | SIT |  |  | Yes | Max
77 | REFX | Rental invoice form | Form | SIT | SIT |  |  | No
78 | REFX | Utility invoice form | Form | SIT | SIT |  |  | No
79 | REFX | Statement of account form | Form | SIT | SIT |  |  | No
80 | REFX | Clear tax integration | Interface | SIT |  | How is this different from Cleartax interface under SD module | Need to discuss with Client | No
81 | REFX | Average rental rate report | Report | SIT | SIT |  |  | No
82 | REFX | Invoice register report | Report | SIT | SIT |  |  | Yes | Max
83 | REFX | Asset management contract process combined report | Report | SIT | SIT | Needs discussion with CTMs | Needs discussion with CTMs | No
84 | PP | BOM creation from upload tool | Conversion | Go Live | UAT | BOM upload Tool | added | Yes | ONX
85 | SD | Customer Master API required in SAP. | Interface | UAT | UAT | 85 and 87 can be covered in same program |  | Yes | ASG
86 | SD | Customer Master uploader required. | Conversion | Go Live |  | This should not be part of WRICEF list. This is a one time activity. | Need to discuss with Shrikant | Yes | ASG
87 | SD | Customer Master update API required. | Interface | UAT |  | Covered in 85 |  | No | No
88 | SD | Channel Partner Creation API required. | Interface | UAT | UAT |  |  | Yes | ASG
89 | SD | Open Booking uploader for legacy data required. | Conversion | Go Live |  | This should not be part of WRICEF list. | Need to discuss with Shrikant | Yes | ASG
90 | SD | Booking creation API required. | Interface | UAT | UAT |  |  | Yes | ASG
91 | SD | Land abetement required during boking process and pricing and tax calculate accordingly in SAP. | Enhancement | UAT |  | This should be covered under #113 | Need to discuss with Shrikant | Yes | ASG
92 | SD | Broker Payout Process. | Enhancement | UAT | UAT | Needs discussion with CTMs | Need to discuss with AP CTM Tapas | Yes | ASG
93 | SD | Create demand of open milestone | Interface | UAT | UAT |  |  | No | No
94 | SD | Legacy Demands uploader required. | Conversion | Go Live |  | This should not be part of WRICEF list. | Need to discuss with AP CTM Tapas | Yes | ASG
95 | SD | Credit Note API required. | Interface | UAT | UAT | 95 and 96 is merged |  | Yes | ASG
96 | SD | Debit Note API required. | Interface | UAT |  | This should be covered under 95 |  | Yes | ASG
97 | SD | Unit cancellation program required for GST reversal. | Enhancement | UAT | UAT | Discuss with Soum about impact on books | Discuss with Soum about impact on books | Yes | ASG
98 | SD | Scrap Invoice Printout required. | Form | Go Live | Go Live | 98 and 101 is merged |  | No | No
99 | SD | Service Invoice Printout required | Form | Go Live | UAT | 99 and 102 is merged |  | No | No
100 | SD | Customer Service report required | Report | UAT | UAT | PMD |  | No | No
101 | SD | Asset Invoice Printout required | Form | Go Live |  | This should be covered under #98 in single smartform |  | No | No
102 | SD | STO / Intercompany Invoice Printout required | Form | UAT |  | This should be covered under #99 in single smartform |  | No | No
103 | SD | Export Invoice Printout | Form | UAT | UAT | Shipping note is required with export invoice | Need to discuss with @Prasanna Sir & @Ramya (TEMC) | No | No
104 | SD | Sales MIS / Sales Register required. | Report | Go Live | Go Live | TEMC |  | No | No
105 | SD | E-Inovice Creation & Cancellation Integration with ClearTax | Interface | UAT | UAT |  |  | Yes | ASG
106 | SD | E-Way Bill Creation & Cancellation Integration with ClearTax | Interface | UAT | UAT | 106 and 107 is merged |  | Yes | ASG
107 | SD | Get E-Way Bill Printout from ClearTax | Interface | UAT |  | This should be covered under #107 |  | Yes | ASG
108 | SD | OC Concept Build for Bookings (New Added) | Enhancement | UAT |  |  | Object Added | No | No
109 | SD | PMD Job Work Estimate Printout (New Added) | Form | UAT |  |  | Object Added | No | No
110 | SD | Booking Update API (New Added) | Interface | UAT |  |  | Object Added | No | No
111 | PM | Automatic Consumption Order | Enhancement | UAT | UAT | Needs discussion with CTMs | Not Required | No | No
112 | PM | Interface with BMS system (Not in Scope) | Interface | Post Go Live | Post Go Live |  | Added(Post Go-Live ) | No | No
113 | PS | Project structure WBS upload program | Conversion | Go Live | UAT | 144 & 143 is merged |  | Yes | ASG
114 | PS | Project Networks/Activity upload program | Conversion | Go Live |  | This should be along with #143 |  | Yes | ASG
115 | PS | Heirarchial Cost plan upload program | Conversion | Go Live | UAT | 145 & 146 is merged |  | Yes | ASG
116 | PS | Unit Cost Plan Upload Program | Conversion | Go Live |  | This should be along with #145. Need download option for cost plan. |  | No | No
117 | PS | Budget approval from CEO for Budget supplement & Internal HOD approval for Budget Transfer | Workflow | UAT | UAT |  | Priority to be moved to SIT | Yes | Bajel
118 | PS | Budget exceed mail trigger to the multiple users | Enhancement | UAT | UAT | Balance budget, % budget consumed report is required which will be emailed to users. Category will be report. |  | No | No
119 | PS | Quantity Validation for materials in project | Enhancement | UAT | UAT |  |  | No | No
120 | PS | Plan vs Actual Qty for material against work done | Report | UAT |  | This should be along with #148 | 148 & 150 is merged | No | No
121 | PS | Budget remaining percentage report | Report | UAT |  |  | Object Added | No | No

## RGS Pivot
Reusability | (ALL)
RGS Status
Count of Development Description |  | RGS Status
Module | RICEFW | Completed | Inprogress | Not Started | Grand Total
FICO, CM | Conversion | 5 | 1 |  | 6
| Enhancement | 12 |  |  | 12
| Form | 2 |  | 1 | 3
| Interface | 1 |  | 2 | 3
| Report | 11 | 1 | 3 | 15
FICO, CM Total |  | 31 | 2 | 6 | 39
MM | Enhancement | 16 |  |  | 16
| Form | 3 |  |  | 3
| Interface | 2 |  |  | 2
| Report | 4 |  |  | 4
| Workflow | 2 |  |  | 2
MM Total |  | 27 |  |  | 27
PM | Enhancement | 1 |  |  | 1
| Interface |  |  | 1 | 1
| Report | 1 |  |  | 1
PM Total |  | 2 |  | 1 | 3
PP | Conversion | 1 |  |  | 1
PP Total |  | 1 |  |  | 1
PS | Conversion | 4 |  |  | 4
| Enhancement | 2 |  |  | 2
| Report | 2 |  |  | 2
| Workflow | 1 |  |  | 1
PS Total |  | 9 |  |  | 9
REFX | Conversion | 2 |  |  | 2
| Enhancement | 2 |  |  | 2
| Form | 3 |  |  | 3
| Interface |  | 1 |  | 1
| Report | 2 | 3 |  | 5
| Workflow | 2 |  |  | 2
REFX Total |  | 11 | 4 |  | 15
SD | Conversion | 3 |  |  | 3
| Enhancement | 4 |  |  | 4
| Form | 2 |  | 4 | 6
| Interface | 9 |  | 2 | 11
| Report |  | 1 | 1 | 2
SD Total |  | 18 | 1 | 7 | 26
Grand Total |  | 99 | 7 | 14 | 120

## RGS List
SL No. | Module | Development Description | RICEFW | Priority | RGS Status | FS Status | TE Remarks | Remark | Reusability | Project
1 | MM | Component Library | Interface | UAT | Completed | Completed |  |  | No
2 | MM | Open PR report for blocked materials | Report | Go Live | Completed | Completed |  |  | Yes | ONX
3 | MM | Field for selecting material brand name in PR | Enhancement | UAT | Completed | Completed |  |  | No
4 | MM | Exceptional Workflow - Rate exceeds CL rate | Workflow | Go Live | Completed | Completed |  |  | No
5 | MM | Reason for rejection in PR and PO | Enhancement | UAT | Completed | Inprogress | Obj. 5 & 7 is merged |  | Yes | ONX
6 | MM | Release Stratgy as per Vertical heads | Enhancement | Go Live | Completed | Completed |  |  | Yes | ONX
7 | MM | PR rejection mail notification | Enhancement | Post Go Live | Completed | Completed | This should be along with #5 |  | No
8 | MM | Workflow for reservation | Workflow | SIT | Completed | Completed |  |  | No
9 | MM | Auto short closure of PR quantity post validity period of PR + 6 months. | Enhancement | Post Go Live | Completed | Completed |  |  | Yes | Patel
10 | MM | E-Design | Interface | Go Live | Completed | Completed |  |  | No
11 | MM | PR to Payment Report (along with lead time) | Report | Go Live | Completed | Completed |  |  | Yes | ONX
12 | MM | Purchase Order Print form | Form | SIT | Completed | Completed |  |  | No
13 | MM | Version Management at PO | Enhancement | Go Live | Completed | Completed | Obj. 13 & 22 is merged together |  | Yes | Runwal
14 | MM | PO Terms and conditions for Advance, BG..etc | Enhancement | UAT | Completed | Completed | Obj. 14 & 16 is merged together |  | Yes | M3M
15 | MM | Auto split of PO advances in ME2DP | Enhancement | Go Live | Completed | Completed |  |  | No
16 | MM | PO document date to be greyed out. | Enhancement | SIT | Completed | Completed | This should be along with #14 |  | Yes | ONX
17 | MM | Report for hold/draft PO's | Report | Go Live | Completed | Completed |  |  | Yes | ONX
18 | MM | Report for Plan date vs actual delivery date of goods | Report | Go Live | Completed | Completed |  |  | Yes | ONX
19 | MM | Short close of PO on Delivery completion Indicator | Enhancement | Post Go Live | Completed | Completed |  |  | Yes | ONX
20 | MM | If Free of charge is checked in PO the PR should not be mandatory. | Enhancement | Post Go Live | Completed | Completed |  |  | No
21 | MM | If release stg not defined the PO should give error during creation | Enhancement | SIT | Completed | Completed | This should be along with #13 |  | Yes | ONX
22 | MM | Service activity Price auto fetch from service master in PR | Enhancement | Go Live | Completed | Completed |  |  | No
23 | MM | custom fields required in Service entry sheet | Enhancement | SIT | Completed | Completed |  |  | No
24 | MM | GRN Print out | Form | SIT | Completed | Completed |  |  | No
25 | MM | Auto closure of expired reservation. | Enhancement | Post Go Live | Completed | Completed |  |  | No
26 | MM | Material issue slip (MIS) | Form | UAT | Completed | Completed |  |  | No
27 | MM | Custom fields in MIGO screen for Goods issue | Enhancement | SIT | Completed | Completed | Report also to be included in this. |  | Yes | M3M
28 | FICO, CM | Validation on Duplicate Vendor | Enhancement | SIT | Completed | Completed | SL No. 76 merged with SL No. 31 |  | Yes | Janapriya
29 | FICO, CM | Vendor Ageing | Report | Go Live | Completed | Completed |  |  | Yes | Janapriya
30 | FICO, CM | Vendor Ledger Statement (report) | Report | Post Go Live | Completed | Completed |  |  | Yes | M3M
31 | FICO, CM | Payment advice (for vendor) | Form | UAT | Completed | Completed | SL No. 43 is merged with SL No.33 |  | Yes | M3M
32 | FICO, CM | MSME payment reminders | Enhancement | UAT | Completed | Completed |  |  | Yes | Max Estates
33 | FICO, CM | Bank Integration with SBI (Incoming & Outgoing) | Interface | UAT | Not Started | Not Started |  |  | No
34 | FICO, CM | Multiple cheque printing | Form | UAT | Completed | Completed |  |  | No
35 | FICO, CM | Bulk uploader for MIR7 | Conversion | Go Live | Completed | Completed | Needs discussion with CTMs | Needs discussion with CTMs | No
36 | FICO, CM | Bulk uploader to park petty cash invoices (FV60) | Conversion | Go Live | Completed | Completed |  |  | No
37 | FICO, CM | BG screen to capture BG details | Enhancement | UAT | Completed | Completed | Cover BG detailed report (#42) under this |  | No
38 | FICO, CM | BG detailed report | Report | UAT | Completed | Completed | Considered in #41 |  | No
39 | FICO, CM | Payment information to be mailed to the stake holders (PO creator, payment initiator etc) | Enhancement | Go Live | Completed | Completed | Can be covered under #35. Merged with SL No. 35 |  | No
40 | FICO, CM | Planned invoice reminders for insurance kind of transactions. | Enhancement | Post Go Live | Completed | Completed | This can be covered under Standard feature. Pls check. |  | No
41 | FICO, CM | Validation of Rs. 9,999 per day, per transaction & per vendor. | Enhancement | UAT | Completed | Completed |  |  | Yes | Max Estate, Kinjal
42 | FICO, CM | Success and failure report of E-Invoice | Report | UAT | Completed | Completed | Can be covered under #47 |  | Yes | Aparna
43 | FICO, CM | Mail trigger on Success and failure report of E-Invoice | Enhancement | UAT | Completed | Completed | SL No. 46 is merged with SL No.47 |  | No
44 | FICO, CM | Debtors aging report | Report | Post Go Live | Completed | Completed |  |  | Yes | Patel, Sunteck, Alkhailfa
45 | FICO, CM | Deferred revenue report | Report | Post Go Live | Not Started | Not Started |  |  | No
46 | FICO, CM | Customer receipt entry posting through SFDC | Interface | UAT | Completed | Completed |  |  | No
47 | FICO, CM | Customer ledger | Report | UAT | Completed | Completed | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | Yes | Aparna
48 | FICO, CM | Customer Invoice | Form | UAT | Not Started | Not Started | Check interface to send customer ledger to SFDC | Check interface to send customer ledger to SFDC | No
49 | FICO, CM | Daily collection upload, collection posting, unaccounted receipt report | Enhancement | Go Live | Completed | Completed | Not required right now. |  | No
50 | FICO, CM | Project wise inter-company and bank transaction report | Report | UAT | Completed | Completed |  |  | No
51 | FICO, CM | TDS uploader | Conversion | Go Live | Inprogress | Inprogress | Discuss with CTM | Discuss with CTM | Yes | Janapriya
52 | FICO, CM | Uploader for salary postings | Conversion | Go Live | Completed | Completed | Vendor wise posting |  | No
53 | FICO, CM | Project wise petty cash report | Conversion | Go Live | Completed | Completed | Can be done using standard features |  | No
54 | FICO, CM | GL – PF, PT report | Report | Go Live | Completed | Completed |  |  | No
55 | FICO, CM | Bulk Payment Uploader | Conversion | Go Live | Completed | Completed | Discuss with CTM | Discuss with CTM | No
56 | FICO, CM | E-BRS | Interface | UAT | Not Started | Not Started |  |  | No
57 | FICO, CM | Maintenance of authorized signatory in respect to bank accounts & approval flow required for changes into it. Mail should be triggered for notification. | Enhancement | Go Live | Completed | Completed |  |  | No
58 | FICO, CM | Fixed asset register is required | Report | Go Live | Completed | Completed |  |  | Yes | Alkifah, KCC
59 | FICO, CM | TDS report | Report | Go Live | Completed | Completed |  |  | Yes | Aparna
60 | FICO, CM | TDS expense report | Report | Go Live | Completed | Completed |  |  | Yes | ASG
61 | FICO, CM | GST Reports | Report | Go Live | Inprogress | Inprogress |  |  | Yes | URC, M3M, Max Estate
62 | FICO, CM | Validation to restirct wrong tax codes based on specified combination. | Enhancement | UAT | Completed | Completed |  |  | No
63 | FICO, CM | Special characters should not be allowed in HSN, GSTIN fields. | Enhancement | UAT | Completed | Completed | Can be covered under duplicate vendor check (#31) |  | No
64 | FICO, CM | Validation for foreign vendor account group mapping. | Enhancement | UAT | Completed | Completed | Schema group, country and currency validation |  | No
65 | FICO, CM | Consolidated trial balance | Report | Go Live | Not Started | Not Started | Format to be shared by Ravi |  | No
66 | FICO, CM | Revenue recognition report | Report | Go Live | Not Started | Not Started | Format to be shared by Ravi |  | Yes | Lodha
67 | PM | Equipment Logbook | Enhancement | UAT | Completed | Completed |  |  | Yes | HGIEL , KCC, Aparna, URC
68 | PM | Equipment Logbook Report | Report | SIT | Completed | Completed | This should be part of #81 |  | yes | HGIEL , KCC, Aparna, URC
69 | REFX | Upload of the contracts | Conversion | Go Live | Completed | Completed | This is not part of WRICEF list. It is a one time activity | Need to discuss with Shrikant | Yes | ESAG
70 | REFX | Upload of unit master data | Conversion | Go Live | Completed | Completed |  |  | Yes | Max
71 | REFX | Contract workflow matrix table | Workflow | SIT | Completed | Completed | This should be part of #87. |  | Yes | ESAG
72 | REFX | Contract workflow | Workflow | SIT | Completed | Completed | SL No. 86 & 87 is merged |  | Yes | ESAG
73 | REFX | Contract workflow report | Report | SIT | Completed | Completed |  |  | Yes | Max
74 | REFX | Contract screen enhancement | Enhancement | SIT | Completed | Completed |  |  | Yes | Max
75 | REFX | Readings upload into the contract | Enhancement | SIT | Completed | Completed |  |  | Yes | Max
76 | REFX | Utility verification report | Report | SIT | Completed | Completed |  |  | Yes | Max
77 | REFX | Rental invoice form | Form | SIT | Completed | Completed |  |  | No
78 | REFX | Utility invoice form | Form | SIT | Completed | Completed |  |  | No
79 | REFX | Statement of account form | Form | SIT | Completed | Completed |  |  | No
80 | REFX | Clear tax integration | Interface | SIT | Inprogress | Inprogress | How is this different from Cleartax interface under SD module | Need to discuss with Client | No
81 | REFX | Average rental rate report | Report | SIT | Inprogress | Inprogress |  |  | No
82 | REFX | Invoice register report | Report | SIT | Inprogress | Inprogress |  |  | Yes | Max
83 | REFX | Asset management contract process combined report | Report | SIT | Inprogress | Inprogress | Needs discussion with CTMs | Needs discussion with CTMs | No
84 | PP | BOM creation from upload tool | Conversion | Go Live | Completed | Inprogress | BOM upload Tool | added | Yes | ONX
85 | SD | Customer Master API required in SAP. | Interface | UAT | Completed | Completed | 85 and 87 can be covered in same program |  | Yes | ASG
86 | SD | Customer Master uploader required. | Conversion | Go Live | Completed | Completed | This should not be part of WRICEF list. This is a one time activity. | Need to discuss with Shrikant | Yes | ASG
87 | SD | Customer Master update API required. | Interface | UAT | Completed | Completed | Covered in 85 |  | No | No
88 | SD | Channel Partner Creation API required. | Interface | UAT | Completed | Completed |  |  | Yes | ASG
89 | SD | Open Booking uploader for legacy data required. | Conversion | Go Live | Completed | Completed | This should not be part of WRICEF list. | Need to discuss with Shrikant | Yes | ASG
90 | SD | Booking creation API required. | Interface | UAT | Completed | Completed |  |  | Yes | ASG
91 | SD | Land abetement required during boking process and pricing and tax calculate accordingly in SAP. | Enhancement | UAT | Completed | Completed | This should be covered under #113 | Need to discuss with Shrikant | Yes | ASG
92 | SD | Broker Payout Process. | Enhancement | UAT | Completed | Completed | Needs discussion with CTMs | Need to discuss with AP CTM Tapas | Yes | ASG
93 | SD | Create demand of open milestone | Interface | UAT | Not Started | Not Started |  |  | No | No
94 | SD | Legacy Demands uploader required. | Conversion | Go Live | Completed | Completed | This should not be part of WRICEF list. | Need to discuss with AP CTM Tapas | Yes | ASG
95 | SD | Credit Note API required. | Interface | UAT | Completed | Completed | 95 and 96 is merged |  | Yes | ASG
96 | SD | Debit Note API required. | Interface | UAT | Completed | Completed | This should be covered under 95 |  | Yes | ASG
97 | SD | Unit cancellation program required for GST reversal. | Enhancement | UAT | Completed | Completed | Discuss with Soum about impact on books | Discuss with Soum about impact on books | Yes | ASG
98 | SD | Scrap Invoice Printout required. | Form | Go Live | Not Started | Not Started | 98 and 101 is merged |  | No | No
99 | SD | Service Invoice Printout required | Form | Go Live | Completed | Completed | 99 and 102 is merged |  | No | No
100 | SD | Customer Service report required | Report | UAT | Inprogress | Inprogress | PMD |  | No | No
101 | SD | Asset Invoice Printout required | Form | Go Live | Not Started | Not Started | This should be covered under #98 in single smartform |  | No | No
102 | SD | STO / Intercompany Invoice Printout required | Form | UAT | Not Started | Not Started | This should be covered under #99 in single smartform |  | No | No
103 | SD | Export Invoice Printout | Form | UAT | Not Started | Not Started | Shipping note is required with export invoice | Need to discuss with @Prasanna Sir & @Ramya (TEMC) | No | No
104 | SD | Sales MIS / Sales Register required. | Report | Go Live | Not Started | Not Started | TEMC |  | No | No
105 | SD | E-Inovice Creation & Cancellation Integration with ClearTax | Interface | UAT | Completed | Completed |  |  | Yes | ASG
106 | SD | E-Way Bill Creation & Cancellation Integration with ClearTax | Interface | UAT | Completed | Completed | 106 and 107 is merged |  | Yes | ASG
107 | SD | Get E-Way Bill Printout from ClearTax | Interface | UAT | Completed | Completed | This should be covered under #107 |  | Yes | ASG
108 | SD | OC Concept Build for Bookings (New Added) | Enhancement | UAT | Completed | Completed |  | Object Added | No | No
109 | SD | PMD Job Work Estimate Printout (New Added) | Form | UAT | Completed | Completed |  | Object Added | No | No
110 | SD | Booking Update API (New Added) | Interface | UAT | Not Started | Not Started |  | Object Added | No | No
112 | PM | Interface with BMS system (Not in Scope) | Interface | Post Go Live | Not Started | Not Started |  | Added(Post Go-Live ) | No | No
113 | PS | Project structure WBS upload program | Conversion | Go Live | Completed | Inprogress | 144 & 143 is merged |  | Yes | ASG
114 | PS | Project Networks/Activity upload program | Conversion | Go Live | Completed | Inprogress | This should be along with #143 |  | Yes | ASG
115 | PS | Heirarchial Cost plan upload program | Conversion | Go Live | Completed | Inprogress | 145 & 146 is merged |  | Yes | ASG
116 | PS | Unit Cost Plan Upload Program | Conversion | Go Live | Completed | Inprogress | This should be along with #145. Need download option for cost plan. |  | No | No
117 | PS | Budget approval from CEO for Budget supplement & Internal HOD approval for Budget Transfer | Workflow | UAT | Completed | Inprogress |  | Priority to be moved to SIT | Yes | Bajel
118 | PS | Budget exceed mail trigger to the multiple users | Enhancement | UAT | Completed | Inprogress | Balance budget, % budget consumed report is required which will be emailed to users. Category will be report. |  | No | No
119 | PS | Quantity Validation for materials in project | Enhancement | UAT | Completed | Inprogress |  |  | No | No
120 | PS | Plan vs Actual Qty for material against work done | Report | UAT | Completed | Inprogress | This should be along with #148 | 148 & 150 is merged | No | No
121 | PS | Budget remaining percentage report | Report | UAT | Completed | Inprogress |  | Object Added | No | No

## WRICEF Pivot
Development Description. | .
Row Labels | Go Live | Post Go Live | SIT | UAT | Grand Total
FICO, CM | 17 | 4 | 1 | 17 | 39
MM | 10 | 5 | 7 | 5 | 27
PM |  | 1 | 1 | 2 | 4
PP | 1 |  |  |  | 1
PS | 4 |  |  | 4 | 8
REFX | 2 |  | 13 |  | 15
SD | 7 |  |  | 19 | 26
Grand Total | 41 | 10 | 22 | 47 | 120

## WRICEF Summary
Reusability | (ALL)
Count of Development Description | Priority
Module | Go Live | Post Go Live | SIT | UAT | Grand Total
FICO, CM | 17 | 4 | 1 | 17 | 39
MM | 10 | 5 | 7 | 5 | 27
PM |  | 1 | 1 | 2 | 4
PP | 1 |  |  |  | 1
PS | 4 |  |  | 5 | 9
REFX | 2 |  | 13 |  | 15
SD | 7 |  |  | 19 | 26
Grand Total | 41 | 10 | 22 | 48 | 121

## Revised Updated List (hidden)
SL No. | Module | Count of object submitted to Client | Object Added | Object Removed | Object Merged | Revised Count after Merged | Revised Count before Merged | Remarks
1 | FI | 50 | 0 | 15 | 4 | 31 | 35 | 8 Obj. merged in 4 Obj.
2 | REFX | 18 | 0 | 3 | 1 | 14 | 15 | 2 Obj. merged in 1 Obj.
3 | PM | 5 | 0 | 3 | 0 | 2 | 2 | Obj. merged 0
4 | SD | 36 | 0 | 13 | 5 | 18 | 23 | 10 Obj. merged in 5 Obj.
5 | MM | 30 | 0 | 3 | 3 | 24 | 27 | 6 Obj. merged in 3 Obj.
6 | PS | 8 | 1 | 0 | 3 | 6 | 9 | 6 Obj. merged in 3 Obj.
7 | PP | 3 | 0 | 2 | 0 | 1 | 1 | Obj. merged 0
|  | 150 | 1 | 39 | 16 | 96 | 112