## Project Plan Gantt Chart (hidden)
Raj Corporation Ltd Mainpuri Project Implementation Plan
[6 empty] | March |  | April |  | May |  | June |  | Jul |  | Aug |  | Sep |  | Oct
|  | Duration (Days) | Start | Finish | Responsibility | 0-15 | 16-31 | 0-15 | 16-30 | 0-15 | 16-31 | 0-15 | 16-30 | 0-15 | 16-31 | 0-15 | 16-31 | 0-15 | 16-30 | 0-15 | 16-31
| SAP Implementation at Raj Corporation Ltd | 208 | 2024-03-07 | 2024-09-30
Wave 1 | S4 HANA Private Clowd Implementation | 117 | 2024-03-07 | 2024-07-01
Implementation |  | 116 | 2024-03-08 | 2024-07-01
| Kick Off | 1 | 2024-03-08 | 2024-03-08 | HBT & RCL
Prepare |  | 6 | 2024-03-07 | 2024-03-12
| Project Plan | 1 | 2024-03-08 | 2024-03-08 | HBT
| Submit Project plan | 1 | 2024-03-08 | 2024-03-08 | HBT
| Apporval of project plan by RCL | 1 | 2024-03-08 | 2024-03-08 | RCL
| Submit initial Training Plan | 3 | 2024-03-11 | 2024-03-13 | HBT
| Prepare & Review Training plan | 1 | 2024-03-11 | 2024-03-11 | HBT
| Submit Training Plan | 1 | 2024-03-12 | 2024-03-12 | HBT
| Project preparation phase sign off by RCL | 1 | 2024-03-13 | 2024-03-13 | RCL & HBT
| Deliverables | 6 | 2024-03-08 | 2024-03-13 | HBT
D: | Baseline Project Plan | 1 | 2024-03-08 | 2024-03-08 | HBT
D: | Training Plan | 1 | 2024-03-12 | 2024-03-12 | HBT
D: | Phase Closure Document | 1 | 2024-03-12 | 2024-03-12 | HBT
Explore |  | 51 | 2024-03-08 | 2024-04-27
| Requirement gathering & Conceptual design | 8 | 2024-03-08 | 2024-03-15 | HBT
| Circulation of AS IS Template & Tree | 1 | 2024-03-09 | 2024-03-09 | HBT
| Preparation of AS IS Tree | 1 | 2024-03-11 | 2024-03-11 | HBT
| AS IS discussion & review | 4 | 2024-03-15 | 2024-03-18 | RCL & HBT
| Update AS IS document as per discussion | 4 | 2024-03-15 | 2024-03-18 | HBT
| Level 1 training - L1 | 2 | 2024-03-19 | 2024-03-20 | HBT
| Making necessary training preparation and Plan | 1 | 2024-03-12 | 2024-03-12 | HBT
| Conducting level-1 training (SAP Overview) | 1 | 2024-03-21 | 2024-03-21 | HBT
| Business Process definition | 4 | 2024-03-22 | 2024-03-25 | RCL & HBT
| Enterprise structure | 4 | 2024-03-22 | 2024-03-25 | RCL & HBT
| Define Org structure | 1 | 2024-03-22 | 2024-03-22 | HBT
| Review & discuss Org Structure with RCL | 1 | 2024-03-22 | 2024-03-22 | RCL & HBT
| Finalize & submit Org structure | 2 | 2024-03-22 | 2024-03-23 | HBT
| Sign off on Org structure by RCL | 1 | 2024-03-25 | 2024-03-25 | RCL
| Business Blueprint | 26 | 2024-03-26 | 2024-04-20 | HBT
| Prepare Business blueprint document & KDS | 7 | 2024-03-26 | 2024-04-01 | HBT
| Review Gap analysis, propose workaround, identify development list | 2 | 2024-04-02 | 2024-04-03 | HBT
| Submit BBP to Core Team | 1 | 2024-04-04 | 2024-04-04 | HBT
| Review BBP with Core Team | 3 | 2024-04-04 | 2024-04-06 | RCL & HBT
| Incorporate changes suggested | 2 | 2024-04-08 | 2024-04-09 | HBT
| Third Party Interface discussion | 4 | 2024-04-10 | 2024-04-13 | RCL & HBT
| Submit Integration document | 1 | 2024-04-13 | 2024-04-13 | RCL & HBT
| Submit final BBP | 2 | 2024-04-15 | 2024-04-16 | HBT
| BBP solution workshop for Management | 2 | 2024-04-17 | 2024-04-18 | RCL & HBT
| BBP sign off by RCL | 2 | 2024-04-19 | 2024-04-20 | RCL
| Completion of Business Blueprint Phase | 1 | 2024-04-20 | 2024-04-20 | RCL
| Master Data | 3 | 2024-04-22 | 2024-04-24 | RCL & HBT
| Identify master data requirement | 1 | 2024-04-22 | 2024-04-22 | HBT
| Prepare & explain master data template | 1 | 2024-04-23 | 2024-04-23 | HBT
| Circulate master data template | 1 | 2024-04-24 | 2024-04-24 | HBT
| SAP Cloud Server | 36 | 2024-03-26 | 2024-04-30 | RCL
Raj Corporation Ltd Mainpuri Project Implementation Plan
[6 empty] | March |  | April |  | May |  | June |  | Jul |  | Aug |  | Sep |  | Oct
| RCL | Duration (Days) | Start | Finish | Responsibility | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30
| SAP cloud server Availability | 21 | 2024-03-26 | 2024-04-15 | RCL
| SAP Server readiness | 15 | 2024-04-16 | 2024-04-30 | HBT
| Deliverables | 30 | 2024-03-26 | 2024-04-24 | HBT
D: | Business Blueprint with end to end process flow diagram, Gap Analysis | 2 | 2024-04-28 | 2024-04-29 | HBT
D: | Core team training/ presentation | 2 | 2024-03-28 | 2024-03-29 | HBT
D: | Initial Master data templates | 2 | 2024-03-28 | 2024-03-29 | HBT
D: | Wireframe document | 2 | 2024-03-28 | 2024-03-29 | HBT
D: | Database design document | 2 | 2024-03-28 | 2024-03-29 | HBT
D: | Phase Closure Document | 2 | 2024-03-28 | 2024-03-29 | HBT
Realize |  | 58 | 2024-04-04 | 2024-05-31
| Configure and Validate Baseline | 20 | 2024-04-15 | 2024-05-04 | HBT
| Configure Processes and Functions in golden master (100) | 20 | 2024-04-15 | 2024-05-04 | HBT
| Transfer of Configuration to Dev testing | 16 | 2024-04-19 | 2024-05-04 | HBT
| Unit testing-1 (Consultant) | 13 | 2024-04-22 | 2024-05-04 | HBT
| Document and Resolve Issues | 13 | 2024-04-22 | 2024-05-04 | HBT
| Submit Unit Testing result & completion of baseline configuration | 3 | 2024-05-04 | 2024-05-06 | HBT
| Identify scenerios for Integration test | 2 | 2024-05-06 | 2024-05-07 | HBT
| Write scripts for Integration test | 3 | 2024-05-08 | 2024-05-10 | HBT
| System Integration Test | 8 | 2024-05-11 | 2024-05-18 | HBT
| identify issues during SIT and Document | 8 | 2024-05-11 | 2024-05-18 | HBT
| Reslove issues identified during SIT | 4 | 2024-05-18 | 2024-05-21 | HBT
| UAT - Perform User Acceptance test - Core Team | 24 | 2024-05-22 | 2024-06-14 | RCL & HBT
| Resolving the issues, if any | 27 | 2024-05-22 | 2024-06-17 | HBT
| Re-UAT of identified issues | 5 | 2024-06-18 | 2024-06-22 | RCL & HBT
| UAT signoff | 32 | 2024-05-22 | 2024-06-22 | RCL
| Plan for Level-2 training (Core Team) | 1 | 2024-05-18 | 2024-05-18 | HBT
| Making necessery training arrangement - PPT + tutorial | 3 | 2024-05-20 | 2024-05-22 | HBT
| Conducting Level-2 Training (Module wise) | 3 | 2024-05-23 | 2024-05-25 | HBT
Developments | Finalize development tracker | 8 | 2024-03-25 | 2024-04-01
| Prepare RGS | 16 | 2024-03-26 | 2024-04-10 | HBT
| Submit of RGS | 4 | 2024-04-11 | 2024-04-14 | HBT
| Prepare functional specfications | 21 | 2024-04-15 | 2024-05-05 | HBT
| ABAP development & Develop reports | 61 | 2024-04-18 | 2024-06-17
| Weighbridge, Bank Integration, ASP/GSP, Payroll | 33 | 2024-05-02 | 2024-06-03 | HBT
| Testing by consultant | 62 | 2024-04-21 | 2024-06-21 | HBT
| Testing by Core Team | 60 | 2024-04-22 | 2024-06-20 | RCL
| Sign off Development | 60 | 2024-04-22 | 2024-06-20 | RCL
| Cutover Strategy | 12 | 2024-06-04 | 2024-06-15 | RCL & HBT
| Discussion on cutover strategy | 3 | 2024-06-04 | 2024-06-06 | RCL & HBT
| Cutover & data responsibility Plan | 5 | 2024-06-07 | 2024-06-11 | RCL & HBT
| Communication to Organisation for Cutover | 4 | 2024-06-12 | 2024-06-15 | RCL
| End user training plan | 1 | 2024-06-17 | 2024-06-17 | HBT
| Communicate plan to RCL | 1 | 2024-06-17 | 2024-06-17 | HBT
| Prepare end user training manual | 13 | 2024-06-06 | 2024-06-18 | HBT
| Conduct end user training | 8 | 2024-06-19 | 2024-06-26 | RCL & HBT
Raj Corporation Ltd Mainpuri Project Implementation Plan
[6 empty] | March |  | April |  | May |  | June |  | Jul |  | Aug |  | Sep |  | Oct
| RCL | Duration (Days) | Start | Finish | Responsibility | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30
| Conduct training to HODs/Management | 6 | 2024-06-26 | 2024-07-01 | RCL & HBT
| Production Environment Preparation | 8 | 2024-05-22 | 2024-05-29 | HBT
D: | Test Scripts | 1 | 2024-06-23 | 2024-06-23 | HBT
D: | Unit test result documentation | 1 | 2024-06-23 | 2024-06-23 | HBT
D: | Integration testing and detailed documentation | 1 | 2024-06-23 | 2024-06-23 | HBT
D: | Final Master data templates | 4 | 2024-05-31 | 2024-06-03 | HBT
D: | Data migration strategy | 1 | 2024-05-31 | 2024-05-31 | HBT
D: | Phase Closure Document | 1 | 2024-06-23 | 2024-06-23
Deploy |  | 38 | 2024-06-01 | 2024-07-08
| Transport final configurations | 1 | 2024-07-01 | 2024-07-01 | HBT
| Maintain number ranges | 2 | 2024-07-02 | 2024-07-03 | HBT
| Maintain client specific data | 2 | 2024-07-02 | 2024-07-03 | HBT
| User creation | 6 | 2024-05-20 | 2024-05-25 | HBT
| Finalize list of users for production enviornment | 3 | 2024-05-20 | 2024-05-22 | RCL & HBT
| Finalise Authorization Matrix | 1 | 2024-05-23 | 2024-05-23 | RCL & HBT
| Check roles and authorization | 3 | 2024-05-23 | 2024-05-25 | RCL & HBT
| Data preparation and upload | 26 | 2024-06-04 | 2024-06-29 | RCL & HBT
| Receipt of master data | 12 | 2024-06-04 | 2024-06-15 | RCL
| Validate & cleanse master data | 2 | 2024-06-17 | 2024-06-18 | RCL
| Upload master data in Production | 3 | 2024-06-18 | 2024-06-20 | HBT
| Confirm uploaded master data | 2 | 2024-06-20 | 2024-06-21 | RCL
| Receipt of cutover data | 1 | 2024-06-20 | 2024-06-20 | RCL
| Validate & cleanse cutover data | 3 | 2024-06-20 | 2024-06-22 | RCL
| Upload cutover data in production | 7 | 2024-06-23 | 2024-06-29 | HBT
| Check and validate uploaded data | 2 | 2024-07-01 | 2024-07-02 | RCL & HBT
| Black Out Period | 11 | 2024-06-20 | 2024-06-30 | RCL & HBT
| Deliverables | 73 | 2024-04-24 | 2024-07-05
D: | Training manual | 8 | 2024-05-20 | 2024-05-27 | HBT
D: | Data migration plan & checklist | 5 | 2024-06-07 | 2024-06-11 | HBT
D: | Master data upload programs | 3 | 2024-04-22 | 2024-04-24 | HBT
D: | Sample data upload validation | 4 | 2024-06-12 | 2024-06-15 | HBT
D: | Final SAP Authorization matrix | 1 | 2024-05-26 | 2024-05-26 | RCL & HBT
D: | Phase Closure Document | 1 | 2024-07-05 | 2024-07-05 | RCL
| Go Live | 1 | 2024-07-01 | 2024-07-01 | RCL & HBT
Run | Run & Post Go Live Stablization | 92 | 2024-07-01 | 2024-09-30
| Post Go live Stabilization | 24 | 2024-07-01 | 2024-09-30 | RCL & HBT
D: | Issue list with resolution status | 1 | 2024-09-30 | 2024-09-30 | HBT
D: | Configuration documents | 1 | 2024-09-30 | 2024-09-30 | HBT
D: | Functional & Technical Specifications | 1 | 2024-09-30 | 2024-09-30 | HBT
D: | Core team training document | 1 | 2024-09-30 | 2024-09-30 | HBT
Raj Corporation Ltd Mainpuri Project Implementation Plan
[6 empty] | March |  | April |  | May |  | June |  | Jul |  | Aug |  | Sep |  | Oct
| RCL | Duration (Days) | Start | Finish | Responsibility | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30 | 0-15 | 16-30
Wave 2 | Doclife solution implementation | 207 | 2024-03-08 | 2024-09-30
Prepare | Project Plan | 1 | 2024-03-08 | 2024-03-08 | HBT
| Submit Project plan | 1 | 2024-03-08 | 2024-03-08 | HBT
| Apporval of project plan by RCL | 1 | 2024-03-08 | 2024-03-08 | RCL
Explore |  |  | 2024-04-15 | 2024-04-30 | RCL & HBT
| AS IS and BBP finalization and Sign off | 16 | 2024-04-15 | 2024-04-30
Realize |  |  | 2024-05-01 | 2024-06-15 | RCL & HBT
| Configuration and Developments and UAT | 46 | 2024-05-01 | 2024-06-15
Deploy |  |  | 2024-06-15 | 2024-06-30 | HBT
| Production deployment | 16 | 2024-06-15 | 2024-06-30
Run |  |  | 2024-07-01 | 2024-09-30 | HBT
| Run & Post Go Live Stablization | 92 | 2024-07-01 | 2024-09-30
| Submitted by Received By |  |  | Reviewed by | [9 empty] | Reviewed & Accepted
| Akhilesh kumar Imran Raza |  |  | Ramji Goswami | [9 empty] | Project Manager / Project Director
| Program Manager - HBT CA - RCL |  |  | CA-RCL

## Project Plan
Raj Corporation Ltd Mainpuri Project Implementation Plan
|  |  | Duration (Days) | Planned Start | Planned Finish | Actual Start | Actual End | Responsibility
|  | SAP Implementation at Raj Corporation Ltd | 123 | 2024-03-07 | 2024-07-07 | 2024-03-07 | 2024-09-02
W1 | Wave 1 | S4 HANA Private Clowd Implementation | 117 | 2024-03-07 | 2024-07-01
| Implementation |  | 116 | 2024-03-08 | 2024-07-01 | 2024-03-07 | 2024-09-02
|  | Kick Off | 1 | 2024-03-08 | 2024-03-08 | 2024-03-09 | 2024-03-09 | HBT & RCL
| Prepare |  | 6 | 2024-03-07 | 2024-03-12
|  | Project Plan | 1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | HBT
|  | Submit Project plan | 1 | 2024-03-08 | 2024-03-08 | 2024-03-09 | 2024-03-09 | HBT
|  | Apporval of project plan by RCL | 1 | 2024-03-08 | 2024-03-08 | 2024-03-11 | 2024-03-11 | RCL
|  | Submit initial Training Plan | 3 | 2024-03-11 | 2024-03-13 | 2024-03-12 | 2024-03-12 | HBT
|  | Prepare & Review Training plan | 1 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | HBT
|  | Submit Training Plan | 1 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | HBT
|  | Project preparation phase sign off by RCL | 1 | 2024-03-13 | 2024-03-13 | 2024-03-09 | 2024-03-09 | RCL & HBT
|  | Deliverables | 6 | 2024-03-08 | 2024-03-13 |  |  | HBT
| D: | Baseline Project Plan | 1 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | HBT
| D: | Training Plan | 1 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | HBT
| D: | Phase Closure Document | 1 | 2024-03-12 | 2024-03-12 | 2024-03-11 | 2024-03-11 | HBT
| Explore |  | 51 | 2024-03-08 | 2024-04-27
|  | Requirement gathering & Conceptual design | 8 | 2024-03-08 | 2024-03-15 | 2024-03-11 | 2024-03-20 | HBT
|  | Circulation of AS IS Template & Tree | 1 | 2024-03-09 | 2024-03-09 | 2024-03-12 | 2024-03-12 | HBT
|  | Preparation of AS IS Tree | 1 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | HBT
|  | AS IS discussion & review | 4 | 2024-03-15 | 2024-03-18 | 2024-03-15 | 2024-03-22 | RCL & HBT
|  | Update AS IS document as per discussion | 4 | 2024-03-15 | 2024-03-18 | 2024-03-15 | 2024-03-22 | HBT
|  | Level 1 training - L1 | 2 | 2024-03-19 | 2024-03-20 | 2024-03-15 | 2024-03-15 | HBT
|  | Making necessary training preparation and Plan | 1 | 2024-03-12 | 2024-03-12 | 2024-03-13 | 2024-03-13 | HBT
|  | Conducting level-1 training (SAP Overview) | 1 | 2024-03-21 | 2024-03-21 | 2024-03-16 | 2024-03-16 | HBT
|  | Business Process definition | 4 | 2024-03-22 | 2024-03-25 | 2024-03-16 | 2024-03-23 | RCL & HBT
|  | Enterprise structure | 4 | 2024-03-22 | 2024-03-25 | 2024-03-31 | 2024-04-01 | RCL & HBT
|  | Define Org structure | 1 | 2024-03-22 | 2024-03-22 | 2024-03-31 | 2024-04-01 | HBT
|  | Review & discuss Org Structure with RCL | 1 | 2024-03-22 | 2024-03-22 | 2024-04-02 | 2024-04-03 | RCL & HBT
|  | Finalize & submit Org structure | 2 | 2024-03-22 | 2024-03-23 | 2024-04-08 | 2024-04-09 | HBT
|  | Sign off on Org structure by RCL | 1 | 2024-03-25 | 2024-03-25 | 2024-04-08 | 2024-04-09 | RCL
|  | Business Blueprint | 26 | 2024-03-26 | 2024-04-20 | 2024-04-06 | 2024-04-11 | HBT
|  | Prepare Business blueprint document & KDS | 7 | 2024-03-26 | 2024-04-01 | 2024-04-06 | 2024-04-11 | HBT
|  | Review Gap analysis, propose workaround, identify development list | 2 | 2024-04-02 | 2024-04-03 | 2024-04-06 | 2024-04-11 | HBT
|  | Submit BBP to Core Team | 1 | 2024-04-04 | 2024-04-04 | 2024-04-13 | 2024-04-13 | HBT
|  | Review BBP with Core Team | 3 | 2024-04-04 | 2024-04-06 | 2024-04-15 | 2024-04-20 | RCL & HBT
|  | Incorporate changes suggested | 2 | 2024-04-08 | 2024-04-09 | 2024-04-15 | 2024-04-20 | HBT
|  | Third Party Interface discussion | 4 | 2024-04-10 | 2024-04-13 | Pending | Pending | RCL & HBT
|  | Submit Integration document | 1 | 2024-04-13 | 2024-04-13 | Pending | Pending | RCL & HBT
|  | Submit final BBP | 2 | 2024-04-15 | 2024-04-16 | 2024-04-19 | 2024-04-20 | HBT
|  | BBP solution workshop for Management | 2 | 2024-04-17 | 2024-04-18 | 2024-04-22 | 2024-04-30 | RCL & HBT
|  | BBP sign off by RCL | 2 | 2024-04-19 | 2024-04-20 | 2024-04-22 | 2024-04-30 | RCL
|  | Completion of Business Blueprint Phase | 1 | 2024-04-20 | 2024-04-20 | 2024-04-22 | 2024-04-30 | RCL
|  | Master Data | 3 | 2024-04-22 | 2024-04-24 | 2024-04-22 | 2024-04-30 | RCL & HBT
|  | Identify master data requirement | 1 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-30 | HBT
|  | Prepare & explain master data template | 1 | 2024-04-23 | 2024-04-23 | 2024-04-22 | 2024-04-30 | HBT
|  | Circulate master data template | 1 | 2024-04-24 | 2024-04-24 | 2024-04-22 | 2024-04-30 | HBT
|  | SAP Cloud Server | 36 | 2024-03-26 | 2024-04-30 | 2024-04-22 | 2024-04-30 | RCL
|  | SAP cloud server Availability | 21 | 2024-03-26 | 2024-04-15 | 2024-04-22 | 2024-04-30 | RCL
|  | SAP Server readiness | 15 | 2024-04-16 | 2024-04-30 | 2024-04-22 | 2024-04-30 | HBT
|  | Deliverables | 30 | 2024-03-26 | 2024-04-24 | 2024-04-22 | 2024-04-30 | HBT
| D: | Business Blueprint with end to end process flow diagram, Gap Analysis | 2 | 2024-04-28 | 2024-04-29 | 2024-04-22 | 2024-04-30 | HBT
| D: | Core team training/ presentation | 2 | 2024-03-28 | 2024-03-29 | 2024-04-22 | 2024-04-30 | HBT
| D: | Initial Master data templates | 2 | 2024-03-28 | 2024-03-29 | 2024-04-22 | 2024-04-30 | HBT
| D: | Wireframe document | 2 | 2024-03-28 | 2024-03-29 | 2024-04-22 | 2024-04-30 | HBT
| D: | Database design document | 2 | 2024-03-28 | 2024-03-29 | 2024-04-22 | 2024-04-30 | HBT
| D: | Phase Closure Document | 2 | 2024-03-28 | 2024-03-29 | 2024-04-22 | 2024-04-30 | HBT
| Realize |  | 58 | 2024-04-04 | 2024-05-31
|  | Configure and Validate Baseline | 20 | 2024-04-15 | 2024-05-04 | 2024-05-01 | 2024-06-10 | HBT
|  | Configure Processes and Functions in golden master (100) | 20 | 2024-04-15 | 2024-05-04 | 2024-05-01 | 2024-06-10 | HBT
|  | Transfer of Configuration to Dev testing | 16 | 2024-04-19 | 2024-05-04 | 2024-05-15 | 2024-06-20 | HBT
|  | Unit testing-1 (Consultant) | 13 | 2024-04-22 | 2024-05-04 | 2024-05-01 | 2024-06-20 | HBT
|  | Document and Resolve Issues | 13 | 2024-04-22 | 2024-05-04 | 2024-05-01 | 2024-06-20 | HBT
|  | Submit Unit Testing result & completion of baseline configuration | 3 | 2024-05-04 | 2024-05-06 | 2024-06-20 | 2024-06-23 | HBT
|  | Identify scenerios for Integration test | 2 | 2024-05-06 | 2024-05-07 | 2024-06-24 | 2024-06-24 | HBT
|  | Write scripts for Integration test | 3 | 2024-05-08 | 2024-05-10 | 2024-06-25 | 2024-06-25 | HBT
|  | System Integration Test | 8 | 2024-05-11 | 2024-05-18 | 2024-06-26 | 2024-06-30 | HBT
|  | identify issues during SIT and Document | 8 | 2024-05-11 | 2024-05-18 | 2024-06-26 | 2024-06-30 | HBT
|  | Reslove issues identified during SIT | 4 | 2024-05-18 | 2024-05-21 | 2024-06-30 | 2024-07-03 | HBT
|  | UAT - Perform User Acceptance test - Core Team | 24 | 2024-05-22 | 2024-06-14 | 2024-07-20 | 2024-08-17 | RCL & HBT
|  | Resolving the issues, if any | 27 | 2024-05-22 | 2024-06-17 | 2024-07-20 | 2024-08-17 | HBT
|  | Re-UAT of identified issues | 5 | 2024-06-18 | 2024-06-22 | 2024-07-20 | 2024-08-17 | RCL & HBT
|  | UAT signoff | 32 | 2024-05-22 | 2024-06-22 | 2024-07-20 | 2024-08-17 | RCL
|  | Plan for Level-2 training (Core Team) | 1 | 2024-05-18 | 2024-05-18 | 2024-08-14 | 2024-08-17 | HBT
|  | Making necessery training arrangement - PPT + tutorial | 3 | 2024-05-20 | 2024-05-22 | 2024-08-14 | 2024-08-17 | HBT
|  | Conducting Level-2 Training (Module wise) | 3 | 2024-05-23 | 2024-05-25 | 2024-08-14 | 2024-08-17 | HBT
| Developments | Finalize development tracker | 8 | 2024-03-25 | 2024-04-01
|  | Prepare RGS | 16 | 2024-03-26 | 2024-04-10 | 2024-06-01 | 2024-06-30 | HBT
|  | Submit of RGS | 4 | 2024-04-11 | 2024-04-14 | 2024-06-01 | 2024-06-30 | HBT
|  | Prepare functional specfications | 21 | 2024-04-15 | 2024-05-05 | 2024-06-01 | 2024-06-30 | HBT
|  | ABAP Development & Develop reports | 61 | 2024-04-18 | 2024-06-17 | 2024-06-15 | 2024-07-15 | HBT
|  | Weighbridge, Bank Integration, ASP/GSP, Payroll | 33 | 2024-05-02 | 2024-06-03 | post go-live | post go-live | HBT
|  | Testing by consultant | 62 | 2024-04-21 | 2024-06-21 | 2024-06-15 | 2024-07-20 | HBT
|  | Testing by Core Team | 60 | 2024-04-22 | 2024-06-20 | 2024-07-09 | 2024-07-20 | RCL
|  | Sign off Development | 60 | 2024-04-22 | 2024-06-20 | 2024-07-20 | 2024-08-14 | RCL
|  | Cutover Strategy | 12 | 2024-06-04 | 2024-06-15 | 2024-07-20 | 2024-07-30 | RCL & HBT
|  | Discussion on cutover strategy | 3 | 2024-06-04 | 2024-06-06 | 2024-07-20 | 2024-07-31 | RCL & HBT
|  | Cutover & data responsibility Plan | 5 | 2024-06-07 | 2024-06-11 | 2024-07-20 | 2024-07-31 | RCL & HBT
|  | Communication to Organisation for Cutover | 4 | 2024-06-12 | 2024-06-15 | 2024-07-20 | 2024-07-31 | RCL
|  | End user training plan | 1 | 2024-06-17 | 2024-06-17 | 2024-07-20 | 2024-07-31 | HBT
|  | Communicate plan to RCL | 1 | 2024-06-17 | 2024-06-17 | 2024-07-20 | 2024-07-31 | HBT
|  | Prepare end user training manual | 13 | 2024-06-06 | 2024-06-18 | 2024-07-20 | 2024-07-31 | HBT
|  | Conduct end user training | 8 | 2024-06-19 | 2024-06-26 | 2024-07-20 | 2024-07-31 | RCL & HBT
|  | Conduct training to HODs/Management | 6 | 2024-06-26 | 2024-07-01 | 2024-07-20 | 2024-07-31 | RCL & HBT
|  | Production Environment Preparation | 8 | 2024-05-22 | 2024-05-29 | 2024-07-20 | 2024-07-31 | HBT
| D: | Test Scripts | 1 | 2024-06-23 | 2024-06-23 | 2024-07-20 | 2024-07-31 | HBT
| D: | Unit test result documentation | 1 | 2024-06-23 | 2024-06-23 | 2024-07-20 | 2024-07-31 | HBT
| D: | Integration testing and detailed documentation | 1 | 2024-06-23 | 2024-06-23 | 2024-07-20 | 2024-07-31 | HBT
| D: | Final Master data templates | 4 | 2024-05-31 | 2024-06-03 | 2024-07-20 | 2024-07-31 | HBT
| D: | Data migration strategy | 1 | 2024-05-31 | 2024-05-31 | 2024-07-20 | 2024-07-31 | HBT
| D: | Phase Closure Document | 1 | 2024-06-23 | 2024-06-23 | 2024-07-20 | 2024-07-31
| Deploy |  | 38 | 2024-06-01 | 2024-07-08
|  | Transport final configurations | 1 | 2024-07-01 | 2024-07-01 | 2024-08-25 | 2024-08-31 | HBT
|  | Maintain number ranges | 2 | 2024-07-02 | 2024-07-03 | 2024-08-25 | 2024-08-31 | HBT
|  | Maintain client specific data | 2 | 2024-07-02 | 2024-07-03 | 2024-08-25 | 2024-08-31 | HBT
|  | User creation | 6 | 2024-05-20 | 2024-05-25 | 2024-08-25 | 2024-08-31 | HBT
|  | Finalize list of users for production enviornment | 3 | 2024-05-20 | 2024-05-22 | 2024-08-15 | 2024-08-25 | RCL & HBT
|  | Finalise Authorization Matrix | 1 | 2024-05-23 | 2024-05-23 | 2024-08-15 | 2024-08-25 | RCL & HBT
|  | Check roles and authorization | 3 | 2024-05-23 | 2024-05-25 | 2024-08-15 | 2024-08-25 | RCL & HBT
|  | Data preparation and upload | 26 | 2024-06-04 | 2024-06-29 | 2024-08-25 | 2024-08-31 | RCL & HBT
|  | Receipt of master data | 12 | 2024-06-04 | 2024-06-15 | 2024-08-25 | 2024-08-31 | RCL
|  | Validate & cleanse master data | 2 | 2024-06-17 | 2024-06-18 | 2024-08-25 | 2024-08-31 | RCL
|  | Upload master data in Production | 3 | 2024-06-18 | 2024-06-20 | 2024-08-25 | 2024-08-31 | HBT
|  | Confirm uploaded master data | 2 | 2024-06-20 | 2024-06-21 | 2024-08-25 | 2024-08-31 | RCL
|  | Receipt of cutover data | 1 | 2024-06-20 | 2024-06-20 | 2024-08-25 | 2024-08-31 | RCL
|  | Validate & cleanse cutover data | 3 | 2024-06-20 | 2024-06-22 | 2024-08-25 | 2024-08-31 | RCL
|  | Upload cutover data in production | 7 | 2024-06-23 | 2024-06-29 | 2024-08-25 | 2024-08-31 | HBT
|  | Check and validate uploaded data | 2 | 2024-07-01 | 2024-07-02 | 2024-08-25 | 2024-08-31 | RCL & HBT
|  | Black Out Period | 11 | 2024-06-20 | 2024-06-30 | 2024-08-25 | 2024-09-01 | RCL & HBT
|  | Deliverables | 73 | 2024-04-24 | 2024-07-05
| D: | Training manual | 8 | 2024-05-20 | 2024-05-27 | 2024-08-05 | 2024-08-12 | HBT
| D: | Data migration plan & checklist | 5 | 2024-06-07 | 2024-06-11 | 2024-08-25 | 2024-09-01 | HBT
| D: | Master data upload programs | 3 | 2024-04-22 | 2024-04-24 | 2024-08-25 | 2024-09-01 | HBT
| D: | Sample data upload validation | 4 | 2024-06-12 | 2024-06-15 | 2024-08-25 | 2024-09-01 | HBT
| D: | Final SAP Authorization matrix | 1 | 2024-05-26 | 2024-05-26 | 2024-08-10 | 2024-08-25 | RCL & HBT
| D: | Phase Closure Document | 1 | 2024-07-05 | 2024-07-05 | 2024-08-10 | 2024-08-25 | RCL
|  | Go Live | 1 | 2024-07-01 | 2024-07-01 | 2024-08-15 | 2024-09-02 | RCL & HBT
| Run | Run & Post Go Live Stablization | 7 | 2024-07-01 | 2024-07-07 | 2024-08-10 | 2024-09-02
|  | Post Go live Stabilization | 24 | 2024-07-01 | 2024-07-07 | 2024-09-02 | 2024-09-09 | RCL & HBT
| D: | Issue list with resolution status | 1 | 2024-07-07 | 2024-07-07 | 2024-09-02 | 2024-09-09 | HBT
| D: | Configuration documents | 1 | 2024-07-07 | 2024-07-07 | 2024-09-02 | 2024-09-09 | HBT
| D: | Functional & Technical Specifications | 1 | 2024-07-07 | 2024-07-07 | 2024-09-02 | 2024-09-09 | HBT
| D: | Core team training document | 1 | 2024-07-07 | 2024-07-07 | 2024-09-02 | 2024-09-09 | HBT
W2 | Wave 2 | Doclife solution implementation | 122 | 2024-03-08 | 2024-07-07 | 2024-08-12 | 2024-08-31
| Prepare | Project Plan | 1 | 2024-03-08 | 2024-03-08 | 2024-08-12 | 2024-08-15 | HBT
|  | Submit Project plan | 1 | 2024-03-08 | 2024-03-08 | 2024-08-12 | 2024-08-15 | HBT
|  | Apporval of project plan by RCL | 1 | 2024-03-08 | 2024-03-08 | 2024-08-12 | 2024-08-15 | RCL
| Explore |  |  | 2024-04-15 | 2024-04-30 |  |  | RCL & HBT
|  | AS IS and BBP finalization and Sign off | 16 | 2024-04-15 | 2024-04-30 | 2024-08-16 | 2024-08-20
| Realize |  |  | 2024-05-01 | 2024-06-15 |  |  | RCL & HBT
|  | Configuration and Developments and UAT | 46 | 2024-05-01 | 2024-06-15 | 2024-08-20 | 2024-08-25
| Deploy |  |  | 2024-06-15 | 2024-06-30 |  |  | HBT
|  | Production deployment | 16 | 2024-06-15 | 2024-06-30 | 2024-08-25 | 2024-08-31
| Run |  |  | 2024-07-01 | 2024-09-30 |  |  | HBT
|  | Run & Post Go Live Stablization | 92 | 2024-07-01 | 2024-09-30 | 2024-09-01 | 2024-11-30
Formulas:
Planned Finish = [Planned Start]
Planned Finish = [Planned Finish, row above]
Actual Start = [Planned Finish]
Actual End = [Actual Start]
Planned Start = [Planned Start, row above]
Planned Start = [Planned Finish, row above]