## Sheet1
WBS | Task Name | Duration | Baseline Start | Baseline Finish | Start | Finish | Actual Start | Actual Finish | Predecessors | % Complete | Primery Responsibility | Core Team | HOD | Management | Status
1 | Rise with SAP S/4 HANA Private Cloud Implementation | 432 days | Fri 13-09-24 | Tue 07-04-26 | Fri 13-09-24 | Mon 11-05-26 | Fri 13-09-24 | NA |  | 12% |  |  |  |  | Future Task
1.1 | Wave 1A: SAP S/4 HANA Solutions Implementation: | 116 days | Wed 25-09-24 | Wed 05-03-25 | Wed 25-09-24 | Wed 05-03-25 | Fri 13-09-24 | NA |  | 29% |  |  |  |  | Future Task
1.1.1 | Prepare Phase | 14 days | Fri 13-09-24 | Wed 02-10-24 | Fri 13-09-24 | Wed 02-10-24 | Fri 13-09-24 | Wed 02-10-24 |  | 100% | HBT & DRAIPL | 100% | 10% | 5% | Complete
1.1.1.1 | Kick Off | 1 day | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 |  | 100% |  |  |  |  | Complete
1.1.1.1.1 | Prepare kickoff presentation in consultation with TE | 1 day | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 |  | 100% | HBT |  |  |  | Complete
1.1.1.1.2 | Review & finalize kickoff presentation | 1 day | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | 5 | 100% | DRAIPL | 100% | 10% | 5% | Complete
1.1.1.1.3 | Project Kick off with Key stakeholders | 1 day | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | 6FF | 100% | DRAIPL | 100% | 10% | 5% | Complete
1.1.1.2 | Project Plan | 4 days | Mon 16-09-24 | Thu 19-09-24 | Mon 16-09-24 | Thu 19-09-24 | Mon 16-09-24 | Thu 19-09-24 | 5SS | 100% |  |  |  |  | Complete
1.1.1.2.1 | Prepare & submit Initial project plan | 1 day | Mon 16-09-24 | Mon 16-09-24 | Mon 16-09-24 | Mon 16-09-24 | Mon 16-09-24 | Mon 16-09-24 |  | 100% | HBT | 100% |  |  | Complete
1.1.1.2.2 | Review project plan | 2 days | Mon 16-09-24 | Tue 17-09-24 | Mon 16-09-24 | Tue 17-09-24 | Mon 16-09-24 | Tue 17-09-24 | 9SS+1 day | 100% | DRAIPL | 100% | 10% |  | Complete
1.1.1.2.3 | Make necessary changes in the plan | 1 day | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | 10 | 100% | HBT |  |  | 5% | Complete
1.1.1.2.4 | Final submission of Project Plan | 1 day | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 |  | 100% | HBT |  |  | 5% | Complete
1.1.1.2.5 | Project Plan Signoff | 1 day | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 |  | 100% | DRAIPL |  |  |  | Complete
1.1.1.3 | SAP Onbaording | 9 days | Fri 13-09-24 | Wed 25-09-24 | Fri 13-09-24 | Wed 25-09-24 | Fri 13-09-24 | Wed 25-09-24 | 5SS | 100% |  |  |  | 5% | Complete
1.1.1.3.1 | SAP Onboarding | 1 day | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | Fri 13-09-24 | 5 | 100% | HBT |  |  |  | Complete
1.1.1.3.2 | Sharing S User ID with HBT Team | 1 day | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 |  | 100% | DRAIPL |  |  |  | Complete
1.1.1.4 | As-Is | 6 days | Tue 17-09-24 | Tue 24-09-24 | Tue 17-09-24 | Tue 24-09-24 | Tue 17-09-24 | Tue 24-09-24 |  | 100% |  |  |  |  | Complete
1.1.1.4.1 | Submit of As-Is Template | 1 day | Tue 17-09-24 | Tue 17-09-24 | Tue 17-09-24 | Tue 17-09-24 | Tue 17-09-24 | Tue 17-09-24 |  | 100% | HBT |  |  |  | Complete
1.1.1.4.2 | Preparation of AS-IS template by DRAIPL core team | 5 days | Wed 18-09-24 | Tue 24-09-24 | Wed 18-09-24 | Tue 24-09-24 | Wed 18-09-24 | Tue 24-09-24 |  | 100% | DRAIPL |  |  |  | Complete
1.1.1.5 | Mobilization of Team | 1 day | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 |  | 100% |  |  |  |  | Complete
1.1.1.5.1 | HBT Team mobilization | 1 day | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 |  | 100% | HBT |  |  |  | Complete
1.1.1.5.2 | DRAIPL team mobilization | 1 day | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 |  | 100% | DRAIPL |  |  |  | Complete
1.1.1.6 | Project Governance | 1 day | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 |  | 100% |  |  |  |  | Complete
1.1.1.6.1 | Finalize deliverable signoff matrix | 1 day | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 |  | 100% | HBT & DRAIPL | 100% | 10% | 5% | Complete
1.1.1.7 | Deliverables | 2 days | Wed 18-09-24 | Thu 19-09-24 | Wed 18-09-24 | Thu 19-09-24 | Wed 18-09-24 | Thu 19-09-24 |  | 100% |  |  |  |  | Complete
1.1.1.7.1 | D: Project Plan | 0 days | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | Thu 19-09-24 | 7 | 100% | HBT |  |  |  | Complete
1.1.1.7.2 | D: Kick off PPT | 0 days | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 | Wed 18-09-24 |  | 100% | HBT |  |  |  | Complete
1.1.1.8 | Key milestones | 3 days | Wed 25-09-24 | Fri 27-09-24 | Wed 25-09-24 | Fri 27-09-24 | Wed 25-09-24 | Fri 27-09-24 |  | 100% |  |  |  |  | Complete
1.1.1.8.1 | Prepare Phase Sign-off | 3 days | Wed 25-09-24 | Fri 27-09-24 | Wed 25-09-24 | Fri 27-09-24 | Wed 25-09-24 | Fri 27-09-24 |  | 100% | HBT & DRAIPL |  |  |  | Complete
1.1.2 | Explore Phase | 63 days | Wed 25-09-24 | Mon 11-11-24 | Wed 25-09-24 | Sun 22-12-24 | Wed 25-09-24 | NA |  | 83% | HBT & DRAIPL | 100% | 15% | 5% | Future Task
1.1.2.1 | Prerequisite | 0 days | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 |  | 100% |  |  |  |  | Complete
1.1.2.1.1 | Onboarding of OEM for Integration | 0 days | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 | Wed 25-09-24 |  | 100% | DRAIPL | 100% | 15% | 5% | Complete
1.1.2.2 | Requirement gathering | 3 days | Thu 26-09-24 | Mon 30-09-24 | Thu 26-09-24 | Mon 30-09-24 | Thu 26-09-24 | Mon 30-09-24 |  | 100% |  |  |  |  | Complete
1.1.2.2.1 | AS IS document walkthrough by DRAIPL | 3 days | Thu 26-09-24 | Mon 30-09-24 | Thu 26-09-24 | Mon 30-09-24 | Thu 26-09-24 | Mon 30-09-24 |  | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.3 | Level 1 training - L1 (SAP Overview) | 2 days | Tue 01-10-24 | Wed 02-10-24 | Tue 01-10-24 | Wed 02-10-24 | Tue 01-10-24 | Wed 02-10-24 |  | 100% |  |  |  |  | Complete
1.1.2.3.1 | Core Team Training Document | 1 day | Tue 01-10-24 | Tue 01-10-24 | Tue 01-10-24 | Tue 01-10-24 | Tue 01-10-24 | Tue 01-10-24 | 34 | 100% | HBT |  |  |  | Complete
1.1.2.3.2 | Conducting SAP Overview - L1 Training | 1 day | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | Wed 02-10-24 | 36 | 100% | HBT | 100% | 15% |  | Complete
1.1.2.4 | Business Process definition | 51 days | Thu 03-10-24 | Mon 11-11-24 | Fri 11-10-24 | Sun 22-12-24 | Fri 11-10-24 | Sun 22-12-24 |  | 100% |  |  |  |  | Complete
1.1.2.4.1 | Enterprise structure | 51 days | Thu 03-10-24 | Fri 11-10-24 | Fri 11-10-24 | Sun 22-12-24 | Fri 11-10-24 | Sun 22-12-24 |  | 100% |  |  |  |  | Complete
1.1.2.4.1.1 | Define Org structure | 3 days | Thu 03-10-24 | Fri 04-10-24 | Fri 11-10-24 | Tue 15-10-24 | Fri 11-10-24 | Tue 15-10-24 | 37 | 100% | HBT & DRAIPL | 100% | 15% |  | Complete
1.1.2.4.1.2 | Review & discuss Org Structure with Client | 4.5 days | Mon 07-10-24 | Tue 08-10-24 | Fri 11-10-24 | Sat 19-10-24 | Fri 11-10-24 | Sat 19-10-24 | 40 | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.4.1.3 | Incorporate changes suggested by Client | 18 days | Wed 09-10-24 | Wed 09-10-24 | Mon 21-10-24 | Wed 13-11-24 | Mon 21-10-24 | Wed 13-11-24 | 41 | 100% | HBT |  |  |  | Complete
1.1.2.4.1.4 | Workshop for As-Is and Org Structure | 27 days | Thu 10-10-24 | Thu 10-10-24 | Tue 15-10-24 | Sun 22-12-24 | Tue 15-10-24 | Sun 22-12-24 | 42 | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.4.1.5 | Sign off on Org structure | 0 days | Fri 11-10-24 | Fri 11-10-24 | Sat 07-12-24 | Sat 07-12-24 | Sat 07-12-24 | Sat 07-12-24 | 43 | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.4.2 | Business Blueprint | 46 days | Mon 07-10-24 | Mon 11-11-24 | Fri 11-10-24 | Sat 14-12-24 | Fri 11-10-24 | Sat 14-12-24 | 44SS | 100% |  |  |  |  | Complete
1.1.2.4.2.1 | Listing of end to end business process | 47 days | Mon 07-10-24 | Tue 08-10-24 | Fri 11-10-24 | Sat 14-12-24 | Fri 11-10-24 | Sat 14-12-24 |  | 100% | HBT | 100% |  |  | Complete
1.1.2.4.2.2 | Prepare Business blueprint document , KDS & Submit | 47 days | Wed 09-10-24 | Wed 23-10-24 | Fri 11-10-24 | Sat 14-12-24 | Fri 11-10-24 | Sat 14-12-24 | 46 | 100% | HBT | 100% | 15% |  | Complete
1.1.2.4.2.3 | Review & discuss BBP with CTM | 0 days | Thu 24-10-24 | Fri 01-11-24 | Sat 12-10-24 | Sat 14-12-24 | Sat 12-10-24 | Sat 14-12-24 | 47 | 100% | DRAIPL | 100% |  |  | Complete
1.1.2.4.2.4 | Review Gap analysis & propose workaround | 0 days | Thu 24-10-24 | Fri 25-10-24 | Sat 14-12-24 | Sat 14-12-24 | Sat 14-12-24 | Sat 14-12-24 | 48SS | 100% | HBT |  |  |  | Complete
1.1.2.4.2.5 | Identify development requirement | 0 days | Thu 24-10-24 | Fri 25-10-24 | Sat 14-12-24 | Sat 14-12-24 | Sat 14-12-24 | Sat 14-12-24 | 48SS | 100% | HBT & DRAIPL | 100% |  |  | Complete
1.1.2.4.2.6 | Finalize FRICE List | 5 days | Thu 24-10-24 | Fri 25-10-24 | Mon 09-12-24 | Sat 14-12-24 | Mon 09-12-24 | Sat 14-12-24 | 48SS | 100% | HBT & DRAIPL | 100% | 15% |  | Complete
1.1.2.4.2.7 | Prioritisation of FRICE objects (UAT, Go-lIve & Post Go-live) | 5 days | Thu 24-10-24 | Fri 25-10-24 | Mon 09-12-24 | Sat 14-12-24 | Mon 09-12-24 | Sat 14-12-24 | 51SS | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.4.2.8 | Acceptance of FRICE objects Prioritisation | 5 days | Thu 24-10-24 | Fri 25-10-24 | Mon 09-12-24 | Sat 14-12-24 | Mon 09-12-24 | Sat 14-12-24 | 51SS | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.4.2.9 | Incorporate changes suggested | 0 days | Mon 28-10-24 | Mon 28-10-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | 49 | 100% | HBT & DRAIPL |  | 15% |  | Complete
1.1.2.4.2.10 | Final Submission of BBP | 0 days | Mon 04-11-24 | Mon 04-11-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | 48 | 100% | HBT |  |  |  | Complete
1.1.2.4.2.11 | Prepare for Workshop | 0 days | Tue 05-11-24 | Wed 06-11-24 | Sat 07-12-24 | Sat 07-12-24 | Sat 07-12-24 | Sat 07-12-24 | 55 | 100% |  |  |  |  | Complete
1.1.2.4.2.12 | BBP solution workshop | 0 days | Thu 07-11-24 | Thu 07-11-24 | Sat 07-12-24 | Sat 07-12-24 | Sat 07-12-24 | Sat 07-12-24 | 56 | 100% | HBT |  |  | 5% | Complete
1.1.2.4.2.13 | BBP sign off | 5 days | Thu 07-11-24 | Mon 11-11-24 | Mon 09-12-24 | Sat 14-12-24 | Mon 09-12-24 | Sat 14-12-24 | 57SS | 100% | DRAIPL | 100% | 15% |  | Complete
1.1.2.5 | Third Party System Integration | 35 days | Thu 03-10-24 | Fri 25-10-24 | Fri 04-10-24 | Thu 21-11-24 | Fri 04-10-24 | NA |  | 41% |  |  |  |  | Future Task
1.1.2.5.1 | Onboarding of OEM for integration design finalization | 1 day | Thu 03-10-24 | Thu 03-10-24 | Fri 11-10-24 | Fri 11-10-24 | NA | NA | 40SS | 0% | DRAIPL | 100% | 15% |  | Future Task
1.1.2.5.2 | Receipt of Plan from Third Party Application Partner | 2 days | Thu 03-10-24 | Fri 04-10-24 | Fri 11-10-24 | Mon 14-10-24 | NA | NA | 40SS | 0% | DRAIPL | 100% | 15% |  | Future Task
1.1.2.5.3 | Alignment of the project plan with the TPA Plan | 1 day | Mon 07-10-24 | Mon 07-10-24 | Tue 15-10-24 | Tue 15-10-24 | NA | NA | 61 | 0% | DRAIPL | 100% | 15% |  | Future Task
1.1.2.5.4 | Intergration Touch points Discussion for Weighbridge | 6 days | Wed 09-10-24 | Fri 18-10-24 | Tue 05-11-24 | Tue 12-11-24 | Tue 05-11-24 | Tue 12-11-24 | 47SS | 100% | HBT & DRAIPL | 100% |  |  | Complete
1.1.2.5.5 | Intergration Touch points Discussion for Banks | 8 days | Wed 09-10-24 | Fri 18-10-24 | Tue 05-11-24 | Thu 14-11-24 | NA | NA | 63SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.2.5.6 | Intergration Touch points Discussion for LivSyt | 17 days | Wed 09-10-24 | Fri 18-10-24 | Fri 04-10-24 | Mon 04-11-24 | Fri 04-10-24 | Mon 04-11-24 | 63SS | 100% | HBT & DRAIPL | 100% |  |  | Complete
1.1.2.5.7 | Intergration Touch points Discussion for ASP/GSP | 8 days | Wed 09-10-24 | Fri 18-10-24 | Tue 05-11-24 | Thu 14-11-24 | NA | NA | 63SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.2.5.8 | Intergration Touch points Discussion for Payroll | 8 days | Wed 09-10-24 | Fri 18-10-24 | Tue 05-11-24 | Thu 14-11-24 | NA | NA | 63SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.2.5.9 | Integration Design Document | 2 days | Mon 21-10-24 | Tue 22-10-24 | Tue 22-10-24 | Mon 18-11-24 | Tue 22-10-24 | NA | 67 | 0% | HBT |  |  |  | Future Task
1.1.2.5.10 | Integration Design Document Sign Off | 3 days | Wed 23-10-24 | Fri 25-10-24 | Tue 19-11-24 | Thu 21-11-24 | NA | NA | 68 | 0% | DRAIPL | 100% | 15% |  | Future Task
1.1.2.6 | Master Data Statergy | 2 days | Fri 08-11-24 | Mon 11-11-24 | Mon 09-12-24 | Tue 10-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.2.6.1 | Identify master data requirement as per the BBP & Gaps | 2 days | Fri 08-11-24 | Mon 11-11-24 | Mon 09-12-24 | Tue 10-12-24 | NA | NA | 57 | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.2.6.2 | Prepare & explain master data template as per the BBP & Gaps | 2 days | Fri 08-11-24 | Mon 11-11-24 | Mon 09-12-24 | Tue 10-12-24 | NA | NA | 57 | 0% | HBT | 100% |  |  | Future Task
1.1.2.6.3 | Circulate master data template as per the BBP & Gaps | 2 days | Fri 08-11-24 | Mon 11-11-24 | Mon 09-12-24 | Tue 10-12-24 | NA | NA | 57 | 0% | HBT | 100% |  |  | Future Task
1.1.2.7 | Deliverables | 53 days | Tue 01-10-24 | Mon 11-11-24 | Tue 01-10-24 | Sat 14-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.2.7.1 | D: Business Blueprint with end to end Process flow diagram, Gap Analysis | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA | 58 | 0% | HBT | 100% | 15% |  | Future Task
1.1.2.7.2 | D: Core team training document - PPT | 0 days | Tue 01-10-24 | Tue 01-10-24 | Tue 01-10-24 | Tue 01-10-24 | NA | NA | 36 | 0% | HBT | 100% |  |  | Future Task
1.1.2.7.3 | D: Initial Master data templates | 0 days | Mon 11-11-24 | Mon 11-11-24 | Tue 10-12-24 | Tue 10-12-24 | NA | NA | 73 | 0% | HBT | 100% |  |  | Future Task
1.1.2.8 | Milestones | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.2.8.1 | Completion of Business Blueprint & Explore phase sign off | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA | 58 | 0% | HBT & DRAIPL | 100% | 15% |  | Future Task
1.1.3 | Realize | 63 days | Mon 11-11-24 | Thu 06-02-25 | Sat 14-12-24 | Wed 12-03-25 | NA | NA |  | 0% |  | 100% | 10% | 3% | Future Task
1.1.3.1 | Preqrequisite | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.1.1 | Availability of Development server for configuration | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA | 79 | 0% | DRAIPL |  |  |  | Future Task
1.1.3.1.2 | Availability of Third Party Vendor for Development API's | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA | 82 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.1.3 | Finalized list and availability of End user for training | 0 days | Mon 11-11-24 | Mon 11-11-24 | Sat 14-12-24 | Sat 14-12-24 | NA | NA | 82 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.2 | RGS & Functional Specifications(UAT & SIT Critical) | 5 days | Wed 13-11-24 | Tue 19-11-24 | Tue 17-12-24 | Mon 23-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.2.1 | RGS Preparation | 5 days | Wed 13-11-24 | Tue 19-11-24 | Tue 17-12-24 | Mon 23-12-24 | NA | NA | 79FS+1 day | 0% | HBT |  |  |  | Future Task
1.1.3.2.2 | RGS Acceptance/Approval | 5 days | Wed 13-11-24 | Tue 19-11-24 | Tue 17-12-24 | Mon 23-12-24 | NA | NA | 86SS | 0% | DRAIPL |  |  |  | Future Task
1.1.3.2.3 | Prepare functional specfications | 5 days | Wed 13-11-24 | Tue 19-11-24 | Tue 17-12-24 | Mon 23-12-24 | NA | NA | 87SS | 0% | HBT |  |  |  | Future Task
1.1.3.2.4 | Finalize development tracker | 5 days | Wed 13-11-24 | Tue 19-11-24 | Tue 17-12-24 | Mon 23-12-24 | NA | NA | 87SS | 0% | HBT |  |  |  | Future Task
1.1.3.3 | Configure and Validate Baseline | 8 days | Wed 20-11-24 | Fri 29-11-24 | Tue 24-12-24 | Thu 02-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.3.1 | Configure Processes and Functions in golden master (100) | 8 days | Wed 20-11-24 | Fri 29-11-24 | Tue 24-12-24 | Thu 02-01-25 | NA | NA | 89 | 0% | HBT |  |  |  | Future Task
1.1.3.3.2 | Transfer of Configuration to Dev testing | 8 days | Wed 20-11-24 | Fri 29-11-24 | Tue 24-12-24 | Thu 02-01-25 | NA | NA | 91SS | 0% | HBT |  |  |  | Future Task
1.1.3.3.3 | Unit testing-1 (Consultant) | 8 days | Wed 20-11-24 | Fri 29-11-24 | Tue 24-12-24 | Thu 02-01-25 | NA | NA | 91SS | 0% | HBT |  |  |  | Future Task
1.1.3.3.4 | Document and Resolve Issues | 8 days | Wed 20-11-24 | Fri 29-11-24 | Tue 24-12-24 | Thu 02-01-25 | NA | NA | 91SS | 0% | HBT |  |  |  | Future Task
1.1.3.3.5 | Verify Baseline Configuration Completion | 8 days | Wed 20-11-24 | Fri 29-11-24 | Tue 24-12-24 | Thu 02-01-25 | NA | NA | 91SS | 0% | HBT |  |  |  | Future Task
1.1.3.4 | Core team training & UT | 11 days | Mon 02-12-24 | Mon 16-12-24 | Fri 03-01-25 | Fri 17-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.4.1 | Plan for Level-2 training (CTM) | 1 day | Mon 02-12-24 | Mon 02-12-24 | Fri 03-01-25 | Fri 03-01-25 | NA | NA | 95 | 0% | HBT | 100% |  |  | Future Task
1.1.3.4.2 | Making necessery training arrangement - PPT + tutorial | 2 days | Tue 03-12-24 | Wed 04-12-24 | Mon 06-01-25 | Tue 07-01-25 | NA | NA | 97 | 0% | HBT | 100% |  |  | Future Task
1.1.3.4.3 | Conducting Level-2 Training (Module wise) | 8 days | Thu 05-12-24 | Mon 16-12-24 | Wed 08-01-25 | Fri 17-01-25 | NA | NA | 98 | 0% | HBT | 100% |  |  | Future Task
1.1.3.5 | ABAP Development - UAT & SIT critical | 50 days | Mon 18-11-24 | Fri 24-01-25 | Fri 20-12-24 | Thu 27-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.5.1 | FRICE Developments UAT & SIT critical | 38 days | Mon 18-11-24 | Wed 08-01-25 | Fri 20-12-24 | Tue 11-02-25 | NA | NA | 88SS+3 days | 0% | HBT |  |  |  | Future Task
1.1.3.5.2 | Testing by consultant | 38 days | Mon 25-11-24 | Wed 15-01-25 | Fri 27-12-24 | Tue 18-02-25 | NA | NA | 101SS+5 days | 0% | HBT |  |  |  | Future Task
1.1.3.5.3 | Testing by CTM | 5 days | Thu 16-01-25 | Wed 22-01-25 | Wed 19-02-25 | Tue 25-02-25 | NA | NA | 102 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.5.4 | Observations & Corrections | 5 days | Mon 20-01-25 | Fri 24-01-25 | Fri 21-02-25 | Thu 27-02-25 | NA | NA | 103SS+2 days | 0% |  |  |  |  | Future Task
1.1.3.5.5 | Sign off Development | 5 days | Mon 20-01-25 | Fri 24-01-25 | Fri 21-02-25 | Thu 27-02-25 | NA | NA | 104SS | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.6 | Third Party System Integration Development - SIT Critical | 45 days | Mon 18-11-24 | Fri 17-01-25 | Fri 20-12-24 | Thu 20-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.6.1 | Interface Development - Third Party Application | 38 days | Mon 18-11-24 | Wed 08-01-25 | Fri 20-12-24 | Tue 11-02-25 | NA | NA | 101SS | 0% | DRAIPL | 100% | 10% |  | Future Task
1.1.3.6.2 | Monitor Third Party Application development as per the plan | 38 days | Mon 18-11-24 | Wed 08-01-25 | Fri 20-12-24 | Tue 11-02-25 | NA | NA | 101SS | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.6.3 | Interface Development - SAP Side | 38 days | Mon 18-11-24 | Wed 08-01-25 | Fri 20-12-24 | Tue 11-02-25 | NA | NA | 101SS | 0% | HBT |  |  |  | Future Task
1.1.3.6.4 | Interface Testing by consultant & TPA Partners | 35 days | Mon 25-11-24 | Fri 10-01-25 | Fri 27-12-24 | Thu 13-02-25 | NA | NA | 109SS+5 days | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.3.6.5 | Interface Testing by CTM | 5 days | Mon 13-01-25 | Fri 17-01-25 | Fri 14-02-25 | Thu 20-02-25 | NA | NA | 110 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.6.6 | Sign off Development | 5 days | Mon 13-01-25 | Fri 17-01-25 | Fri 14-02-25 | Thu 20-02-25 | NA | NA | 110 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.7 | System Integration Test | 36 days | Mon 02-12-24 | Mon 20-01-25 | Fri 03-01-25 | Fri 21-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.7.1 | Integration testing plan | 5 days | Mon 02-12-24 | Fri 06-12-24 | Fri 03-01-25 | Thu 09-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.7.1.1 | Identify scenerios for Integration test | 3 days | Mon 02-12-24 | Wed 04-12-24 | Fri 03-01-25 | Tue 07-01-25 | NA | NA | 95 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.7.1.2 | Write scripts for Integration test | 3 days | Mon 02-12-24 | Wed 04-12-24 | Fri 03-01-25 | Tue 07-01-25 | NA | NA | 115SS | 0% | HBT |  |  |  | Future Task
1.1.3.7.1.3 | Integration Test Script Acceptance | 2 days | Thu 05-12-24 | Fri 06-12-24 | Wed 08-01-25 | Thu 09-01-25 | NA | NA | 116 | 0% | DRAIPL | 100% | 10% |  | Future Task
1.1.3.7.2 | Conduct System integration test | 8 days | Thu 09-01-25 | Mon 20-01-25 | Wed 12-02-25 | Fri 21-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.7.2.1 | Perform Integration testing by Consultant | 8 days | Thu 09-01-25 | Mon 20-01-25 | Wed 12-02-25 | Fri 21-02-25 | NA | NA | 109 | 0% | HBT |  |  |  | Future Task
1.1.3.8 | User Roles & Authorization | 10 days | Thu 05-12-24 | Wed 18-12-24 | Wed 08-01-25 | Tue 21-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.8.1 | Receipt of Final Authorization Matrix with User List | 5 days | Thu 05-12-24 | Wed 11-12-24 | Wed 08-01-25 | Tue 14-01-25 | NA | NA | 99SS | 0% | DRAIPL | 100% | 10% |  | Future Task
1.1.3.8.2 | Role Creation | 5 days | Thu 12-12-24 | Wed 18-12-24 | Wed 15-01-25 | Tue 21-01-25 | NA | NA | 121 | 0% | HBT |  |  |  | Future Task
1.1.3.8.3 | Role Testing & User assigning for UAT | 5 days | Thu 12-12-24 | Wed 18-12-24 | Wed 15-01-25 | Tue 21-01-25 | NA | NA | 122SS | 0% | HBT |  |  |  | Future Task
1.1.3.9 | Cutover Strategy | 4 days | Mon 09-12-24 | Thu 12-12-24 | Fri 10-01-25 | Wed 15-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.9.1 | Define cutover startegy with core team | 2 days | Mon 09-12-24 | Tue 10-12-24 | Fri 10-01-25 | Mon 13-01-25 | NA | NA | 117 | 0% | HBT & DRAIPL |  |  |  | Future Task
1.1.3.9.2 | Finalise cutover strategy with BPO's | 2 days | Wed 11-12-24 | Thu 12-12-24 | Tue 14-01-25 | Wed 15-01-25 | NA | NA | 125 | 0% | HBT & DRAIPL |  |  |  | Future Task
1.1.3.10 | User Acceptance Test - UAT | 11 days | Tue 21-01-25 | Tue 04-02-25 | Mon 24-02-25 | Mon 10-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.10.1 | Perform User Acceptance test - CTM | 8 days | Tue 21-01-25 | Thu 30-01-25 | Mon 24-02-25 | Wed 05-03-25 | NA | NA | 119 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.10.2 | Resolving the issues, if any | 8 days | Tue 21-01-25 | Thu 30-01-25 | Mon 24-02-25 | Wed 05-03-25 | NA | NA | 128SS | 0% | HBT |  |  |  | Future Task
1.1.3.10.3 | Retesting of scenarios | 3 days | Fri 31-01-25 | Tue 04-02-25 | Thu 06-03-25 | Mon 10-03-25 | NA | NA | 129 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.10.4 | UAT signoff | 3 days | Fri 31-01-25 | Tue 04-02-25 | Thu 06-03-25 | Mon 10-03-25 | NA | NA | 130SS | 0% | DRAIPL | 100% |  |  | Future Task
1.1.3.11 | End user training plan | 3 days | Thu 05-12-24 | Mon 09-12-24 | Wed 08-01-25 | Fri 10-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.11.1 | Preparation of End User training plan | 3 days | Thu 05-12-24 | Mon 09-12-24 | Wed 08-01-25 | Fri 10-01-25 | NA | NA | 99SS | 0% | HBT | 100% |  |  | Future Task
1.1.3.11.2 | Communicate plan | 3 days | Thu 05-12-24 | Mon 09-12-24 | Wed 08-01-25 | Fri 10-01-25 | NA | NA | 133SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.3.12 | Production Server Check/Setup | 2 days | Tue 21-01-25 | Wed 22-01-25 | Mon 24-02-25 | Tue 25-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.12.1 | Receipt of Production server | 1 day | Tue 21-01-25 | Tue 21-01-25 | Mon 24-02-25 | Mon 24-02-25 | NA | NA | 128SS,254SS | 0% | DRAIPL |  |  |  | Future Task
1.1.3.12.2 | Production server setup check | 2 days | Tue 21-01-25 | Wed 22-01-25 | Mon 24-02-25 | Tue 25-02-25 | NA | NA | 136SS | 0% | HBT |  |  |  | Future Task
1.1.3.13 | Deliverables | 49 days | Fri 29-11-24 | Thu 06-02-25 | Thu 02-01-25 | Wed 12-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.13.1 | D: Test Script | 0 days | Fri 29-11-24 | Fri 29-11-24 | Thu 02-01-25 | Thu 02-01-25 | NA | NA | 95 | 0% | HBT |  |  |  | Future Task
1.1.3.13.2 | D: Unit test result document | 0 days | Fri 29-11-24 | Fri 29-11-24 | Thu 02-01-25 | Thu 02-01-25 | NA | NA | 95 | 0% | HBT |  |  |  | Future Task
1.1.3.13.3 | D: Integration testing document | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 131257 | 0% | HBT |  |  |  | Future Task
1.1.3.13.4 | D: Final Master/Cutover Data template | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 131257 | 0% | HBT |  |  |  | Future Task
1.1.3.14 | Milestones | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.3.14.1 | Realization Phase Signoff | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 131257 | 0% | HBT & DRAIPL |  |  |  | Future Task
1.1.4 | Deploy | 20 days | Thu 06-02-25 | Wed 05-03-25 | Thu 06-02-25 | Wed 05-03-25 | NA | NA |  | 0% |  | 100% | 10% | 3% | Future Task
1.1.4.1 | Prerequisite | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.1.1 | End user training plan | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 144 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.1.2 | Availability of end users & Management for training | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 144 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.1.3 | Availability of Master data | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 144 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.1.4 | Availability of Cutover data | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 144 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.1.5 | User list & authorizations | 0 days | Thu 06-02-25 | Thu 06-02-25 | Wed 12-03-25 | Wed 12-03-25 | NA | NA | 144 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.2 | ABAP Development Go Live Critical | 18 days | Fri 07-02-25 | Tue 04-03-25 | Thu 13-03-25 | Mon 07-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.2.1 | Develop FRICE | 15 days | Fri 07-02-25 | Thu 27-02-25 | Thu 13-03-25 | Wed 02-04-25 | NA | NA | 131257 | 0% | HBT |  |  |  | Future Task
1.1.4.2.2 | Testing by consultant | 13 days | Tue 11-02-25 | Thu 27-02-25 | Mon 17-03-25 | Wed 02-04-25 | NA | NA | 153SS+2 days | 0% | HBT |  |  |  | Future Task
1.1.4.2.3 | Testing by CTM | 3 days | Fri 28-02-25 | Tue 04-03-25 | Thu 03-04-25 | Mon 07-04-25 | NA | NA | 154 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.2.4 | Sign off Development | 3 days | Fri 28-02-25 | Tue 04-03-25 | Thu 03-04-25 | Mon 07-04-25 | NA | NA | 155SS | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.3 | End User Training | 15 days | Fri 07-02-25 | Thu 27-02-25 | Thu 13-03-25 | Wed 02-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.3.1 | Prepare end user training manual | 4 days | Fri 07-02-25 | Wed 12-02-25 | Thu 13-03-25 | Tue 18-03-25 | NA | NA | 131257 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.3.2 | Conduct end user training | 11 days | Thu 13-02-25 | Thu 27-02-25 | Wed 19-03-25 | Wed 02-04-25 | NA | NA | 158 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.4 | Production Environment Preparation | 8 days | Thu 13-02-25 | Mon 24-02-25 | Wed 19-03-25 | Fri 28-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.4.1 | Transport final configurations | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 158274 | 0% | HBT |  |  |  | Future Task
1.1.4.4.2 | Maintain number ranges | 4 days | Wed 19-02-25 | Mon 24-02-25 | Tue 25-03-25 | Fri 28-03-25 | NA | NA | 161 | 0% | HBT |  |  |  | Future Task
1.1.4.4.3 | Maintain client specific data | 4 days | Wed 19-02-25 | Mon 24-02-25 | Tue 25-03-25 | Fri 28-03-25 | NA | NA | 162SS | 0% | HBT |  |  |  | Future Task
1.1.4.4.4 | Preparation of Production envoirnment by Third party OEM | 3 days | Wed 19-02-25 | Fri 21-02-25 | Tue 25-03-25 | Thu 27-03-25 | NA | NA | 161 | 0% | DRAIPL |  |  |  | Future Task
1.1.4.5 | User creation & authorization | 11 days | Thu 13-02-25 | Thu 27-02-25 | Wed 19-03-25 | Wed 02-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.5.1 | Finalize list of users for production enviornment | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 158274 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.5.2 | Finalise Authorization Matrix | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 166SS | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.5.3 | Create roles and authorization | 5 days | Wed 19-02-25 | Tue 25-02-25 | Tue 25-03-25 | Mon 31-03-25 | NA | NA | 167 | 0% | HBT |  |  |  | Future Task
1.1.4.5.4 | Test roles and authorization | 5 days | Fri 21-02-25 | Thu 27-02-25 | Thu 27-03-25 | Wed 02-04-25 | NA | NA | 168SS+2 days | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.4.6 | Data preparation & upload | 15 days | Thu 13-02-25 | Wed 05-03-25 | Wed 19-03-25 | Tue 08-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.6.1 | Receipt of master data | 1 day | Thu 13-02-25 | Thu 13-02-25 | Wed 19-03-25 | Wed 19-03-25 | NA | NA | 158 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.6.2 | Validate & cleanse master data | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 158 | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.6.3 | Upload master data in Production | 3 days | Wed 19-02-25 | Fri 21-02-25 | Tue 25-03-25 | Thu 27-03-25 | NA | NA | 172 | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.4.6.4 | Confirm uploaded master data | 3 days | Mon 24-02-25 | Wed 26-02-25 | Fri 28-03-25 | Tue 01-04-25 | NA | NA | 173 | 0% | DRAIPL | 100% | 10% |  | Future Task
1.1.4.6.5 | Receipt of cutover data | 4 days | Tue 25-02-25 | Fri 28-02-25 | Mon 31-03-25 | Thu 03-04-25 | NA | NA | 174SS+1 day | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.1.4.6.6 | Validate & cleanse cutover data | 4 days | Tue 25-02-25 | Fri 28-02-25 | Mon 31-03-25 | Thu 03-04-25 | NA | NA | 175SS | 0% | DRAIPL | 100% |  |  | Future Task
1.1.4.6.7 | Black Out Period | 3 days | Mon 03-03-25 | Wed 05-03-25 | Fri 04-04-25 | Tue 08-04-25 | NA | NA | 176 | 0% |  |  |  |  | Future Task
1.1.4.6.8 | Upload cutover data in production | 3 days | Mon 03-03-25 | Wed 05-03-25 | Fri 04-04-25 | Tue 08-04-25 | NA | NA | 176 | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.4.6.9 | Check and validate uploaded data | 3 days | Mon 03-03-25 | Wed 05-03-25 | Fri 04-04-25 | Tue 08-04-25 | NA | NA | 178SS | 0% | DRAIPL | 100% | 10% |  | Future Task
1.1.4.7 | Go-Live | 1 day | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.7.1 | Go-Live | 1 day | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA | 179 | 0% | DRAIPL |  |  |  | Future Task
1.1.4.8 | Establish Post Go-Live Support mechanism | 6 days | Fri 07-02-25 | Fri 14-02-25 | Thu 13-03-25 | Thu 20-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.8.1 | Setup Mechanism for tracking & monitoring of support | 2 days | Fri 07-02-25 | Mon 10-02-25 | Thu 13-03-25 | Fri 14-03-25 | NA | NA | 158SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.4.8.2 | Conduct training for end users for Support Mechanism | 2 days | Thu 13-02-25 | Fri 14-02-25 | Wed 19-03-25 | Thu 20-03-25 | NA | NA | 159SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.1.4.9 | Deliverables | 15 days | Wed 12-02-25 | Wed 05-03-25 | Tue 18-03-25 | Tue 08-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.9.1 | D: End user training manual | 0 days | Wed 12-02-25 | Wed 12-02-25 | Tue 18-03-25 | Tue 18-03-25 | NA | NA | 158274 | 0% | HBT |  |  |  | Future Task
1.1.4.9.2 | D: Data migration strategy document | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 179296 | 0% | HBT |  |  |  | Future Task
1.1.4.9.3 | D: Master data upload programs | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 179296 | 0% | HBT |  |  |  | Future Task
1.1.4.9.4 | D: Sample data upload validation | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 179296 | 0% | HBT |  |  |  | Future Task
1.1.4.9.5 | D: Final authorization matrix, roles & authorizations | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 179296 | 0% | HBT |  |  |  | Future Task
1.1.4.10 | Obtain Approval & phase Sign Off | 1 day | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.1.4.10.1 | Deploy Phae signoff | 1 day | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA | 181SS | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2 | Wave 1B,1D, 1E, 1F, 1G, 1H, 1I -SAP Solution rollout with Statutory Localization, Cash Mangement, Receivable Mangement, Group Reporting, Integration with Equipment tracking, Vendor Registration & Onboarding,SAP Digital Supplier Network | 106 days | Wed 13-11-24 | Thu 06-03-25 | Wed 13-11-24 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1 | Explore Phase | 16 days | Wed 13-11-24 | Wed 04-12-24 | Wed 13-11-24 | Wed 04-12-24 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 15% | 5% | Future Task
1.2.1.1 | Prerequisite | 0 days | Thu 14-11-24 | Thu 14-11-24 | Thu 14-11-24 | Thu 14-11-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.1.1 | Availability of Bank for Bank integration design finalization | 0 days | Thu 14-11-24 | Thu 14-11-24 | Thu 14-11-24 | Thu 14-11-24 | NA | NA | 5SS+45 days | 0% | DRAIPL | 100% | 15% | 5% | Future Task
1.2.1.2 | Requirement gathering | 2 days | Wed 13-11-24 | Thu 14-11-24 | Wed 13-11-24 | Thu 14-11-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.2.1 | Delta requirement gathering for country specific localization | 2 days | Wed 13-11-24 | Thu 14-11-24 | Wed 13-11-24 | Thu 14-11-24 | NA | NA | 5SS+43 days | 0% | DRAIPL | 100% | 15% |  | Future Task
1.2.1.2.2 | Requirement Gathering for additonal components | 2 days | Wed 13-11-24 | Thu 14-11-24 | Wed 13-11-24 | Thu 14-11-24 | NA | NA | 198SS | 0% | HBT |  |  |  | Future Task
1.2.1.3 | Business Process definition | 14 days | Thu 14-11-24 | Tue 03-12-24 | Thu 14-11-24 | Tue 03-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.3.1 | Business Blueprint | 14 days | Thu 14-11-24 | Tue 03-12-24 | Thu 14-11-24 | Tue 03-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.3.1.1 | Listing of Process for additional components | 11 days | Thu 14-11-24 | Thu 28-11-24 | Thu 14-11-24 | Thu 28-11-24 | NA | NA | 198SS+1 day | 0% | HBT | 100% |  |  | Future Task
1.2.1.3.1.2 | Review & discuss localization & statutary document | 1 day | Fri 29-11-24 | Fri 29-11-24 | Fri 29-11-24 | Fri 29-11-24 | NA | NA | 202 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.1.3.1.3 | Incorporate changes suggested | 1 day | Mon 02-12-24 | Mon 02-12-24 | Mon 02-12-24 | Mon 02-12-24 | NA | NA | 203 | 0% | HBT |  |  |  | Future Task
1.2.1.3.1.4 | Delta BBP for Localization sign off | 2 days | Mon 02-12-24 | Tue 03-12-24 | Mon 02-12-24 | Tue 03-12-24 | NA | NA | 203 | 0% | DRAIPL | 100% | 15% |  | Future Task
1.2.1.3.1.5 | BBP sign of for additional components | 2 days | Mon 02-12-24 | Tue 03-12-24 | Mon 02-12-24 | Tue 03-12-24 | NA | NA | 203 | 0% | DRAIPL |  |  |  | Future Task
1.2.1.4 | Third Party System Integration | 6 days | Thu 14-11-24 | Thu 21-11-24 | Thu 14-11-24 | Thu 21-11-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.4.1 | Intergration Touch points Discussion for Bank & other related component | 2 days | Thu 14-11-24 | Fri 15-11-24 | Thu 14-11-24 | Fri 15-11-24 | NA | NA | 202SS | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.2.1.4.2 | Integration Design Document | 2 days | Mon 18-11-24 | Tue 19-11-24 | Mon 18-11-24 | Tue 19-11-24 | NA | NA | 208 | 0% | HBT |  |  |  | Future Task
1.2.1.4.3 | Integration Design Document Sign Off | 2 days | Wed 20-11-24 | Thu 21-11-24 | Wed 20-11-24 | Thu 21-11-24 | NA | NA | 209 | 0% | DRAIPL | 100% | 15% |  | Future Task
1.2.1.5 | Deliverables | 1 day | Tue 03-12-24 | Wed 04-12-24 | Tue 03-12-24 | Wed 04-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.5.1 | D: Business Blueprint with end to end Process flow diagram, FRICE List | 0 days | Tue 03-12-24 | Tue 03-12-24 | Tue 03-12-24 | Tue 03-12-24 | NA | NA | 205 | 0% | HBT | 100% | 15% |  | Future Task
1.2.1.5.2 | D: Initial Master data templates | 0 days | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | NA | NA | 205FS+1 day | 0% | HBT | 100% |  |  | Future Task
1.2.1.6 | Milestones | 0 days | Tue 03-12-24 | Tue 03-12-24 | Tue 03-12-24 | Tue 03-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.1.6.1 | Completion of Business Blueprint Explore phase sign off | 0 days | Tue 03-12-24 | Tue 03-12-24 | Tue 03-12-24 | Tue 03-12-24 | NA | NA | 205 | 0% | HBT & DRAIPL | 100% | 15% |  | Future Task
1.2.2 | Realize | 72 days | Mon 02-12-24 | Tue 11-02-25 | Thu 05-12-24 | Mon 17-03-25 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 10% | 3% | Future Task
1.2.2.1 | Preqrequisite | 0 days | Thu 05-12-24 | Thu 05-12-24 | Thu 05-12-24 | Thu 05-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.1.1 | Availability of Third Party Vendor for Development API's | 0 days | Thu 05-12-24 | Thu 05-12-24 | Thu 05-12-24 | Thu 05-12-24 | NA | NA | 213FS+1 day | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.1.2 | Finalized list and availability of End user for training | 0 days | Thu 05-12-24 | Thu 05-12-24 | Thu 05-12-24 | Thu 05-12-24 | NA | NA | 213FS+1 day | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.2 | RGS & Functional Specifications(UAT & SIT Critical) | 10 days | Fri 06-12-24 | Thu 19-12-24 | Fri 06-12-24 | Thu 19-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.2.1 | RGS Preparation | 10 days | Fri 06-12-24 | Thu 19-12-24 | Fri 06-12-24 | Thu 19-12-24 | NA | NA | 218 | 0% | HBT |  |  |  | Future Task
1.2.2.2.2 | RGS Acceptance/Approval | 5 days | Fri 06-12-24 | Thu 12-12-24 | Fri 06-12-24 | Thu 12-12-24 | NA | NA | 221SS | 0% | DRAIPL |  |  |  | Future Task
1.2.2.2.3 | Prepare functional specfications | 10 days | Fri 06-12-24 | Thu 19-12-24 | Fri 06-12-24 | Thu 19-12-24 | NA | NA | 222SS | 0% | HBT |  |  |  | Future Task
1.2.2.2.4 | Finalize development tracker | 5 days | Fri 06-12-24 | Thu 12-12-24 | Fri 06-12-24 | Thu 12-12-24 | NA | NA | 222SS | 0% | HBT |  |  |  | Future Task
1.2.2.3 | Configure and Validate Baseline | 13 days | Fri 13-12-24 | Tue 31-12-24 | Fri 13-12-24 | Tue 31-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.3.1 | Configure Processes and Functions in golden master (100) | 5 days | Fri 13-12-24 | Thu 19-12-24 | Fri 13-12-24 | Thu 19-12-24 | NA | NA | 224 | 0% | HBT |  |  |  | Future Task
1.2.2.3.2 | Transfer of Configuration to Dev testing | 5 days | Fri 13-12-24 | Thu 19-12-24 | Fri 13-12-24 | Thu 19-12-24 | NA | NA | 226SS | 0% | HBT |  |  |  | Future Task
1.2.2.3.3 | Unit testing-1 (Consultant) | 4 days | Fri 20-12-24 | Wed 25-12-24 | Fri 20-12-24 | Wed 25-12-24 | NA | NA | 227 | 0% | HBT |  |  |  | Future Task
1.2.2.3.4 | Document and Resolve Issues | 4 days | Fri 20-12-24 | Wed 25-12-24 | Fri 20-12-24 | Wed 25-12-24 | NA | NA | 228SS | 0% | HBT |  |  |  | Future Task
1.2.2.3.5 | Verify Baseline Configuration Completion | 4 days | Fri 20-12-24 | Wed 25-12-24 | Fri 20-12-24 | Wed 25-12-24 | NA | NA | 228SS | 0% | HBT |  |  |  | Future Task
1.2.2.3.6 | Core Team Training | 2 days | Thu 26-12-24 | Fri 27-12-24 | Thu 26-12-24 | Fri 27-12-24 | NA | NA | 230 | 0% | HBT |  |  |  | Future Task
1.2.2.3.7 | UT by Core Team | 2 days | Mon 30-12-24 | Tue 31-12-24 | Mon 30-12-24 | Tue 31-12-24 | NA | NA | 231 | 0% | DRAIPL |  |  |  | Future Task
1.2.2.4 | ABAP Development - UAT & SIT critical | 37 days | Wed 11-12-24 | Thu 30-01-25 | Fri 20-12-24 | Mon 10-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.4.1 | FRICE Developments SIT critical | 25 days | Wed 11-12-24 | Tue 14-01-25 | Fri 20-12-24 | Thu 23-01-25 | NA | NA | 88SS+3 days,223SS+3 days | 0% | HBT |  |  |  | Future Task
1.2.2.4.2 | Testing by consultant | 25 days | Wed 18-12-24 | Tue 21-01-25 | Fri 27-12-24 | Thu 30-01-25 | NA | NA | 234SS+5 days | 0% | HBT |  |  |  | Future Task
1.2.2.4.3 | Testing by CTM | 5 days | Wed 22-01-25 | Tue 28-01-25 | Fri 31-01-25 | Thu 06-02-25 | NA | NA | 235 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.4.4 | Observations & Corrections | 5 days | Fri 24-01-25 | Thu 30-01-25 | Tue 04-02-25 | Mon 10-02-25 | NA | NA | 236SS+2 days | 0% |  |  |  |  | Future Task
1.2.2.4.5 | Sign off Development | 5 days | Fri 24-01-25 | Thu 30-01-25 | Tue 04-02-25 | Mon 10-02-25 | NA | NA | 237SS | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.5 | Third Party System Integration Development - Bank | 20 days | Wed 15-01-25 | Tue 11-02-25 | Fri 24-01-25 | Thu 20-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.5.1 | Interface Development - Third Party Application | 15 days | Wed 15-01-25 | Tue 04-02-25 | Fri 24-01-25 | Thu 13-02-25 | NA | NA | 233SS+25 days | 0% | HBT |  |  |  | Future Task
1.2.2.5.2 | Interface Testing by consultant | 5 days | Wed 05-02-25 | Tue 11-02-25 | Fri 14-02-25 | Thu 20-02-25 | NA | NA | 240 | 0% | HBT |  |  |  | Future Task
1.2.2.6 | System Integration Test | 35 days | Mon 02-12-24 | Fri 17-01-25 | Fri 03-01-25 | Thu 20-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.6.1 | Integration testing plan | 5 days | Mon 02-12-24 | Fri 06-12-24 | Fri 03-01-25 | Thu 09-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.6.1.1 | Identify scenerios for Integration test | 3 days | Mon 02-12-24 | Wed 04-12-24 | Fri 03-01-25 | Tue 07-01-25 | NA | NA | 95 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.6.1.2 | Write scripts for Integration test | 3 days | Mon 02-12-24 | Wed 04-12-24 | Fri 03-01-25 | Tue 07-01-25 | NA | NA | 244SS | 0% | HBT |  |  |  | Future Task
1.2.2.6.1.3 | Integration Test Script Acceptance | 2 days | Thu 05-12-24 | Fri 06-12-24 | Wed 08-01-25 | Thu 09-01-25 | NA | NA | 245 | 0% | DRAIPL | 100% | 10% |  | Future Task
1.2.2.6.2 | Conduct System integration test | 7 days | Thu 09-01-25 | Fri 17-01-25 | Wed 12-02-25 | Thu 20-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.6.2.1 | Perform Integration testing by Consultant | 7 days | Thu 09-01-25 | Fri 17-01-25 | Wed 12-02-25 | Thu 20-02-25 | NA | NA | 109 | 0% | HBT |  |  |  | Future Task
1.2.2.7 | User Roles & Authorization | 10 days | Thu 05-12-24 | Wed 18-12-24 | Wed 08-01-25 | Tue 21-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.7.1 | Receipt of Final Authorization Matrix with User List | 5 days | Thu 05-12-24 | Wed 11-12-24 | Wed 08-01-25 | Tue 14-01-25 | NA | NA | 99SS | 0% | DRAIPL | 100% | 10% |  | Future Task
1.2.2.7.2 | Role Creation | 5 days | Thu 12-12-24 | Wed 18-12-24 | Wed 15-01-25 | Tue 21-01-25 | NA | NA | 250 | 0% | HBT |  |  |  | Future Task
1.2.2.7.3 | Role Testing & User assigning for UAT | 5 days | Thu 12-12-24 | Wed 18-12-24 | Wed 15-01-25 | Tue 21-01-25 | NA | NA | 251SS | 0% | HBT & DRAIPL |  |  |  | Future Task
1.2.2.8 | User Acceptance Test - UAT | 14 days | Mon 20-01-25 | Thu 06-02-25 | Fri 21-02-25 | Wed 12-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.8.1 | Perform User Acceptance test - CTM | 10 days | Mon 20-01-25 | Fri 31-01-25 | Fri 21-02-25 | Thu 06-03-25 | NA | NA | 248 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.8.2 | Resolving the issues, if any | 10 days | Mon 20-01-25 | Fri 31-01-25 | Fri 21-02-25 | Thu 06-03-25 | NA | NA | 254SS | 0% | HBT |  |  |  | Future Task
1.2.2.8.3 | Retesting of scenarios | 4 days | Mon 03-02-25 | Thu 06-02-25 | Fri 07-03-25 | Wed 12-03-25 | NA | NA | 255 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.8.4 | UAT signoff | 4 days | Mon 03-02-25 | Thu 06-02-25 | Fri 07-03-25 | Wed 12-03-25 | NA | NA | 256SS | 0% | DRAIPL | 100% |  |  | Future Task
1.2.2.9 | End user training plan | 3 days | Fri 07-02-25 | Tue 11-02-25 | Thu 13-03-25 | Mon 17-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.9.1 | Preparation of End User training plan & Submit | 3 days | Fri 07-02-25 | Tue 11-02-25 | Thu 13-03-25 | Mon 17-03-25 | NA | NA | 257 | 0% | HBT | 100% |  |  | Future Task
1.2.2.10 | Deliverables | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.10.1 | D: Test Script | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 257FS+1 day | 0% | HBT |  |  |  | Future Task
1.2.2.10.2 | D: Unit test result document | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 261SS | 0% | HBT |  |  |  | Future Task
1.2.2.10.3 | D: Integration testing document | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 261SS | 0% | HBT |  |  |  | Future Task
1.2.2.10.4 | D: Cutover Data template | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 261SS | 0% | HBT |  |  |  | Future Task
1.2.2.11 | Milestones | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.2.11.1 | Realization Phase Signoff | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 264 | 0% | DRAIPL |  |  |  | Future Task
1.2.3 | Deploy | 19 days | Fri 07-02-25 | Thu 06-03-25 | Thu 13-03-25 | Wed 09-04-25 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.1 | Prerequisite | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.1.1 | Availability of end users & Management for training | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 266 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.1.2 | Availability of Master data | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 266 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.1.3 | Availability of Cutover data | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 266 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.1.4 | User list & authorizations | 0 days | Fri 07-02-25 | Fri 07-02-25 | Thu 13-03-25 | Thu 13-03-25 | NA | NA | 266 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.2 | End User Training | 7 days | Mon 10-02-25 | Tue 18-02-25 | Fri 14-03-25 | Mon 24-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.2.1 | Prepare end user training manual | 2 days | Mon 10-02-25 | Tue 11-02-25 | Fri 14-03-25 | Mon 17-03-25 | NA | NA | 259SS+1 day | 0% | DRAIPL | 100% |  |  | Future Task
1.2.3.2.2 | Conduct end user training | 5 days | Wed 12-02-25 | Tue 18-02-25 | Tue 18-03-25 | Mon 24-03-25 | NA | NA | 274 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.3.3 | Production Environment Preparation | 8 days | Thu 13-02-25 | Mon 24-02-25 | Wed 19-03-25 | Fri 28-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.3.1 | Transport final configurations | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 158274 | 0% | HBT |  |  |  | Future Task
1.2.3.3.2 | Maintain number ranges | 4 days | Wed 19-02-25 | Mon 24-02-25 | Tue 25-03-25 | Fri 28-03-25 | NA | NA | 277 | 0% | HBT |  |  |  | Future Task
1.2.3.3.3 | Maintain client specific data | 4 days | Wed 19-02-25 | Mon 24-02-25 | Tue 25-03-25 | Fri 28-03-25 | NA | NA | 278SS | 0% | HBT |  |  |  | Future Task
1.2.3.3.4 | Production envoirnment to be ready by TPA - OEM | 3 days | Wed 19-02-25 | Fri 21-02-25 | Tue 25-03-25 | Thu 27-03-25 | NA | NA | 277 | 0% | DRAIPL |  |  |  | Future Task
1.2.3.4 | User creation & authorization | 11 days | Thu 13-02-25 | Thu 27-02-25 | Wed 19-03-25 | Wed 02-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.4.1 | Finalize list of users for production enviornment | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 158274 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.4.2 | Finalise Authorization Matrix | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 282SS | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.4.3 | Create roles and authorization | 5 days | Wed 19-02-25 | Tue 25-02-25 | Tue 25-03-25 | Mon 31-03-25 | NA | NA | 283 | 0% | HBT |  |  |  | Future Task
1.2.3.4.4 | Test roles and authorization | 5 days | Fri 21-02-25 | Thu 27-02-25 | Thu 27-03-25 | Wed 02-04-25 | NA | NA | 284SS+2 days | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.2.3.5 | Data preparation & upload | 16 days | Thu 13-02-25 | Thu 06-03-25 | Wed 19-03-25 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.5.1 | Data Migration Statergy | 1 day | Thu 13-02-25 | Thu 13-02-25 | Wed 19-03-25 | Wed 19-03-25 | NA | NA | 158 | 0% | HBT |  |  |  | Future Task
1.2.3.5.2 | Receipt of master data | 1 day | Thu 13-02-25 | Thu 13-02-25 | Wed 19-03-25 | Wed 19-03-25 | NA | NA | 158 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.5.3 | Validate & cleanse master data | 4 days | Thu 13-02-25 | Tue 18-02-25 | Wed 19-03-25 | Mon 24-03-25 | NA | NA | 158 | 0% | DRAIPL | 100% |  |  | Future Task
1.2.3.5.4 | Upload master data in Production | 3 days | Wed 19-02-25 | Fri 21-02-25 | Tue 25-03-25 | Thu 27-03-25 | NA | NA | 172 | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.2.3.5.5 | Confirm uploaded master data | 3 days | Mon 24-02-25 | Wed 26-02-25 | Fri 28-03-25 | Tue 01-04-25 | NA | NA | 173 | 0% | DRAIPL | 100% | 10% |  | Future Task
1.2.3.5.6 | Receipt of cutover data | 4 days | Tue 25-02-25 | Fri 28-02-25 | Mon 31-03-25 | Thu 03-04-25 | NA | NA | 174SS+1 day | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.5.7 | Validate & cleanse cutover data | 4 days | Tue 25-02-25 | Fri 28-02-25 | Mon 31-03-25 | Thu 03-04-25 | NA | NA | 175SS | 0% | DRAIPL | 100% |  |  | Future Task
1.2.3.5.8 | Black Out Period | 4 days | Mon 03-03-25 | Thu 06-03-25 | Fri 04-04-25 | Wed 09-04-25 | NA | NA | 176 | 0% | DRAIPL |  |  |  | Future Task
1.2.3.5.9 | Upload cutover data in production | 4 days | Mon 03-03-25 | Thu 06-03-25 | Fri 04-04-25 | Wed 09-04-25 | NA | NA | 176 | 0% | HBT & DRAIPL | 100% |  |  | Future Task
1.2.3.5.10 | Check and validate uploaded data | 3 days | Mon 03-03-25 | Wed 05-03-25 | Fri 04-04-25 | Tue 08-04-25 | NA | NA | 178SS | 0% | DRAIPL | 100% | 10% |  | Future Task
1.2.3.6 | Go-Live | 1 day | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.6.1 | Go-Live | 1 day | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA | 296 | 0% | HBT & DRAIPL | 100% | 10% | 3% | Future Task
1.2.3.7 | Deliverables | 15 days | Wed 12-02-25 | Wed 05-03-25 | Tue 18-03-25 | Tue 08-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.7.1 | D: End user training manual | 0 days | Wed 12-02-25 | Wed 12-02-25 | Tue 18-03-25 | Tue 18-03-25 | NA | NA | 186 | 0% | HBT |  |  |  | Future Task
1.2.3.7.2 | D: Data migration strategy document | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 187 | 0% | HBT |  |  |  | Future Task
1.2.3.7.3 | D: Master data upload programs | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 188 | 0% | HBT |  |  |  | Future Task
1.2.3.7.4 | D: Sample data upload validation | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 189 | 0% | HBT |  |  |  | Future Task
1.2.3.7.5 | D: Final authorization matrix, roles & authorizations | 0 days | Wed 05-03-25 | Wed 05-03-25 | Tue 08-04-25 | Tue 08-04-25 | NA | NA | 190 | 0% | HBT |  |  |  | Future Task
1.2.3.8 | Obtain Approval & phase Sign Off | 0 days | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.2.3.8.1 | Deploy signoff | 0 days | Thu 06-03-25 | Thu 06-03-25 | Wed 09-04-25 | Wed 09-04-25 | NA | NA | 192 | 0% | DRAIPL | 100% | 10% | 3% | Future Task
1.3 | Wave 1C: Management Analytics (SAC) | 81 days | Thu 14-11-24 | Thu 06-03-25 | Thu 14-11-24 | Thu 06-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.1 | EXPLORE (BUSINESS BLUEPRINT) | 15 days | Thu 14-11-24 | Wed 04-12-24 | Thu 14-11-24 | Wed 04-12-24 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 15% | 5% | Future Task
1.3.1.1 | Requirement Gathering Workshop for SAC | 15 days | Thu 14-11-24 | Wed 04-12-24 | Thu 14-11-24 | Wed 04-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.1.1.1 | Requirement Gathering Workshop for SAC | 7 days | Thu 14-11-24 | Fri 22-11-24 | Thu 14-11-24 | Fri 22-11-24 | NA | NA | 5SS+44 days | 0% | DRAIPL | 100% | 15% |  | Future Task
1.3.1.1.2 | Finalize reporting requiremnt | 5 days | Mon 25-11-24 | Fri 29-11-24 | Mon 25-11-24 | Fri 29-11-24 | NA | NA | 310 | 0% | HBT & DRAIPL | 100% | 15% |  | Future Task
1.3.1.1.3 | Submit SAC Business Requirement Document | 5 days | Mon 25-11-24 | Fri 29-11-24 | Mon 25-11-24 | Fri 29-11-24 | NA | NA | 311SS | 0% | HBT |  |  |  | Future Task
1.3.1.1.4 | Explore Phase Sign-off | 3 days | Mon 02-12-24 | Wed 04-12-24 | Mon 02-12-24 | Wed 04-12-24 | NA | NA | 312 | 0% | DRAIPL | 100% | 15% |  | Future Task
1.3.1.2 | Deliverables | 0 days | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.1.2.1 | D: SAC Business Requirement Document | 0 days | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | NA | NA | 313 | 0% | HBT |  |  |  | Future Task
1.3.1.3 | Key milestones | 0 days | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.1.3.1 | On Completion of Explore Phase | 0 days | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | Wed 04-12-24 | NA | NA | 313 | 0% | HBT & DRAIPL |  |  |  | Future Task
1.3.2 | REALIZE (REALIZATION) | 47 days | Tue 03-12-24 | Wed 05-02-25 | Tue 03-12-24 | Wed 05-02-25 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 10% | 3% | Future Task
1.3.2.1 | Prepare functional specifications | 5 days | Tue 03-12-24 | Mon 09-12-24 | Tue 03-12-24 | Mon 09-12-24 | NA | NA | 312FS+1 day | 0% | HBT |  |  |  | Future Task
1.3.2.2 | Backend data source development | 5 days | Tue 10-12-24 | Mon 16-12-24 | Tue 10-12-24 | Mon 16-12-24 | NA | NA | 319 | 0% | HBT |  |  |  | Future Task
1.3.2.3 | Dashboard development | 25 days | Tue 10-12-24 | Mon 13-01-25 | Tue 10-12-24 | Mon 13-01-25 | NA | NA | 319 | 0% | HBT |  |  |  | Future Task
1.3.2.4 | Dashboard testing in development by HBT & issue resolution | 20 days | Tue 24-12-24 | Mon 20-01-25 | Tue 24-12-24 | Mon 20-01-25 | NA | NA | 321SS+10 days | 0% | HBT |  |  |  | Future Task
1.3.2.5 | Release of Seven Dashboard for UAT | 1 day | Tue 21-01-25 | Tue 21-01-25 | Tue 21-01-25 | Tue 21-01-25 | NA | NA | 322 | 0% | HBT |  |  |  | Future Task
1.3.2.6 | UAT by CTM for Seven released dashboards | 5 days | Wed 22-01-25 | Tue 28-01-25 | Wed 22-01-25 | Tue 28-01-25 | NA | NA | 323 | 0% | DRAIPL | 100% |  |  | Future Task
1.3.2.7 | Release of Balance Eight Dashboard for UAT | 1 day | Wed 29-01-25 | Wed 29-01-25 | Wed 29-01-25 | Wed 29-01-25 | NA | NA | 324 | 0% | HBT |  |  |  | Future Task
1.3.2.8 | UAT by CTM for balance Eight released dashboards | 3 days | Thu 30-01-25 | Mon 03-02-25 | Thu 30-01-25 | Mon 03-02-25 | NA | NA | 325 | 0% | DRAIPL | 100% |  |  | Future Task
1.3.2.9 | UAT Sign-off | 3 days | Thu 30-01-25 | Mon 03-02-25 | Thu 30-01-25 | Mon 03-02-25 | NA | NA | 326SS | 0% | DRAIPL | 100% |  |  | Future Task
1.3.2.10 | Deliverables | 0 days | Mon 03-02-25 | Mon 03-02-25 | Mon 03-02-25 | Mon 03-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.2.10.1 | D: UAT Sign off | 0 days | Mon 03-02-25 | Mon 03-02-25 | Mon 03-02-25 | Mon 03-02-25 | NA | NA | 327 | 0% | DARIPL |  |  |  | Future Task
1.3.2.11 | Key milestones | 9 days | Tue 21-01-25 | Mon 03-02-25 | Tue 21-01-25 | Mon 03-02-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.2.11.1 | Release of Five Dashboard for UAT | 0 days | Tue 21-01-25 | Tue 21-01-25 | Tue 21-01-25 | Tue 21-01-25 | NA | NA | 323 | 0% | HBT |  |  |  | Future Task
1.3.2.11.2 | Release of Balance Ten Dashboard for UAT | 0 days | Wed 29-01-25 | Wed 29-01-25 | Wed 29-01-25 | Wed 29-01-25 | NA | NA | 325 | 0% | HBT |  |  |  | Future Task
1.3.2.11.3 | UAT Sign-off | 0 days | Mon 03-02-25 | Mon 03-02-25 | Mon 03-02-25 | Mon 03-02-25 | NA | NA | 327 | 0% | DRAIPL |  |  |  | Future Task
1.3.3 | DEPLOY (FINAL PREPARATION & GO LIVE) | 23 days | Tue 04-02-25 | Thu 06-03-25 | Tue 04-02-25 | Thu 06-03-25 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 10% | 3% | Future Task
1.3.3.1 | Prepare end user training manual - Go Live | 2 days | Tue 04-02-25 | Wed 05-02-25 | Tue 04-02-25 | Wed 05-02-25 | NA | NA | 327 | 0% | HBT |  |  |  | Future Task
1.3.3.2 | Conduct End User Training | 9 days | Thu 06-02-25 | Tue 18-02-25 | Thu 06-02-25 | Tue 18-02-25 | NA | NA | 335 | 0% | HBT |  |  |  | Future Task
1.3.3.3 | Submit training completion report | 1 day | Wed 19-02-25 | Wed 19-02-25 | Wed 19-02-25 | Wed 19-02-25 | NA | NA | 336 | 0% | HBT |  |  |  | Future Task
1.3.3.4 | Final Preparation (Production readiness i.e. end user creation, roles and assignment) | 5 days | Thu 20-02-25 | Wed 26-02-25 | Thu 20-02-25 | Wed 26-02-25 | NA | NA | 337 | 0% | HBT |  |  |  | Future Task
1.3.3.5 | Move dashboards to production environment | 4 days | Thu 27-02-25 | Tue 04-03-25 | Thu 27-02-25 | Tue 04-03-25 | NA | NA | 338 | 0% | HBT |  |  |  | Future Task
1.3.3.6 | Go-Live | 1 day | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA | 339FS+1 day | 0% | HBT & DRAIPL |  |  |  | Future Task
1.3.3.7 | Phase Sign-off- Final Preparation & Go-Live Phase | 0 days | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA | 340 | 0% | DRAIPL |  |  |  | Future Task
1.3.3.8 | Deliverables | 0 days | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.3.8.1 | D: FS , TS Documents | 0 days | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA | 340 | 0% | HBT |  |  |  | Future Task
1.3.3.8.2 | D: Deploy phase sign Off | 0 days | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA | 340 | 0% | HBT |  |  |  | Future Task
1.3.3.9 | Key milestones | 0 days | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.3.3.9.1 | Completion of Final Preparation & Go-Live | 0 days | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | Thu 06-03-25 | NA | NA | 340 | 0% | HBT & DRAIPL |  |  |  | Future Task
1.4 | Wave 1J HBT’s Onsite Team Deployment for Guiding & assisting Data Preparation: | 107 days | Fri 08-11-24 | Mon 07-04-25 | Fri 08-11-24 | Mon 07-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.4.1 | Team Mobilisation | 1 day | Fri 08-11-24 | Fri 08-11-24 | Fri 08-11-24 | Fri 08-11-24 | NA | NA |  | 0% |  |  |  |  | Future Task
1.4.1.1 | Team Mobilisation | 1 day | Fri 08-11-24 | Fri 08-11-24 | Fri 08-11-24 | Fri 08-11-24 | NA | NA |  | 0% | HBT |  |  |  | Future Task
1.4.2 | Explore | 53 days | Mon 11-11-24 | Thu 19-12-24 | Mon 11-11-24 | Wed 22-01-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.4.2.1 | Explain Master Data Template | 5 days | Mon 11-11-24 | Fri 15-11-24 | Mon 11-11-24 | Fri 15-11-24 | NA | NA | 349 | 0% | HBT |  |  |  | Future Task
1.4.2.2 | Explain Cutover Data Template | 5 days | Fri 13-12-24 | Thu 19-12-24 | Thu 16-01-25 | Wed 22-01-25 | NA | NA | 126 | 0% | HBT |  |  |  | Future Task
1.4.3 | Realize | 55 days | Fri 20-12-24 | Thu 06-03-25 | Thu 23-01-25 | Wed 09-04-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.4.3.1 | Guiding & Assisting CTM for Data preparation | 55 days | Fri 20-12-24 | Thu 06-03-25 | Thu 23-01-25 | Wed 09-04-25 | NA | NA | 352 | 0% | HBT |  |  |  | Future Task
1.4.4 | Deploy | 22 days | Fri 07-03-25 | Mon 07-04-25 | Thu 10-04-25 | Fri 09-05-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.4.4.1 | Guiding & Assisting CTM for Data Upload in Qality & Production | 22 days | Fri 07-03-25 | Mon 07-04-25 | Thu 10-04-25 | Fri 09-05-25 | NA | NA | 354 | 0% | HBT |  |  |  | Future Task
1.5 | Post Go-Live Support | 22 days | Fri 07-03-25 | Mon 07-04-25 | Thu 10-04-25 | Fri 09-05-25 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.5.1 | Run | 22 days | Fri 07-03-25 | Mon 07-04-25 | Thu 10-04-25 | Fri 09-05-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.5.1.1 | First month post Go-Live support | 22 days | Fri 07-03-25 | Mon 07-04-25 | Thu 10-04-25 | Fri 09-05-25 | NA | NA | 181 | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.5.1.2 | First Month End closing | 5 days | Tue 01-04-25 | Mon 07-04-25 | Mon 05-05-25 | Fri 09-05-25 | NA | NA | 359SS+17 days | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.5.1.3 | First month Data guidamnce and support to CTM | 22 days | Fri 07-03-25 | Mon 07-04-25 | Thu 10-04-25 | Fri 09-05-25 | NA | NA | 181 | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.5.2 | Deliverables | 0 days | Mon 07-04-25 | Mon 07-04-25 | Fri 09-05-25 | Fri 09-05-25 | NA | NA |  | 0% |  |  |  |  | Future Task
1.5.2.1 | D: Issue log & resolutions | 0 days | Mon 07-04-25 | Mon 07-04-25 | Fri 09-05-25 | Fri 09-05-25 | NA | NA | 359 | 0% | HBT |  |  |  | Future Task
1.5.2.2 | D: FS & TS | 0 days | Mon 07-04-25 | Mon 07-04-25 | Fri 09-05-25 | Fri 09-05-25 | NA | NA | 359 | 0% | HBT |  |  |  | Future Task
1.6 | Wave 2 Support - for 12 months | 261 days | Tue 08-04-25 | Tue 07-04-26 | Mon 12-05-25 | Mon 11-05-26 | NA | NA |  | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.6.1 | Issue resolution, bug fixing etc - 200 Tickets | 261 days | Tue 08-04-25 | Tue 07-04-26 | Mon 12-05-25 | Mon 11-05-26 | NA | NA | 361 | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.6.2 | 100 Mandays provision for CR & Developments | 261 days | Tue 08-04-25 | Tue 07-04-26 | Mon 12-05-25 | Mon 11-05-26 | NA | NA | 366SS | 0% | HBT & DRAIPL | 100% | 100% | 100% | Future Task
1.6.3 | Deliverables | 0 days | Tue 07-04-26 | Tue 07-04-26 | Mon 11-05-26 | Mon 11-05-26 | NA | NA |  | 0% |  |  |  |  | Future Task
1.6.3.1 | D: Issue log & resolutions | 0 days | Tue 07-04-26 | Tue 07-04-26 | Mon 11-05-26 | Mon 11-05-26 | NA | NA | 367 | 0% | HBT |  |  |  | Future Task
1.6.3.2 | D: FS & TS | 0 days | Tue 07-04-26 | Tue 07-04-26 | Mon 11-05-26 | Mon 11-05-26 | NA | NA | 367 | 0% | HBT |  |  |  | Future Task