## P1
[6 empty] | RGS |  |  |  |  | FSD |  |  |  |  | Development | [5 empty] | UAT
[6 empty] | Planned |  | Revised | Actual |  | Planned |  | Actual |  |  | Planned |  | Revised | Actual |  |  | Planned |  | Revised | Actual
S.No. | Objects | Priority | Status | RGS Signed-off By | UAT Signed-off By | From | To |  | From | To | From | To | From | To | Functional Consultant | From | To |  | From | To | Technical Consultant | From | To |  | From | To | Remarks on 15.07.2024 | Remarks on 17.07.2024 | Remarks on 18.07.2024 | Remarks on 24.07.2024 | Remarks on 29.07.2024 | Remarks on 07.08.2024 | Remarks on 18.08.2024 | Remarks on 21.08.2024
1 | Area Change | P1 | Done | Harkesh Jolly, Ankur Gupta | - | 2024-06-10 | 2024-06-11 |  | Done | Done | 2024-06-12 | 2024-06-13 | Done | Done | Karan Jha | 2024-06-17 | 2024-07-09 | 2024-07-16 | 2024-06-17 |  | Amarjeet Singh | 2024-07-10 | 2024-07-12 | 2024-07-23 |  |  | Development Done, UAT given on 12-July-24. Change feedback received. Working on that. Changes - Report Column Additon, Revised Rate Functionality, Credit Note Liability Date calculation. Mail sent for confirmation. |  | Final UAT to be scheduled on Monday post the disucssion with Harkesh Jolly. | UAT Done on Tuesday, mail for the confirmation received from Satyendra Jha. Reminder mail has been sent to Ankur Sir as well as Harish Sir. | UAT Sign off received from CTMs, BPO sign off to be received post user UAT. User Manual to be create. | 1. User Manual to be share on 07.08.2024. 2. Call with sunny on 08.08.2024. RGS to be sign off with him on 08.08.2024. Post signoff development will start and end by 12.08.2024. UAT on 13.08.2024. | All CTM sign off received. Change in process, Requirement gathering meeting have been done Sunny and Sunil Sharma waiting for the confirmation. Post confirmation, it will take 4 days to develop and test the scenerio. Follow up mail have been sent. On mail and whatsapp both. | All CTM sign off received. Change in process, Requirement gathering meeting have been done Sunny and Sunil Sharma. Confirmation received yesterday i.e. 20.08.2024. By 23.08.2024, we will provide the development.
2 | Possession | P1 | WIP (Changes) | Harkesh Jolly, Ankur Gupta | Mukesh Kumar Khan ( Gurugram) | 2024-06-14 | 2024-06-14 |  | Done | Done | 2024-06-19 | 2024-06-20 | Done | Done | Karan Jha/Deepak Baviskar. | 2024-07-02 | 2024-07-06 | 2024-07-16 | 2024-07-02 |  | Anjali | 2024-07-08 | 2024-07-09 | 2024-07-29 |  |  | Development Done, changes in internal testing noted. Working on those changes. Changes - Stamp Duty Calcualtion, Interest Logic to be implement. |  |  | Mail to be sent for UAT. | Testing to be done by today. | User Manual to be create and UAT Mail to be sent to Gurgaon team by 09.08.2024. | Development to be done by 22.08.2024. | Development to be done by 22.08.2024.
3 | Stamp Duty Calculation | P1 | WIP (Changes) | Harkesh Jolly, Ankur Gupta | Mukesh Kumar Khan ( Gurugram) | 2024-06-14 | 2024-06-14 |  | Done | Done | 2024-06-19 | 2024-06-20 | Done | Done | Karan Jha/Deepak Baviskar. | 2024-07-02 | 2024-07-06 | 2024-07-16 | 2024-07-02 |  | Anjali | 2024-07-08 | 2024-07-09 | 2024-07-29 |  |  | Development Done, changes in internal testing noted. Working on those changes. Changes - Stamp Duty Calcualtion, Interest Logic to be implement. |  |  | Mail to be sent for UAT. | Testing to be done by today. | User Manual to be create and UAT Mail to be sent to Gurgaon team by 09.08.2024. | Development to be done by 22.08.2024. | Development to be done by 22.08.2024.
4 | Auto GST Reversal/ Forfeiture amount GST Calculation | P1 | Re-UAT | Satyendra Jha | Rajan Kapoor | - | - |  | - | - | - | - | - | - | Saddam | - | - | 2024-07-17 | - | - | - | 2024-07-03 | 2024-07-09 | 2024-07-30 |  |  | UAT Given on 9-July-24 including FI as well as GST team as well. Feedbacks in UAT Received, Clarification feedbacks are there. Saddam and Tanuj need to re schedule the UAT again. |  | UAT will be scheduled post the CPIs activity will be resolved. It will resolve by Saturday morning confirmed by Vinod. | Test cases to be create by Saddam, now re UAT will be plan. Gap while receiving payment in against of demands (F-28). | Facing challenge while receiving payment against demand. F-28 issue. | Mail to be sent by 07.08.2024 to Harish Bansal, Ankur Gupta and Sunny to Gurgaon UAT. | UAT to be given by 21.08.2024. | UAT to be given by 27.08.2024. Mail to be sent by today post discussion with Arpit and Saddam.
5 | E-Invoicing | P1 | Re-UAT | - | - | - | - |  | - | - | - | - | - | - | Saddam | - | - |  | - | - | - | 2024-07-03 | 2024-07-09 | 2024-07-30 |  |  |  | In case of any query come during the UAT of Auto GST (pt. 4) then same to address. | In case of any query come during the UAT of Auto GST (pt. 4) then same to address. | In case of any query come during the UAT of Auto GST (pt. 4) then same to address. | In case of any query come during the UAT of Auto GST (pt. 4) then same to address. | In case of any query come during the UAT of Auto GST (pt. 4) then same to address. | In case of any query come during the UAT of Auto GST (pt. 4) then same to address. | In case of any query come during the UAT of Auto GST (pt. 4) then same to address.
6 | Booking Category | P1 | WIP | - | - | 2024-07-03 | 2024-07-05 |  |  |  | 2024-07-06 | 2024-07-06 |  |  | Karan Jha | 2024-07-08 | 2024-07-11 |  |  |  | Anjali | 2024-07-12 | 2024-07-20 | 2024-07-30 |  |  |  |  | Will be cater once area change UAT will be done. | RGS have been submitted, waiting for the confirmation. Today it is not possible because Harkesh Sir is on leave and M3M team is occupied in possession activity. | Reminder mail have been sent for the final RGS sign off mail. Although parallel development have been started. |  | RGS to be create and signoff to be done. Highly Dependent on Dunning Cockpit. | RGS to be create and signoff to be done. Highly Dependent on Dunning Cockpit.
7 | Pre Handover | P1 | Done | Harkesh Jolly, Rajan Kapoor, Ankur Gupta, Satyendra Jha | Satyendra Jha | - | - |  | - | - | - | - | - | - | Karan Jha | [5 empty] | - | 2024-07-08 | 2024-07-13 | 2024-07-30 |  |  | UAT Given on 12-July-2024, It was concluded that user will do the testing. Mail to sent for the testing. | To prepare the plan for testing, in concurrence with Ankur Gupta, Rakesh Sharma and Vikas Sharma during urbana visit on 18th July 2024. | Segement plan have been prepared with Rakesh and Vikas from M3M. This will be proceed further once Comfort Letter and Booking Category will be delivered. | Entire segement have been planned. But as per Harkesh Sir, there is dependency of Comfort Letter as well as Booking Category. Once this will be done plan will be flow on. | Entire segement have been planned. But as per Harkesh Sir, there is dependency of Comfort Letter as well as Booking Category. Once this will be done plan will be flow on. |  | Depending in Comfort Letter and Booking Category. | Depending on Comfort Letter and Booking Category.
8 | Post Handover | P1 | WIP | Harkesh Jolly, Ankur Gupta |  | - | - |  | Done | Done |  |  | Done | Done | Pratik Mandlik | 2024-07-01 | 2024-07-08 | 2024-07-19 |  |  | Santosh | 2024-07-10 | 2024-07-14 | 2024-08-01 | [5 empty] | This will be cater once done with Booking Category. | This will be cater once done with Booking Category. |  | Development to be done by 22.08.2024. | Development to be done by 22.08.2024.
9 | Document Flow from SAP to SFDC (PDF Document) | P1 | Done | - | - | - | - |  | - | - | - | - | - | - | - | 2024-07-10 | 2024-07-13 |  | - | - | - | 2024-07-15 | 2024-07-15 |  | - | - | API Development have been done from SAP side, and the same was shared with team manras. Waiting for their response. |  | I have deliver the JSON keeping in mind that API route will SFDC-SAP then data will be flow back from SAP to SFDC. But today it was finalized that SAP will send form immediately post generation of Document. Style will be Template + Digital Signature (new requirement). | I have deliver the JSON keeping in mind that API route will SFDC-SAP then data will be flow back from SAP to SFDC. But today it was finalized that SAP will send form immediately post generation of Document. Style will be Template + Digital Signature (new requirement). | I have deliver the JSON keeping in mind that API route will SFDC-SAP then data will be flow back from SAP to SFDC. But today it was finalized that SAP will send form immediately post generation of Document. Style will be Template + Digital Signature (new requirement). |  | API from SAP to SFDC have been shared. Now awaiting Manras to be share SFDC to SAP document. | API from SAP to SFDC have been shared. Now awaiting Manras to be share SFDC to SAP document.
10 | Brokerage Module | P1 | WIP | - | - | - | - |  | - | - | 2024-07-07 | 2024-07-07 | - | - | Shubham Parashar, Saddam | 2024-07-08 | 2024-07-09 | 2024-07-17 | - | - | - | 2024-07-10 | 2024-07-12 | 2024-08-02 |  |  | UAT given. Few observarions provided. Re UAT to be done |  | Shubham and Kaushal will work on this post 6:30PM and deliver this. |  |  |  | Change Development under process. | Change Development under process. Will be done by 23.08.2024.
11 | Comfort Letter | P1 | WIP | - | - | - | - |  | - | - | - | - | - | - | Hrishikesh Bagul/Saddam | - | - |  | - | - | - | 2024-07-02 | 2024-07-03 | 2024-07-30 |  |  | It was planned to be geiven UAT to users, but new 35 forms to be development request have been received. |  | 5 out of 35 formats have been received from Navneet Ved. Tomorrow I will conduct one meeting these forms to gather the logic for dynamic field and take the RGS signoff. | 9 out of 35 formats have been received from Navneet Ved. RGS to be submit today. And FSD will be created by today. | RGS to be created by today. And will be sent for approval. |  | Out of 35 forms. - 19 forms received, RGS Created and Submitted. (Partial Signed off by CTM only) - 16 forms received on 13.08.2024. Remaining RGS to be submitted by 20.08.2024 EOD. | Out of 35 forms. - 19 forms received, RGS Created and Submitted. (Partial Signed off by CTM only) - 16 forms received on 13.08.2024. Remaining RGS to be submitted by 20.08.2024 EOD.
12 | Dunning Letters | P1 | UAT to start | - | - | - | - |  | - | - | - | - | - | - | Hrishikesh Bagul/Saddam | - | - |  | - | - | - | 2024-07-15 | 2024-07-15 | 2024-08-01 |  |  | Depending on Interest closure | [5 empty] | Dunning Cockpit to be develop by Tanuj. | Dunning Cockpit to be develop by Tanuj
13 | BBA Printing, Dispatch, Received date for exectuion, Execution Date, Schedued Date of Registraion, Registraion Date Vasika Number to be catpure in SAP, BBA Handover Date and Status. | P1 | Done |  |  | 2024-07-02 | 2024-07-03 |  |  |  | 2024-07-04 | 2024-07-04 |  |  | Hrishikesh Bagul/Saddam | 2024-07-05 | 2024-07-08 |  |  |  |  | 2024-07-09 | 2024-07-10 | 2024-08-01 |  |  | RGS Submitted by 2 July 2024, re RGS Submited by 4 July 2024, reminder mail already sent. Awaiting RGS Sign off from Sumit Seghal and Ankur Gupta.
14 | CD Printing, Schedued Date of Registraion, Registeration Date, Vasika Number to be catpure in SAP, CD Handover Date and Status. | P1 | Done |  |  | 2024-07-02 | 2024-07-03 |  |  |  | 2024-07-04 | 2024-07-04 |  |  | Hrishikesh Bagul/Saddam | 2024-07-05 | 2024-07-08 |  |  |  |  | 2024-07-09 | 2024-07-10 | 2024-08-01 |  |  | RGS Submitted by 2 July 2024, re RGS Submited by 4 July 2024, reminder mail already sent. Awaiting RGS Sign off from Sumit Seghal and Ankur Gupta.
15 | TPR TPD | P2 | Not Started |  |  | 2024-08-22 | 2024-08-27 |  |  |  | 2024-08-28 | 2024-08-30 |  |  | Karan Jha | 2024-08-31 | 2024-09-08 |  |  |  |  | 2024-09-09 | 2024-09-11 | [9 empty] | TBD
Formulas:
To = [RGS]+1
To = [UAT]+2
FSD = [To]+1
FSD = [FSD, row above]
Development = [To]+2
Development = [Development, row above]
UAT = [To]+1
UAT = [UAT, row above]
RGS = [RGS, row above]

## Critical objects tracker
Head | Sub-Head | Module | Process | Description |  | Development Type | Complexity | Function Consultant | Technical Consultant | RGS |  |  |  | Functional Specification |  |  |  | ABAP Development |  |  |  | Functional Testing |  |  |  | CTM Testing |  |  |  | Sign off
Sr.No. | Sr.No. |  |  |  | Dependency |  |  |  |  | Duration | Start Date | End Date | Status | Duration | Start Date | End Date | Status | Duration | Start Date | End Date | Status | Duration | Start Date | End Date | Status | Duration | Start Date | End Date | Status | CTM | BPO
1 | 1 | SD | Area Change | 3 Area Change Database Creation | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 2 | SD | Area Change | Area Main Screen To Access | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 3 | SD | Area Change | Report to Capture New Area Change Detail | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 4 | SD | Area Change | Report to Approve New Area Change Detail | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 5 | SD | Area Change | Enhancement to Change Unit Master Area | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 6 | SD | Area Change | Report to Capture New Booking Amendment Detail | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 7 | SD | Area Change | Report to Approve New Booking Amendment Detail | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 8 | SD | Area Change | Enhancement to Change Booking Payment Plan | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 9 | SD | Area Change | Enhancement to Change Booking and Component Pricing | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 10 | SD | Area Change | Enhancement to Create Credit Note Request Number | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 11 | SD | Area Change | Enhancement for Finance to approve credit note request | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 12 | SD | Area Change | Report for History for Area Change | - | Module Pool | Complex | Karan Jha | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | Sign off
1 | 13 | SD | Area Change | Credit Note Posting Screen | - | Module Pool | Complex | Karan Jha | Kaushal Sharma |  |  |  | Completed |  | 2024-08-22 | 2024-08-23 | In Progress |  | 2024-08-26 | 2024-08-28 | Not Started | 1 | 2024-08-29 | 2024-08-29 | Not Started | 1 | 2024-08-30 | 2024-08-30 | Not Started
2 | 14 | SD | Possession | Possession Form | Booking Category | Smartform | Complex | Karan Jha | Anjali |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  | 2024-08-23 | In Progress | 2 | 2024-09-22 | 2024-09-22 | Not Started
3 | 15 | SD | Stamp Duty Calculation | Stamp Duty Calculation | Possession | Smartform | Complex | Karan Jha | Anjali |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  | 2024-08-23 | In Progress | 2 | 2024-09-22 | 2024-09-22 | Not Started | 0 | 0
4 | 16 | SD | Auto GST Reversal | Auto GST Reversal UAT | - | Module Pool | Complex | Karan Jha | Satish Bhakt |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | 2 | 2024-08-27 | 2024-08-29 | In Progress
5 | 17 | SD | E-Invoicing | E-Invoicing | Auto GST Reversal | Module Pool | Complex | Karan Jha | Satish Bhakt |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | 2 | 2024-08-27 | 2024-08-29 | In Progress
6 | 18 | SD | Booking Category | 4 Booking Category Database Creation | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | 2 | 2024-08-22 | 2024-08-23 | Not Started | 3 | 2024-08-24 | 2024-08-27 | Not Started | 8 | 2024-08-28 | 2024-09-05 | Not Started | 2 | 2024-09-06 | 2024-09-08 | Not Started | 2 | 2024-09-22 | 2024-09-22 | Not Started
6 | 19 | SD | Booking Category | Screen Creation to Capture tags | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | 2 | 2024-08-22 | 2024-08-23 | Not Started | 3 | 2024-08-24 | 2024-08-27 | Not Started | 8 | 2024-08-28 | 2024-09-05 | Not Started | 2 | 2024-09-06 | 2024-09-08 | Not Started | 2 | 2024-09-22 | 2024-09-22 | Not Started
6 | 20 | SD | Booking Category | Approval Process on each category | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | 2 | 2024-08-22 | 2024-08-23 | Not Started | 3 | 2024-08-24 | 2024-08-27 | Not Started | 8 | 2024-08-28 | 2024-09-05 | Not Started | 2 | 2024-09-06 | 2024-09-08 | Not Started | 2 | 2024-09-22 | 2024-09-22 | Not Started
6 | 21 | SD | Booking Category | Enhacements for each category | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | 2 | 2024-08-22 | 2024-08-23 | Not Started | 3 | 2024-08-24 | 2024-08-27 | Not Started | 8 | 2024-08-28 | 2024-09-05 | Not Started | 2 | 2024-09-06 | 2024-09-08 | Not Started | 2 | 2024-09-22 | 2024-09-22 | Not Started
6 | 22 | SD | Booking Category | Report for Booking Category | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | 2 | 2024-08-22 | 2024-08-23 | Not Started | 3 | 2024-08-24 | 2024-08-27 | Not Started | 8 | 2024-08-28 | 2024-09-05 | Not Started | 2 | 2024-09-06 | 2024-09-08 | Not Started | 2 | 2024-09-22 | 2024-09-22 | Not Started
7 | 23 | SD | Pre Handover | Pre Handover | Dunning Cockpit | Module Pool | Complex | Karan Jha | Amarjeet Singh | - | - | - | Completed | - | - | - | Completed | - | - | - | Completed | - | - | - | Completed | 3 | 2024-09-23 | 2024-09-26 | Not Started
8 | 24 | SD | Post Handover | 5 Post Handover Database Creation | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | - | - | - | Completed | - | - | - | Completed | - | - | - | Completed | - | - | - | Completed | 3 | 2024-09-27 | 2024-09-29 | Not Started
8 | 25 | SD | Post Handover | Rule Set Creation Screen | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | - | - | - | Completed | - | - | - | Completed | - | - | 2024-08-23 | In Progress | 1 | 2024-08-23 | 2024-08-24 | Not Started | 3 | 2024-09-27 | 2024-09-29 | Not Started
8 | 26 | SD | Post Handover | Approval Screen on Tenant Data | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | - | - | - | Completed | - | - | - | Completed | - | - | 2024-08-23 | In Progress | 1 | 2024-08-23 | 2024-08-24 | Not Started | 3 | 2024-09-27 | 2024-09-29 | Not Started
8 | 27 | SD | Post Handover | Payout Report | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | - | - | - | Completed | - | - | - | Completed | - | - | 2024-08-23 | In Progress | 1 | 2024-08-23 | 2024-08-24 | Not Started | 3 | 2024-09-27 | 2024-09-29 | Not Started
8 | 28 | SD | Post Handover | FI Payout Post Report | Dunning Cockpit | Module Pool | Complex | Karan Jha | Kaushal Sharma | - | - | - | Completed | - | - | - | Completed | - | - | 2024-08-23 | In Progress | 1 | 2024-08-23 | 2024-08-24 | Not Started | 3 | 2024-09-27 | 2024-09-29 | Not Started
9 | 29 | SD | Document API | Document API | - | Interface | Complex | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | Not Started | 1 | 2024-08-24 | 2024-08-25 | Not Started | 4 | 2024-08-26 | 2024-08-30 | Not Started | 1 | 2024-08-31 | 2024-09-01 | Not Started | 1 | 2024-09-03 | 2024-09-04 | Not Started
10 | 30 | SD | Comfort Letter | Antaliya Hills Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 31 | SD | Comfort Letter | Antaliya Hills Phase 1 &2 Pre Emi Subvention Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 32 | SD | Comfort Letter | Antalya 26 White Goods Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 33 | SD | Comfort Letter | BBA Discount Antalya Hills | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 34 | SD | Comfort Letter | BBA Discount Golf Hills | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 35 | SD | Comfort Letter | Capital 26 White Goods Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 36 | SD | Comfort Letter | Car Parking Letter For All Projects | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 37 | SD | Comfort Letter | Commercial Accumaltion Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 38 | SD | Comfort Letter | Commercial Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 39 | SD | Comfort Letter | Crown 26 White Goods Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 40 | SD | Comfort Letter | Crown Pre Emi Subvention Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 41 | SD | Comfort Letter | First Transfer Free Letter for All Projects | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 42 | SD | Comfort Letter | Golf Hills Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 43 | SD | Comfort Letter | Golf Hills Lawn Letter Only for Ground Floor | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 44 | SD | Comfort Letter | Golf Hills Phase 1 & 2 Pre Emi Subvention Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 45 | SD | Comfort Letter | Golf Hills Phase 1 Tpr Non-Subvention Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 46 | SD | Comfort Letter | Golf Hills Phase 1Tpr Subvention Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 47 | SD | Comfort Letter | Golf Hills Phase 2 Tpr Non-Subvention Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 48 | SD | Comfort Letter | Maintainance Letter for All Projects | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 49 | SD | Comfort Letter | One Time Discount All Commercial Projects Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 50 | SD | Comfort Letter | One Time Discount All Residential Preojects Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 51 | SD | Comfort Letter | One Time Rebate All Commercial Projects Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 52 | SD | Comfort Letter | One Time Rebate All Residential Project Letter | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 53 | SD | Comfort Letter | Pre Payment Letter For All Projects | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 54 | SD | Comfort Letter | Recovery Clause For Residential Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 55 | SD | Comfort Letter | Recovery Clause Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 56 | SD | Comfort Letter | Residential Accumation Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 57 | SD | Comfort Letter | Residential Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 58 | SD | Comfort Letter | Soulitude Format | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 59 | SD | Comfort Letter | Timely Payment Discount Residential Project | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 60 | SD | Comfort Letter | Timely Payment Discount Commercial Project | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 61 | SD | Comfort Letter | Timely Payment Rebate Commercial Project | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 62 | SD | Comfort Letter | Timely Payment Rebate Resdential Project | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 63 | SD | Comfort Letter | Tpd Antaliya Hills | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
10 | 64 | SD | Comfort Letter | Tpr 400 | - | Smartform | Simple | Karan Jha | Kaushal Sharma |  | 2024-08-22 | 2024-08-23 | In Progress | 2 | 2024-08-24 | 2024-08-26 | In Progress | 4 | 2024-08-27 | 2024-08-31 | Not Started | 1 | 2024-09-01 | 2024-09-02 | Not Started | 1 | 2024-09-04 | 2024-09-05 | Not Started
11 | 65 | SD | Dunning Cockpit | Dunning Cockpit | - | Module Pool | Complex | Tanuj | Amarjeet Singh | 3 | 2024-08-29 | 2024-08-31 | Not Started | 4 | 2024-09-01 | 2024-09-05 | Not Started | 7 | 2024-09-06 | 2024-09-13 | Not Started | 2 | 2024-09-14 | 2024-09-16 | Not Started | 3 | 2024-09-18 | 2024-09-21 | Not Started
11 | 66 | SD | Dunning Letters | Reminder 1 | - | Smartform | Medium | Tanuj | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | 1 | 2024-08-26 | 2024-08-26 | Not Started
11 | 67 | SD | Dunning Letters | Pre Cancellation Letter | - | Smartform | Medium | Tanuj | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | 1 | 2024-08-26 | 2024-08-26 | Not Started
11 | 68 | SD | Dunning Letters | Last and Final Opportunity | - | Smartform | Medium | Tanuj | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | 1 | 2024-08-26 | 2024-08-26 | Not Started
11 | 69 | SD | Dunning Letters | Cancellation Sent | - | Smartform | Medium | Tanuj | Amarjeet Singh |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed | 1 | 2024-08-26 | 2024-08-26 | Not Started
12 | 70 | SD | TPR TPD | TPR TPD |  | Module Pool | Complex | Karan Jha | Kaushal Sharma | 3 | 2024-08-26 | 2024-08-29 | Not Started | 4 | 2024-08-29 | 2024-09-02 | Not Started | 7 | 2024-09-02 | 2024-09-09 | Not Started | 2 | 2024-09-09 | 2024-09-11 | Not Started | 3 | 2024-09-11 | 2024-09-14 | Not Started
13 | 71 | SD | BBA Printing | BBA Printing |  | Report | Medium | [18 empty] | 1 | 2024-08-28 | 2024-08-28 | Not Started
14 | 72 | SD | CD Printing | CD Printing |  | Report | Medium | [18 empty] | 1 | 2024-08-28 | 2024-08-28 | Not Started
15 | 73 | SD | Brokerage Module | Brokerage Module |  | Module Pool | Complex | Shubham Parashar | Kaushal Sharma | [5 empty] | 2024-08-27 | 2024-08-28 | Not Started |  | 2024-08-29 | 2024-08-31 | Not Started | 1 | 2024-08-31 | 2024-09-01 | Not Started | 4 | 2024-09-02 | 2024-09-06 | Not Started
[27 empty] | Maximum | 2024-09-29
[27 empty] | Minimum | 2024-08-26
Formulas:
Start Date = [End Date]+1
Start Date = [Start Date, row above]
End Date = [Start Date]
End Date = [Start Date]+[CTM Testing]