## Testing
2024-10-12 | Discussion | Status
|  | Done | Excel Template | On download template add date format in template header(dd.mm.yyyy)
|  | Done |  | Fomarting excel
|  | Done |  | Consultant name should be emp_code - emp_name in template
|  |  | Submit_Plan | Allow to changes consulant/Abaper
|  | Done |  | Donwload Link active on mouse hover
|  | Done |  | Email Option need to add for CTM case
|  | Done |  | Add option to view/update uploaded ABAP object (if its draft)
After ABAP object plan submission show notification for PRM
Mail Body required
|  |  | ABAP_Object_Tracker_Plan_View.aspx | show pending & approved ABAP object PM.
|  |  | ABAP_Object_Tracker_Index | PM is login and his abap object is not submitted then change FS, ABAP, CTM link should not be display
Need to changes button text As View Abap Object Plan
|  |  | ABAP_Object_Tracker_PendingList | Show PM Name in gridview
|  |  | ABAP_Object_Tracker_Plan_for_Approval | Show Approver grid after remark
|  |  | ABAP_Object_Tracker_ApprovedList | Show Project Manager as column head and its values should its name
|  |  | Common | Whenever we show project location need to show his PM name
|  |  | ABAP_Object_Tracker_Plan_View | Project Manager name should be display
|  | Done | ABAP_Object_Tracker_Change_FS_Consultant | Remarks field need to display below
|  | Done | ABAP_Object_Tracker_Change_Status_RGS_FS_ABAP_Test | All data need to show in popup

## DB Table Schema
ABAP Object Tracking Table Schema's
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_Mst_Module | ModuleId | int |  | PK
| ModuleCode | varchar | 5
| ModuleName | varchar | 50
| Isactive | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_Mst_FCategory | FCategoryId | int |  | PK
| FCategoryName | varchar | 15
| Isactive | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_Mst_Priority | PriorityId | int |  | PK
| PriorityName | varchar | 15
| Isactive | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_Mst_Complexity | ComplexityId | int |  | PK
| ComplexityName | varchar | 10
| Isactive | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_Mst_Status | StatusId | int |  | PK
| StatusName | varchar | 50
| IsRGS | bit
| IsFS | bit
| IsABAPDev | bit
| IsHBTTest | bit
| IsCTMTest | bit
| IsUATSignOff | bit
| Isactive | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_Template | ABAPODTemplateId | int |  | PK
| ProjectLocation | int |  | FK
| ModuleId | int |  | FK
| Interface | varchar | 15
| Development_Desc | varchar | 200
| Scope | varchar | 10
| FCategoryId | int |  | FK
| Priority | int
| PriorityId | int |  | FK
| ComplexityId | int |  | FK
| IsApprovedStatus | int
| Remark | varchar | 100 |  | Submit the template, Send for approval, Template Approved
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_GeneralDetails | ABAPODId | int |  | PK
| ProjectLocation | int |  | FK
| ModuleId | int |  | FK
| Interface | varchar | 15
| Development_Desc | varchar | 200
| Scope | varchar | 10
| FCategoryId | int |  | FK
| Priority | int
| PriorityId | int |  | FK
| ComplexityId | int |  | FK
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_RGSDetails | RGSDetailsId | int |  | PK
| ABAPODId | int |  | FK
| ConsultantId | int |  | FK
| PlannedPrepStart | datetime
| PlannedPrepFinish | datetime
| PlannedSubmit | datetime
| PlannedApprove | datetime
| RevActualPrepStart | datetime |  |  | Need to confirm make separate or one field for revised & Actual date
| RevActualPrepFinish | datetime |  |  | Need to confirm make separate or one field for revised & Actual date
| RevActualSubmit | datetime |  |  | Need to confirm make separate or one field for revised & Actual date
| RevActualApprove | datetime |  |  | Need to confirm make separate or one field for revised & Actual date
| RGSStatus | int
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_RGSDetails_Logs | RGSDetailsLogId | int |  | PK
| RGSDetailsId | int |  | FK
| ABAPODId | int |  | FK
| ConsultantId | int |  | FK
| StartDate | datetime
| EndDate | datetime
| RGSStatus | int
| LogDescription | varchar | 100 |  | it’s a default while inserting log i.e. RGS plan Start, RGS plan End etc.
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_FSDetails | FSDetailsId | int |  | PK
| ABAPODId | int |  | FK
| ConsultantId | int |  | FK
| PlannedStart | datetime
| PlannedFinish | datetime
| RevisedStart | datetime
| RevisedFinish | datetime
| ActualStart | datetime
| ActualFinish | datetime
| FSStatus | int
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_FSDetails_Logs | FSDetailsLogId | int |  | PK
| FSDetailsId | int |  | FK
| ABAPODId | int |  | FK
| ConsultantId | int |  | FK
| StartDate | datetime
| EndDate | datetime
| FSStatus | int
| LogDescription | varchar | 100 |  | it’s a default while inserting log i.FS plan Start, FS plan End etc.
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_ABAPerDetails | ABAPDetailsId | int |  | PK
| ABAPODId | int |  | FK
| ActPln_EmpCode | int |  | FK
| DevDuaration | varchar | 5
| PlannedStart | datetime
| PlannedFinish | datetime
| RevisedStart | datetime
| RevisedFinish | datetime
| ActualStart | datetime
| ActualFinish | datetime
| ABAPDevStatus | int
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_ABAPerDetails_Logs | ABAPDetailsLogId | int |  | PK
| ABAPDetailsId | int |  | FK
| ABAPODId | int |  | FK
| ActPln_EmpCode | int |  | FK
| DevDuaration | varchar | 5
| StartDate | datetime
| EndDate | datetime
| ABAPDevStatus | int
| LogDescription | varchar | 100 |  | it’s a default while inserting log i.e.ABA Dev plan Start, ABA Dev plan End etc.
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_ABAPChangeLog | ABAPChangeLogId | int |  | PK
| ABAPODId | int |  | FK
| Old_ABAP_EmpCode | varchar | 10 | FK
| New_ABAP_EmpCode | varchar | 10 | FK
| Remark | varchar | 100
| CreatedOn | datetime
| CreatedBy | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_HBTTestDetails | HBTDetailsId | int |  | PK
| ABAPODId | int |  | FK
| ConsultantId | int |  | FK
| PlannedStart | datetime
| PlannedFinish | datetime
| RevisedStart | datetime
| RevisedFinish | datetime
| ActualStart | datetime
| ActualFinish | datetime
| HBTTestStatus | int
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_HBTTestDetailsLogs | HBTDetailsLogId | int |  | PK
| HBTDetailsId | int |  | FK
| ABAPODId | int |  | FK
| ConsultantId | int |  | FK
| StartDate | datetime
| EndDate | datetime
| HBTTestStatus | int
| LogDescription | varchar | 100 |  | it’s a default while inserting log i.e.HBT Testing plan Start, HBT Testing plan End etc.
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_CTMTestDetails | CTMDetailsId | int |  | PK
| ABAPODId | int |  | FK
| CTMName | varchar | 50
| TrainingStart | datetime
| TrainingEnd | datetime
| PlannedStart | datetime
| PlannedFinish | datetime
| RevisedStart | datetime
| RevisedFinish | datetime
| ActualStart | datetime
| ActualFinish | datetime
| CTMStatus | int |  | FK
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
| Updated_On | datetime
| Updated_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_CTMTestDetailsLogs | CTMDetailsLogId | int |  | PK
| CTMDetailsId | int |  | FK
| ABAPODId | int |  | FK
| CTMName | varchar | 50
| StartDate | datetime
| EndDate | datetime
| CTMStatus | int |  | FK
| LogDescription | varchar | 100 |  | it’s a default while inserting log i.e.CTM Training Start, CTM Training End, CTM Planing start,
| Remark | varchar | 100
| Created_On | datetime
| Created_By | varchar | 10
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_GoLive | GoLiveId | int |  | PK
| GoLivePlannedDate | datetime |  | FK
| GoLiveRevisedDate | datetime | 10
| GoLiveActualDate | datetime
| RPRDStatus | int
| Remark | varchar | 100
| CreatedBy | varchar | 10
| CreatedOn | datetime
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_ConsultantTracking | ConsultanttrackId | int |  | PK
| ConsultantId | int |  | FK
| ActivityType | varchar | 10
| StartDate | datetime
| EndDate | datetime
| Description | varchar | 100
| Remark | varchar | 100
| CreatedBy | varchar | 10
| CreatedOn | datetime
Table Name | Column Name | Data Type | Data Size | PK/FK | Remarks
ABAP_OD_tbl_ConsultantChangeLog | ConsultantChangeLogId | int |  | PK
| ABAPODId | int |  | FK
| Stage | varchar | 10
| Old_Consultant_Id | varchar | 10 | FK
| New_Consultant_Id | varchar | 10 | FK
| Remark | varchar | 100
| Status | varchar | 100
| CreatedBy | varchar | 10
| CreatedOn | datetime

## Sheet2
1 | mail for Sending for ABAP Object Plan approval
| to | PRM
| CC | DH
Subject:[Project Name] ABAP Object Development Plan Submitted for Approval
Dear [Program Manager's Name],
The ABAP Object development plan for the project [Project Name] has been submitted by the [Login Employee] and is now awaiting your review and approval.
please click here to view ABAP Object Plan
auto generated mail
2 | mail for Approve ABAP Obejct Plan
| to | PM
| cc | DH
Subject: [Project Name] ABAP Object Plan Approved
Dear [Project Manager's Name],
This is to inform you that the ABAP Object development plan for the project [Project Name] has been approved by [Program Manager's Name].
please click here to view ABAP Object Plan
3 | mail for Approve ABAP Obejct Plan
| to | PM
| cc | DH
Subject: [Project Name] ABAP Object Plan Rejected
Dear [Project Manager's Name],
This is to inform you that the ABAP Object development plan for the project [Project Name] has been rejected by [Program Manager's Name].
Reason for Rejection:
[Include rejection reason here, if applicable]
Please review the feedback and make the necessary changes before resubmitting the plan for approval.
please click here to view ABAP Object Plan
4 | mail for change consultant
Subject: Assignment as Consultant for [Project Name]
To: [New Consultant's Email]
CC: [Old Consultant's Email]
Dear [New Consultant's Name],
This is to inform you that you have been assigned as the consultant for the project [Project Name]. Please review the project details and coordinate with [Old Consultant's Name], to ensure a smooth transition.
For any pending tasks or additional information, please coordinate with [Old Consultant's Name] and the [project manager].
please click here to view ABAP Object Plan

## Mail Content
PM will Send ABAP Object Plan for Approval
to | PRM
CC | DH
Subject:[Project Name] ABAP Object Development Plan Submitted for Approval
Dear [Program Manager's Name],
The ABAP Object development plan for the project [Project Name] has been submitted by the [Login Employee] and is now awaiting your review and approval.
please click here to view ABAP Object Plan
PRM will approve the ABAP Object Plan
to | PM
cc | DH
Subject: [Project Name] ABAP Object Plan Approved
Dear [Project Manager's Name],
This is to inform you that the ABAP Object development plan for the project [Project Name] has been approved by [Program Manager's Name].
please click here to view ABAP Object Plan
Programer Manager :- to reject the ABAP Object Plan
to | PM
cc | DH
Subject: [Project Name] ABAP Object Plan has been Rejected
Dear [Project Manager's Name],
This is to inform you that the ABAP Object development plan for the project [Project Name] has been Rejected by [Program Manager's Name].
please click here to view ABAP Object Plan
Change FS Status :- if FS Consultant Change status as Complete & send mail to ABAP Developer
to | ABAPer
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [ABAP Name],
This is to inform you that the [FS Consultant Name] has completed the FS of the Object [Object Name].Click the below link to Accept or Not Accept the object.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
please click here to Accept/ Not Accept Object
Change ABAP Status |  | Send mail to FS if ABAP developer Accept the FS
to | FS
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [FS Consultant Name],
This is to inform you that [ABAP Consultant Name] has accepted the Functional Specification (FS) for the object [Object Name].
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
please click here to view Object
Change ABAP Status Send mail to FS if ABAP developer not Accept the FS
to | FS
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [FS Consultant Name],
This is to inform you that [ABAP Consultant Name] has not accepted the Functional Specification (FS) for the object [Object Name].
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object and resubmit for further review
Change ABAP Status Send mail to HBT Testing if ABAP developer development has been completed & send to HBT Testing
to | HBT Testing Consultant
cc | PM,FS Consultant
Subject: [Project Name] ABAP Object - [Object Name]
Dear [HBT Consultant Name],
This is to inform you that [ABAP Consultant Name] has has complete the object [Object Name] development please take the action on this Object.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
Change HBT Testing Status send mail to CTM Testing Consultant if Test cases approved
to | CTM Consultant
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [CTM Testing Consultant Name],
This is to inform you that [HBT Testing Consultant Name] has send the object [Object Name] for Testing please click on below lnk for action.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
to | ABAP Consultant
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [ABAP Consultant Name],
This is to inform you that [HBT Testing Consultant Name] has approved the object [Object Name] please click on link to view the object.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
Change HBT Testing Status send mail to ABAP Consultant if Test case Correction
to | ABAP Consultant
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [ ABAP Consultant Name],
This is to inform you that [HBT Testing Consultant Name] has send for correction the object [Object Name] please review the object & resubmit
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
Change HBT Testing Status send mail to FS Consultant if Test case Correction
to | FS Consultant
cc | PM, ABAP Consultant
Subject: [Project Name] ABAP Object - [Object Name]
Dear [ FS Consultant Name],
This is to inform you that [HBT Testing Consultant Name] has send for correction the object [Object Name] please review the object & resubmit
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
Change CTM Testing Status send mail to PM if CTM Test cases approval
to | PM
cc | PRM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [ PM Name],
This is to inform you that [CTM Testing Consultant Name] has send Test Cases for approval for the object [Object Name] please click on below link for action.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
Change CTM Testing Status send mail to HBT Testing Consultant if Correction
to | HBT Testing Consultant
cc | PM
Subject: [Project Name] ABAP Object - [Object Name]
Dear [ HBT Testing Consultant Name],
This is to inform you that [CTM Testing Consultant Name] has send Test Cases for approval for the object [Object Name] please click on below link for action.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Please click here to view the object.
Change Go-Live Status send mail to PRM
to | FS,ABAP, HBT CTM Consultant
cc | PRM,DH
Subject: [Project Name] ABAP Object - [Object Name]
Dear All,
This is to inform you that Object [Object Name] has been Go-Live.
Object Name | Module | Interface | Plan Start Date | Plan End Date | Revised Start Date | Revised end date
Change Consultant PM -
to | Consultant Name
cc | PRM, old Consultant
Subject: [Project Name] ABAP Object - [Object Name]
Dear [New Consultant Name],
This is to inform you that you have assigned to new object [object name]. Please co-ordinatinate with [old Consultant name].

## DB Table Data
Table Name | ModuleId | ModuleCode | ModuleName | Isactive
ABAP_OD_tbl_Mst_Module | 1 | FICO | SAP FICO | A
| 2 | ABAP | SAP ABAP | A
| 3 | SEM | SAP SEM | A
| 4 | PRA | SAP PRA | A
Table Name | FCategoryId | FCategoryName | Isactive
ABAP_OD_tbl_Mst_FCategory | 1 | Conversion | A
| 2 | Enhancement | A
| 3 | Integration | A
| 4 | Report | A
| 5 | Form | A
Table Name | PriorityId | PriorityName | Isactive
ABAP_OD_tbl_Mst_Priority | 1 | All | A
| 2 | SIT | A
| 3 | Go Live | A
| 4 | Post Go Live | A
| 5 | Hold | A
Table Name | ComplexityId | ComplexityName | Isactive
ABAP_OD_tbl_Mst_Complexity | 1 | Simple | A
| 2 | Medium | A
| 3 | Complex | A
Table Name | ComplexityId | ComplexityName | Isactive
ABAP_OD_tbl_Mst_Complexity | 1 | Simple | A
| 2 | Medium | A
| 3 | Complex | A
Table Name | StatusId | StatusName | IsRGS | IsFS | IsABAPDev | IsHBTTest | IsCTMTest | IsUATSignOff | Isactive
ABAP_OD_tbl_Mst_Status | 1 | NA | 1 | 1 | 0 | 0 | 0 | 0 | A
| 2 | Not Started | 1 | 0 | 1 | 0 | 1 | 0 | A
| 3 | Submitted | 1 | 0 | 0 | 0 | 0 | 1 | A
| 4 | Hold | 1 | 1 | 1 | 1 | 1 | 1 | A
| 5 | Cancelled | 0 | 0 | 1 | 1 | 1 | 0 | A
| 6 | In Process | 0 | 1 | 1 | 1 | 1 | 1 | A
| 7 | Approved | 1 | 0 | 0 | 0 | 1 | 1 | A
| 8 | Completed | 0 | 1 | 1 | 1 | 0 | 0 | A
| 9 | Enhancement | 0 | 0 | 1 | 1 | 0 | 0 | A
| 10 | Functional Testing | 0 | 0 | 1 | 0 | 0 | 0 | A
| 11 | Functional Correction | 0 | 0 | 1 | 1 | 0 | 0 | A
| 12 | CTM Testing | 0 | 0 | 1 | 1 | 0 | 0 | A
| 13 | CTM Correction | 0 | 0 | 1 | 1 | 0 | 0 | A
| 14 | In Correction | 0 | 0 | 0 | 0 | 1 | 0 | A
| 15 | Delay | 0 | 0 | 0 | 0 | 0 | 0 | A
Table Name | ABAPODId | ProjectLocation | ModuleId | Interface | Development_Desc | Scope | FCategoryId | Priority | PriorityId | ComplexityId | IsApprovedStatus | Remark | Created_On | Created_By | Updated_On | Updated_By
ABAP_OD_tbl_Template | 1 | ABL Migrat | 1 | SFDC | BPO Upload Program | SOW | 1 | 1 | 1 | 1 | TRUE |  | 2024-10-10 21:03 | 630930 | NULL | NULL
| 2 | ABL Migrat | 2 | Clear tax | Vendor master upload | HOLD | 2 | 2 | 2 | 2 | TRUE |  | 2024-10-10 21:03 | 630930 | NULL | NULL
| 3 | ABL Migrat | 3 | HDFC/ICICI | Asset Cutover upload Program | Additional | 4 | 2 | 2 | 3 | TRUE |  | 2024-10-10 21:03 | 630930 | NULL | NULL
Table Name | ABAPODId | ProjectLocation | ModuleId | Interface | Development_Desc | Scope | FCategoryId | Priority | PriorityId | ComplexityId | Created_On | Created_By | Updated_On | Updated_By
ABAP_OD_tbl_GeneralDetails | 1 | ABL Migrat | 1 | SFDC | BPO Upload Program | SOW | 1 | 1 | 1 | 1 | 2024-10-10 21:03 | 630930 | NULL | NULL
| 2 | ABL Migrat | 2 | Clear tax | Vendor master upload | HOLD | 2 | 2 | 2 | 2 | 2024-10-10 21:03 | 630930 | NULL | NULL
| 3 | ABL Migrat | 3 | HDFC/ICICI | Asset Cutover upload Program | Additional | 4 | 2 | 2 | 3 | 2024-10-10 21:03 | 630930 | NULL | NULL
Table Name | RGSDetailsId | ABAPODId | ConsultantId | PlannedPrepStart | PlannedPrepFinish | PlannedSubmit | PlannedApprove | RevActualPrepStart | RevActualPrepFinish | RevActualSubmit | RevActualApprove | RGSStatus | Remark | Created_On | Created_By | Updated_On | Updated_By
ABAP_OD_tbl_RGSDetails | 1 | 1 | 630940 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | NULL | NULL | NULL | NULL | 2 | RGS Planned Started | 2024-10-14 21:03 | 630930 | 2024-10-15 21:03 | 630930
| 2 | 2 | 630942 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | NULL | NULL | NULL | NULL |  |  | 2024-10-14 21:03 | 630930 | NULL | NULL
Table Name | RGSDetailsLogId | RGSDetailsId | ABAPODId | ConsultantId | StartDate | EndDate | RGSStatus | LogDescription | Remark | Created_On | Created_By
ABAP_OD_tbl_RGSDetails_Logs | 1 | 1 | 1 | 630940 | 2024-10-16 | 2024-10-17 | 2 | Planned Preparation Started | RGS Planned Started | 2024-10-15 | 630930
| 2 | 1 | 1 | 630940 | 2024-10-18 | NULL | 2 | Planned Preparation Submitted | RGS Planned Submit | 2024-10-15 | 630930
| 3 | 1 | 1 | 630940 | 2024-10-19 | NULL | 2 | Planned Preparation Approved | RGS Planned aprroved | 2024-10-15 | 630930
| 4 | 1 | 1 | 630940 | 2024-10-20 | 2024-10-21 | 2 | Revised Preparation Started | RGS Revised Start | 2024-10-15 | 630930
| 5 | 1 | 1 | 630940 | 2024-10-22 | NULL | 2 | Revised Preparation Submitted | RGS Revised Submit | 2024-10-15 | 630930
| 6 | 1 | 1 | 630940 | 2024-10-23 | NULL | 2 | Revised Preparation Approved | RGS Revised Approved | 2024-10-15 | 630930
| 7 | 1 | 1 | 630940 | 2024-10-24 | 2024-10-25 | 6 | Actual Preparation Started | RGS Revised Start | 2024-10-15 | 630930
| 8 | 1 | 1 | 630940 | 2024-10-26 | NULL | 6 | Actual Preparation Submitted | RGS Revised Submit | 2024-10-15 | 630930
| 9 | 1 | 1 | 630940 | 2024-10-27 | NULL | 8 | Actual Preparation Approved | RGS Revised Approved | 2024-10-15 | 630930
Table Name | FSDetailsId | ABAPODId | ConsultantId | PlannedStart | PlannedFinish | RevisedStart | RevisedFinish | ActualStart | ActualFinish | FSStatus | Remark | Created_On | Created_By | Updated_On | Updated_By
ABAP_OD_tbl_FSDetails | 1 | 1 | 630940 | 2024-10-20 | 2024-10-22 | NULL | NULL | NULL | NULL | 2 | FS Planned Initiated | 2024-10-14 21:03 | 630930 | NULL | NULL
| 2 | 2 | 630940 | 2024-10-21 | 2024-10-23 | NULL | NULL | NULL | NULL | 2 | FS Planned Started | 2024-10-14 21:03 | 630930 | NULL | NULL
Table Name | FSDetailsLogId | FSDetailsId | ABAPODId | ConsultantId | StartDate | EndDate | FSStatus | LogDescription | Remark | Created_On | Created_By
ABAP_OD_tbl_FSDetails_Logs | 1 | 1 | 1 | 630940 | 2024-10-20 | 2024-10-22 | 2 | Planned Initiated | FS Planned Initiated | 2024-10-14 21:03 | 630930
| 2 | 1 | 1 | 630940 | 2024-10-20 | 2024-10-22 | 2 | Planned Started | FS Planned Started | 2024-10-14 21:03 | 630930
| 3 | 1 | 1 | 630940 | 2024-10-22 | NULL | 2 | Planned Finished | FS Planned Finished | 2024-10-14 21:03 | 630930
| 4 | 1 | 1 | 630940 | 2024-10-23 | 2024-10-26 | 2 | Revised initiated | FS Revised Initiated | 2024-10-14 21:03 | 630930
| 5 | 1 | 1 | 630940 | 2024-10-23 | 2024-10-26 | 2 | Revised Started | FS Revised Started | 2024-10-14 21:03 | 630930
| 6 | 1 | 1 | 630940 | 2024-10-26 | NULL | 2 | Revied Finished | FS Revised Finished | 2024-10-14 21:03 | 630930
| 7 | 1 | 1 | 630940 | 2024-10-27 | 2024-10-28 | 2 | Actual Initiated | FS Actual Initiated | 2024-10-14 21:03 | 630931
| 8 | 1 | 1 | 630940 | 2024-10-27 | 2024-10-28 | 6 | Actual Started | FS Actual Started | 2024-10-14 21:03 | 630932
| 9 | 1 | 1 | 630940 | 2024-10-28 |  | 8 | Actual Finished | FS Actual Finished | 2024-10-14 21:03 | 630933
Table Name | ABAPDetailsId | ABAPODId | ActPln_EmpCode | DevDuaration | PlannedStart | PlannedFinish | RevisedStart | RevisedFinish | ActualStart | ActualFinish | ABAPDevStatus | Remark | Created_On | Created_By | Updated_On | Updated_By
ABAP_OD_tbl_ABAPerDetails | 1 | 1 | 630942 | 2 | 2024-10-29 | 2024-10-31 | NULL | NULL | NULL | NULL | 2 | ABAP Dev Initiated | 2024-10-15 21:03 | 630930 | NULL | NULL
| 2 | 2 | 630942 | 2 | 2024-11-01 | 2024-11-03 | NULL | NULL | NULL | NULL | 2 | ABAP Dev Initiated | 2024-10-15 21:03 | 630930 | NULL | NULL
Table Name | ABAPDetailsLogId | ABAPDetailsId | ABAPODId | ActPln_EmpCode | DevDuaration | StartDate | EndDate | ABAPDevStatus | LogDescription | Remark | Created_On | Created_By
ABAP_OD_tbl_ABAPerDetails_Logs | 1 | 1 | 2 | 630942 | 2 | 2024-10-29 | 2024-10-31 | 2 | Planned Dev Initiated | ABAP Planned Dev Initiated | 2024-10-15 21:03 | 630930
| 2 | 1 | 2 | 630942 | 2 | 2024-10-29 | 2024-10-31 | 2 | Planned Dev Started | ABAP Planned Dev Started | 2024-10-15 21:03 | 630930
| 3 | 1 | 2 | 630942 | 2 | 2024-10-31 | NULL | 2 | Planned Dev Finished | ABAP Planned Dev Finished | 2024-10-15 21:03 | 630930
| 4 | 1 | 2 | 630943 | 2 | 2024-11-02 | 2024-11-04 | 2 | Revised Dev Initiated | ABAP Revised Dev Initiated | 2024-10-15 21:03 | 630930
| 5 | 1 | 2 | 630943 | 2 | 2024-11-02 | 2024-11-04 | 2 | Revised Dev Started | ABAP Revised Dev Starter | 2024-10-15 21:03 | 630930
| 6 | 1 | 2 | 630943 | 2 | 2024-11-04 | NULL | 2 | Revised Dev Finished | ABAP Revised Dev Finished | 2024-10-15 21:03 | 630930
Table Name | ABAPChangeLogId | ABAPODId | Old_ABAP_EmpCode | New_ABAP_EmpCode | Remark | CreatedOn | CreatedBy
ABAP_OD_tbl_ABAPChangeLog | 1 | 2 | 630942 | 630943 | ABAPer Changed | 2024-10-15 21:03 | 630930
Table Name | HBTDetailsId | ABAPODId | ConsultantId | PlannedStart | PlannedFinish | RevisedStart | RevisedFinish | ActualStart | ActualFinish | HBTTestStatus
ABAP_OD_tbl_HBTTestDetails | 1 | 2 | 630940 | 2024-11-05 | 2024-11-06 | NULL | NULL | NULL | NULL | 2
| 2 | 2 | 630940 | 2024-11-05 | 2024-11-06 | NULL | NULL | NULL | NULL | 2
Table Name | HBTDetailsLogId | HBTDetailsId | ABAPODId | ConsultantId | StartDate | EndDate | HBTTestStatus | LogDescription | Remark | Created_On | Created_By
ABAP_OD_tbl_HBTTestDetailsLogs | 1 | 1 | 2 | 630940 | 2024-11-05 | 2024-11-06 | 2 | Planned Testing Initiated | HBT Planned Testing Initiated | 2024-10-15 21:03 | 630930
| 2 | 1 | 2 | 630940 | 2024-11-05 | 2024-11-06 | 2 | Planned Testing Started | HBT Planned Testing Started | 2024-10-15 21:03 | 630930
| 3 | 1 | 2 | 630940 | 2024-11-06 | NULL | 2 | Planned Testing Finished | HBT Planned Testing Finished | 2024-10-15 21:03 | 630930
| 4 | 1 | 2 | 630940 | 2024-11-07 | 2024-11-08 | 2 | Revised Testing Initiated | HBT Revised Testing Initiated | 2024-10-15 21:03 | 630930
| 5 | 1 | 2 | 630940 | 2024-11-07 | 2024-11-08 | 2 | Revised Testing Started | HBT Revised Testing Started | 2024-10-15 21:03 | 630930
| 6 | 1 | 2 | 630940 | 2024-11-08 | NULL | 2 | Revised Testing Finished | HBT Revised Testing Finished | 2024-10-15 21:03 | 630930
| 7 | 1 | 2 | 630940 | 2024-11-09 | 2024-11-10 | 2 | Actual Testing Initiated | HBT Actual Testing Initiated | 2024-10-15 21:03 | 630930
| 8 | 1 | 2 | 630940 | 2024-11-09 | 2024-11-10 | 2 | Actual Testing Started | HBT Actual Testing Started | 2024-10-15 21:03 | 630930
| 9 | 1 | 2 | 630940 | 2024-11-10 | NULL | 2 | Actual Testing Finished | HBT Actual Testing Finished | 2024-10-15 21:03 | 630930
Table Name | CTMDetailsId | ABAPODId | CTMName | TrainingStart | TrainingEnd | PlannedStart | PlannedFinish | RevisedStart | RevisedFinish | ActualStart | ActualFinish | CTMStatus | Remark | Created_On | Created_By | Updated_On | Updated_By
ABAP_OD_tbl_CTMTestDetails | 1 | 1 | CTM1 | NULL | NULL | 2024-11-11 | 2024-11-12 | NULL | NULL | NULL | NULL | 2 | HTB Testing Initiated | 2024-10-15 21:03 | 630930 | NULL | NULL
| 2 | 2 | CTM2 | NULL | NULL | 2024-11-11 | 2024-11-12 | NULL | NULL | NULL | NULL | 2 | HTB Testing Initiated | 2024-10-15 21:03 | 630930 | NULL | NULL
Table Name | CTMDetailsLogId | CTMDetailsId | ABAPODId | CTMName | StartDate | EndDate | CTMStatus | LogDescription | Remark | Created_On | Created_By
ABAP_OD_tbl_CTMTestDetailsLogs | 1 | 1 | 1 | CTM1 | 2024-11-11 | 2024-11-12 | 2 | Planned Testing Initiated | CTM Planned Testing Initiated
| 2 | 1 | 1 | CTM1 | 2024-11-11 | 2024-11-12 | 2 | Planned Testing started | CTM Planned Testing Started
| 3 | 1 | 1 | CTM1 | 2024-11-12 | NULL | 2 | Planned Testing Finished | CTM Planned Testing Finished
| 4 | 1 | 1 | CTM1 | 2024-11-11 | 2024-11-12 | 2 | Training Initiated | CTM Training Initiated
| 5 | 1 | 1 | CTM1 | 2024-11-11 | 2024-11-12 | 2 | Training started | CTM Training Started
| 6 | 1 | 1 | CTM1 | 2024-11-12 | NULL | 2 | Training Finished | CTM Training Finished
| 7 | 1 | 1 | CTM1 | 2024-11-11 | 2024-11-12 | 2 | Actual Testing Initiated | CTM Actual Testing Initiated
| 8 | 1 | 1 | CTM1 | 2024-11-11 | 2024-11-12 | 2 | Actual Testing started | CTM Actual Testing Started
| 9 | 1 | 1 | CTM1 | 2024-11-12 | NULL | 2 | Actual Testing Finished | CTM Actual Testing Finished

## DPR Summary
Project : ASHWIN SHETH GROUP_Rise with SAP S/4HANA Implementation
[22 empty] | AS On: | 2024-12-31
Daily Progress Report
| Module | Development Objects |  |  |  | On Hold |  | Reusable |  | RGS Status |  | FS Status |  | Development Status |  |  |  |  | Functional testing Status |  |  | CTM testing Status |  | Moved To PRD
[10 empty] | Plan | Actual | Plan | Actual | Plan | Actual |  |  |  | Plan | Actual |  | Plan | Actual | Actual
|  | Total | SIT | Go-Live | Post Go-Live | SIT + Go-Live | Post Go-Live | SIT + Go-Live | Post Go-Live | Complete | Complete | Complete | Complete | Complete | Complete - Reusable | Complete - Fresh | In Progress - Reusable | In Progress - Fresh | Complete | Complete | In Progress | Complete | Complete | Complete
7 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PS | 10 | 3 | 7 | 0 | 0 | 0 | 5 | 0 | 10 | 10 | 10 | 10 | 10 | 4 | 4 | 0 | 1 | 10 | 5 | 0 | 10 | 4 | 4
20 | SD | 48 | 39 | 5 | 4 | 0 | 2 | 15 | 1 | 48 | 37 | 48 | 42 | 48 | 15 | 28 | 0 | 2 | 48 | 36 | 3 | 44 | 14 | 14
8 | MM | 39 | 23 | 11 | 5 | 0 | 2 | 19 | 1 | 39 | 34 | 39 | 35 | 39 | 19 | 15 | 1 | 2 | 39 | 31 | 1 | 34 | 31 | 31
| DMS | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
0 | HCM | 5 | 1 | 4 | 0 | 0 | 0 | 3 | 0 | 5 | 2 | 5 | 5 | 5 | 3 | 2 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 0
13 | FICO | 26 | 14 | 12 | 0 | 0 | 0 | 7 | 0 | 26 | 26 | 26 | 24 | 26 | 6 | 15 | 0 | 3 | 26 | 16 | 0 | 26 | 12 | 12
13 | TRM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 129 | 80 | 40 | 9 | 0 | 4 | 49 | 2 | 129 | 109 | 129 | 116 | 129 | 47 | 65 | 1 | 8 | 129 | 93 | 4 | 120 | 61 | 61
|  |  | 120 | [11 empty] | 112 |  | 9
| Shortfall (W/o HOLD) | [8 empty] | 16 |  | 9 |  | 4 |  |  |  |  | 23 |  |  | 59
Notes:
1
2
Key Highlights / Concerns:
1
2
3
4
ABAP Resource

## SIT (hidden)
Sr No | Module | Object No | Development Description | WRICEF Category | Priority | Complexity | Functional Consultant | RGS Planned Date | RGS Actual Date | RGS Status | FS Planned Date | FS Actual Date | FS Status | Technical Consultant | Developement Planned start Date | Developemnt Actual Start Date | Developemnt Planned Finish Date | Development Actual Finish Date | Development Status | HBT Testing Status | CTM Testing Status | UAT Sign OFF | BPO / CTM Signature | PRD Status | Department | Remark
1 | PS | KCC_CN_PS_02 | Base Planning Object Upload | Conversion | SIT | Medium | Pranay Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
2 | PS | KCC_CN_PS_03 | Execution BOQ Master Upload | Conversion | SIT | Medium | Pranay Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
3 | PS | KCC_CN_PS_04 | Cost Plan Upload | Conversion | SIT | Complex | Pranay Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
4 | PS | KCC_EN_PS_05 | Work Plan | Enhancement | SIT | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
5 | PS | KCC_EN_PS_09 | DPR Entry | Enhancement | SIT | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
6 | PS | KCC_RP_PS_11 | Cost Plan version Comparison with Actual (Qty & Amount) | Report | Go Live | Complex | Pranay Reddy | 2022-07-27 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
7 | PS | KCC_EN_PS_15 | Conversion of Work order line items to Client bill Qty Through coefficient in DPR report | Enhancement | Go Live | Medium | Pranay Reddy | 2022-07-27 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
8 | PS | KCC_WF_PS_16 | DPR has an Workflow of Approval | Workflow | SIT | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
9 | FI | KCC_EN_FI_01 | Validation on GSTN Number in Vendor Master | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
10 | FI | KCC_EN_FI_04 | Additional Tab in GL Master data | Enhancement | SIT | Complex | Venkat Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
11 | FI | KCC_EN_FI_07 | Capture GSTN Number in FB70 Screen | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
12 | FI | KCC_EN_FI_09 | Validation on un-registered vendor invoice(Limit-20L) | Enhancement | SIT | Simple | Venkat Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
13 | FI | KCC_EN_FI_10 | Validation on without PAN Vendor Payment(Limit-50K):F-53 | Enhancement | SIT | Simple | Venkat Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
14 | FI | KCC_EN_FI_11 | Validation on one time vendor invoice(Limit-10K) | Enhancement | SIT | Simple | Venkat Reddy | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
15 | FI | KCC_EN_FI_12 | Display GSTN Number in FB60 Screen | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
16 | FI | KCC_EN_FI_13 | Display GSTN Number in MIRO Screen | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
17 | FI | KCC_EN_FI_14 | Validation on composition vendor invoice bookings | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
18 | FI | KCC_EN_FI_16 | Validation/Check for duplicate vendor invoice(FB60/MIRO) | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
19 | FI | KCC_RP_FI_24 | Tax Code Change Restriction on MIRO | Enhancement | SIT | Medium | Venkat Reddy | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
20 | MM | KCC_FM_MM_01 | Purchase requisition Print | Form | SIT | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
21 | MM | KCC_FM_MM_03 | Service PO | Form | SIT | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
22 | MM | KCC_FM_MM_04 | Service/Work order PR print | Form | Go Live | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
23 | MM | KCC_FM_MM_06 | Work Order Print | Form | SIT | Simple | Abhishek Godse | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
24 | MM | KCC_EN_MM_07 | WO terms & condition Header | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
25 | MM | KCC_EN_MM_08 | Materials _T&C_Materials to be issued & Recovery | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
26 | MM | KCC_EN_MM_09 | Advance request & its recovery | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
27 | MM | KCC_EN_MM_10 | Wo Terms & condition _Item Condition(Escalation) | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
28 | MM | KCC_EN_MM_11 | RA BILL Preparation_Work done quantity confirmation against Work order with SES posting | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
29 | MM | KCC_EN_MM_13 | Material recovery against Work done | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
30 | MM | KCC_EN_MM_16 | Posting of invoice,recovery,debit note,credit note,etc document along with Payment abstract screen | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
31 | MM | KCC_EN_MM_18 | Work order & vendor entry while material issue to Subcon & Restrict material issue against WO | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
32 | MM | KCC_EN_MM_24 | In Migo Screen Input In Goods Receipt Note(GRN) at MIGO screen Required Fields are Royalty No, Royalty Date-Item Wise, Royality Qty, Royality Location, E-way Bill No,E-way Bill date, LR Number, LR Date, Security Gate Entry Number, Gate Entry Number date, DMR Number, DMR Date , Custom field for Rack & Bin, Challan no., challan date, Invoice no., invoice date, RST No. | Enhancement | SIT | Simple | Abhishek Godse | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
33 | MM | KCC_EN_MM_25 | DMR Entry process | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-26 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
34 | MM | KCC_EN_MM_27 | Material reservation Process required Supplier code | Enhancement | Go Live | Complex | Abhishek Godse | 2022-07-28 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
35 | MM | KCC_EN_MM_35 | Quantity check valiadtion in PR with WBS | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
36 | MM | KCC_EN_MM_36 | Stock overview at PR screen | Enhancement | SIT | Medium | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
37 | MM | KCC_EN_MM_39 | Custom Workflow for PR | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase/Store
38 | MM | KCC_EN_MM_42 | Item text field mandatory for the material for which technical specifications are required in PR | Enhancement | SIT | Medium | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
39 | MM | KCC_EN_MM_44 | Notifiction if class A materials stock falls below defined safety level along with screen. | Enhancement | SIT | Complex | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
40 | MM | KCC_EN_MM_50 | Addition fields in PO to capture FOC value | Enhancement | SIT | Medium | Abhishek Godse | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase /P&M
41 | MM | KCC_WF_MM_52 | Custom Workflow for PO | Workflow | SIT | Medium | Abhishek Godse | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
42 | HCM | KCC_IN_HCM_11 | RFC SAP to Time Watch | Interface | SIT | Simple | Muzammil Ansari | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
43 | HCM | KCC_IN_HCM_12 | RFC Time Watch to SAP | Interface | SIT | Simple | Muzammil Ansari | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
44 | SD | KCC_WF_SD_01 | Sales Order approval Process | Workflow | Go Live | Medium | Nitin Kumar | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Client Billing
45 | PM | KCC_EN_PM_02 | Custom screen for installation and dismantle of Tyre and battery | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-26 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
46 | PM | KCC_EN_PM_03 | New custom fields (Requested Plant, Transfer/Hire/Purchase etc ) are required in notification screen | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
47 | PM | KCC_RP_PM_09 | Equipment & Plant Utilization, Performance & Cost Analysis Based upon the Log Entry of equipments, Utilization (Productivity) & performance report will be required to generate. Period wise for a Plant, group of Plants & for individual Equipment. | Report | Go Live | Complex | Prateek Srivastav | 2022-07-27 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
48 | PM | KCC_EN_PM_10 | Auto assignment of Settlement Rule in Equipment Consumption Order as per Equipment Log Entry (CO Entry posting WBS wise ) | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-25 |  | Not Submitted | 2022-07-25 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
49 | PM | KCC_EN_PM_11 | A common Log Entry (Plant/Equipment) screen for capturing Hours, KM, Energy Hour Meter reading etc. of own equipments & Plant & LMV | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-28 |  | Not Submitted | 2022-08-01 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
50 | PM | KCC_EN_PM_12 | Auto Creation of Consumption order | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
51 | PM | KCC_EN_PM_14 | Custom table to maintain the hiring rates and condition | Enhancement | SIT | Simple | Prateek Srivastav | 2022-07-26 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
52 | PM | KCC_EN_PM_15 | Module Pool for Maintainance Plan | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-27 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
53 | PM | KCC_EN_PM_16 | Scheduling of Maintainace Plan | Enhancement | SIT | Medium | Prateek Srivastav | 2022-07-28 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
54 | PM | KCC_EN_PM_17 | Auto Generation of Maintainance Order from Maintainance Plan | Enhancement | SIT | Complex | Prateek Srivastav | 2022-07-28 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical

## Go Live (hidden)
Sr No | Module | Object No | Development Description | WRICEF Category | Priority | Complexity | Functional Consultant | RGS Planned Date | RGS Actual Date | RGS Status | FS Planned Date | FS Actual Date | FS Status | Technical Consultant | Developement Planned start Date | Development Actual Start Date | Developemnt Planned Finish Date | Development Actual Finish Date | Development Status | HBT Testing Status | CTM Testing Status | CTM Testing Status | UAT Sign OFF | BPO / CTM Signature | PRD Status | Department | Remark
1 | PS | KCC_EN_PS_17 | DPR punching Qty will be Validated against Balance Work order Qty +PR Qty | Enhancement | Go Live | Medium | Pranay Reddy | 2022-07-26 |  | Not Submitted | 2022-08-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Planning
2 | FI | KCC_IN_FI_21 | Payment Interface | Interface | Go Live | Complex | Venkat Reddy | 2022-08-06 |  | Not Submitted | 2022-08-06 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
3 | FI | KCC_RP_FI_22 | Payment Interface Report | Report | Go Live | Complex | Venkat Reddy | 2022-08-06 |  | Not Submitted | 2022-08-09 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
4 | FI | KCC_RP_FI_26 | GST Credit Report | Report | Go Live | Medium | Venkat Reddy | 2022-08-02 |  | Not Submitted | 2022-08-03 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
5 | FI | KCC_RP_FI_26 | Vendor Payment Process | Report | Go Live | Complex | Venkat Reddy | 2022-08-03 |  | Not Submitted | 2022-08-07 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
6 | FI | KCC_RP_FI_27 | Trial Balance report | Report | Go Live | Complex | Venkat Reddy | 2022-08-06 |  | Not Submitted | 2022-08-10 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
7 | FI | KCC_RP_FI_30 | Invoice Print (FB70) | Enhancement | Go Live | Simple | Venkat Reddy | 2022-08-01 |  | Not Submitted | 2022-08-03 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Account
8 | MM | KCC_FM_MM_02 | Purchase Order Print | Form | Go Live | Simple | Abhishek Godse | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Purchase
9 | MM | KCC_FM_MM_15 | Material Issue & Return (Loan Basis) | Form | Go Live | Complex | Abhishek Godse | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Store
10 | MM | KCC_FM_MM_17 | Transportation PO | Form | Go Live | Simple | Abhishek Godse | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Purchase
11 | MM | KCC_FM_MM_22 | Material Rejection Note | Form | Go Live | Simple | Abhishek Godse | 2022-08-03 |  | Not Submitted | 2022-08-04 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Store
12 | MM | KCC_FM_MM_51 | QR code print for Materials | Form | Go Live | Medium | Abhishek Godse | 2022-08-03 |  | Not Submitted | 2022-08-05 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Store
13 | HCM | KCC_RP_HCM_13 | Salary Register Report | Report | Go Live | Medium | Muzammil Ansari | 2022-07-25 |  | Not Submitted | 2022-07-26 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
14 | HCM | KCC_RP_HCM_14 | Salary Hold/Release Report | Report | Go Live | Simple | Muzammil Ansari | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
15 | HCM | KCC_RP_HCM_15 | Bank Csv file report | Report | Go Live | Medium | Muzammil Ansari | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
16 | HCM | KCC_CN_HCM_16 | Earning & Deduction Upload | Conversion | Go Live | Simple | Muzammil Ansari | 2022-07-22 |  | Not Submitted | 2022-07-23 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
17 | HCM | KCC_RP_HCM_17 | Attendance Report | Report | Go Live | Simple | Muzammil Ansari | 2022-07-26 |  | Not Submitted | 2022-07-27 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
18 | HCM | KCC_FM_HCM_18 | Form 16 | Form | Go Live | Simple | Muzammil Ansari | 2022-07-27 |  | Not Submitted | 2022-07-28 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | HR
19 | SD | KCC_FM_SD_02 | Project Sale Invoice Print (EPC,Item Rate, HAM Contract) | Form | Go Live | Medium | Nitin Kumar | 2022-07-27 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
20 | SD | KCC_FM_SD_03 | Scrap Sale Inovice Print | Form | Go Live | Medium | Nitin Kumar | 2022-07-27 |  | Not Submitted | 2022-07-29 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
21 | SD | KCC_FM_SD_04 | Asset Sale Invoice Print | Form | Go Live | Medium | Nitin Kumar | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
22 | SD | KCC_FM_SD_05 | Material Sale Invoice Print | Form | Go Live | Medium | Nitin Kumar | 2022-07-29 |  | Not Submitted | 2022-07-30 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Client Billing
23 | PM | KCC_RP_PM_01 | Tyre and Battery history report | Report | Go Live | Medium | Prateek Srivastav | 2022-08-01 |  | Not Submitted | 2022-08-02 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical
24 | PM | KCC_FM_PM_04 | Print for Multiple Equipment request | Form | Go Live | Simple | Prateek Srivastav | 2022-08-05 |  | Not Submitted | 2022-08-06 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical
25 | PM | KCC_FM_PM_05 | Reservation Print | Form | Go Live | Simple | Prateek Srivastav | 2022-08-02 |  | Not Submitted | 2022-08-03 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical
26 | PM | KCC_FM_PM_13 | Print for Hired Equipment daily uses and fuel qty | Form | Go Live | Simple | Prateek Srivastav | 2022-08-07 |  | Not Submitted | 2022-08-08 |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  |  | Not Approved | Mechanical

## Post Go Live (hidden)
Sr No | Module | Object No | Development Description | WRICEF Category | Priority | Complexity | Functional Consultant | RGS Planned Date | RGS Actual Date | RGS Status | FS Planned Date | FS Actual Date | FS Status | Technical Consultant | Developement Planned start Date | Development Actual Start Date | Developemnt Planned Finish Date | Development Actual Finish Date | Development Status | HBT Testing Status | CTM Testing Status | UAT Sign OFF | BPO / CTM Signature | PRD Status | Department | Remark
1 | PS | KCC_RP_PS_06 | Planned Monthly Material Report | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
2 | PS | KCC_RP_PS_07 | Planned Monthly Equipment/Labour Report | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
3 | PS | KCC_RP_PS_08 | Planned Monthly Service Report | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
4 | PS | KCC_RP_PS_10 | DPR Detailed report | Report | Post Go Live | Medium | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
5 | PS | KCC_RP_PS_12 | Major material required Vs issued against Subcon work order line item. | Report | Post Go Live | Medium | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Planning
6 | PS | KCC_RP_PS_13 | Unit Rate Comparison BPO Vs Actual | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
7 | PS | KCC_RP_PS_14 | DPR Vs IPC Vs Subcon | Report | Post Go Live | Complex | Pranay Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
8 | QM | KCC_EN_QM_01 | Email trigger for the inspection lot rejection | Enhancement | Post Go Live | Simple | Vijay Dhembare |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | QS
9 | QM | KCC_FM_QM_03 | Customized Inspection Form | Form | Post Go Live | Simple | Vijay Dhembare |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | QS
10 | QM | KCC_FM_QM_04 | Quality Certificate | Form | Post Go Live | Simple | Vijay Dhembare |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | QS
11 | FI | KCC_EN_FI_02 | Additional Tab in Asset Master data | Enhancement | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
12 | FI | KCC_RP_FI_06 | BG Report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
13 | FI | KCC_RP_FI_18 | Asset report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
14 | FI | KCC_EN_FI_19 | Upload Program for BRS | Conversion | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
15 | FI | KCC_FM_FI_20 | Multiple Cheque Printing | Form | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
16 | FI | KCC_RP_FI_23 | GSTR1 (Sales Register) | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
17 | FI | KCC_RP_FI_24 | GSTR2 (Purchase Register) | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
18 | FI | KCC_RP_FI_25 | GST E-Invoice extract report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
19 | FI | KCC_RP_FI_23 | MSME Vendor Reports | Report | Post Go Live | Medium | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
20 | FI | KCC_RP_FI_25 | LC report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
21 | FI | KCC_RP_FI_28 | Balance Sheet Report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
22 | FI | KCC_RP_FI_29 | Cashflow Report | Report | Post Go Live | Complex | Venkat Reddy |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Account
23 | MM | KCC_RP_MM_05 | Purchase Register required with PR to Payment process. | Report | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
24 | MM | KCC_FM_MM_12 | Payment abstract Print | Form | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
25 | MM | KCC_RP_MM_14 | Inventory Analysis report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
26 | MM | KCC_RP_MM_19 | PR to Payment abstract Report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
27 | MM | KCC_FM_MM_20 | RA Bill Print | Form | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Planning
28 | MM | KCC_FM_MM_21 | NON RETURNABLE/ RETURNABLE GATE PASS | Form | Post Go Live | Simple | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
29 | MM | KCC_FM_MM_23 | Backdated PR not to be created (validation on Delivery Date) | Enhancement | Post Go Live | Simple | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
30 | MM | KCC_RP_MM_26 | Asset Spares tracking report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
31 | MM | KCC_EN_MM_28 | Develop RFC to push master data in WBMS - Material | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
32 | MM | KCC_IN_MM_29 | Develop RFC to push master data in WBMS - Vendor (Supplier, Transporter, Subcontractor etc) | Interface | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
33 | MM | KCC_IN_MM_30 | Develop RFC to push master data in WBMS - Plant/Project codes | Interface | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
34 | MM | KCC_IN_MM_31 | Develop RFC to push master data in WBMS - Storage location | Interface | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
35 | MM | KCC_IN_MM_32 | Develop RFC to receive transaction data to SAP | Interface | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
36 | MM | KCC_RP_MM_33 | Store Inventory Report | Report | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
37 | MM | KCC_FM_MM_34 | HSD Register Print | Form | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Hold | Not Started | Not Started |  |  | Not Approved | Store
38 | MM | KCC_EN_MM_37 | Mass PO short closure | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
39 | MM | KCC_EN_MM_38 | PR auto deletion if no action taken for 30 days from the creation date | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
40 | MM | KCC_WF_MM_40 | Validation not to allow backdated PO to be created (expect some users) | Workflow | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
41 | MM | KCC_EN_MM_41 | Notification if no action is taken against the PR for more than 72 hrs from the date of final release | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
42 | MM | KCC_EN_MM_43 | RFQ Comparison screen | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
43 | MM | KCC_EN_MM_45 | Adding custom fields in standard stock reports | Enhancement | Post Go Live | Complex | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
44 | MM | KCC_EN_MM_46 | Mail to vendor along with RFQ print | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
45 | MM | KCC_FM_MM_47 | RFQ Print | Form | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
46 | MM | KCC_EN_MM_48 | Reminder to vendor (RFQ) | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Purchase
47 | MM | KCC_RP_MM_49 | Material Aging report | Report | Post Go Live | Simple | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
48 | MM | KCC_EN_MM_53 | Enhancement in MIGO Screen to update the data from Wigh Bridge | Enhancement | Post Go Live | Medium | Abhishek Godse |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Store
49 | HCM | KCC_FM_HCM_01 | Increment Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
50 | HCM | KCC_FM_HCM_02 | Promotion Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
51 | HCM | KCC_FM_HCM_03 | Reliving Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
52 | HCM | KCC_FM_HCM_04 | Experience Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
53 | HCM | KCC_FM_HCM_05 | Disciplinary Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
54 | HCM | KCC_FM_HCM_06 | Offer Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
55 | HCM | KCC_FM_HCM_07 | Appointment Letter | Form | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
56 | HCM | KCC_EN_HCM_08 | Pop up for Driving License | Enhancement | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
57 | HCM | KCC_EN_HCM_09 | Pop for Confirmation | Enhancement | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
58 | HCM | KCC_EN_HCM_10 | Pop for Retirement | Enhancement | Post Go Live | Simple | Muzammil Ansari |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | HR
59 | SD | KCC_EN_SD_06 | Validation in Scrap Sale for Hazard material to Customer | Enhancement | Post Go Live | Medium | Nitin Kumar |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Client Billing
60 | PM | KCC_WF_PM_06 | Breakdown Mail | Workflow | Post Go Live | Simple | Prateek Srivastav |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
61 | PM | KCC_RP_PM_07 | Schedule Maintenance - Service Schedule Report | Report | Post Go Live | Complex | Prateek Srivastav |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical
62 | PM | KCC_RP_PM_08 | RTO Permit and Insurance schedule report | Report | Post Go Live | Simple | Prateek Srivastav |  |  | Not Submitted |  |  | Not Submitted | Santosh Choudhary |  |  |  |  | Not Started | Not Started | Not Started |  |  | Not Approved | Mechanical

## Plan vs Actual (hidden)
SIT |  | As On Date | 2022-09-03
Module | Total | Hold | Cancelled | Balance | RGS Status till 3rd Sep |  | FS Status till 3rd Sep |  | Development Status till 3rd Sep |  | Functional testing Status till 3rd Sep |  | CTM testing Status till 3rd Sep
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 6 | 0 | 0 | 6 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 6 | 0 | 0 | 6 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Go Live |  | As On Date | 2022-09-03
Module | Total | Hold | Cancelled | Balance | RGS Status |  | FS Status |  | Development Status till 25th Aug |  | Functional testing Status till 22nd Aug |  | CTM testing Status till 22nd Aug
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 4 | 0 | 0 | 4 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 4 | 0 | 0 | 4 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a
Post Go Live |  | As On Date | 2022-09-01
Module | Total | Hold | Cancelled | Balance | RGS Status |  | FS Status |  | Development Status till 25th Aug |  | Functional testing Status till 22nd Aug |  | CTM testing Status till 22nd Aug
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 4 | 3 | 0 | 1 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 5 | 2 | 0 | 3 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 9 | 5 | 0 | 4 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall
Module | Total | Hold | Cancelled | Balance | RGS Status |  | FS Status |  | Development Status |  | Functional testing Status till 22nd Aug |  | CTM testing Status till 22nd Aug
[5 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
PS | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SD | 4 | 3 | 0 | 1 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MM | 5 | 2 | 0 | 3 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM | 10 | 0 | 0 | 10 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PP | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HCM | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FI | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 19 | 5 | 0 | 14 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet1 (hidden)
Module | Development description | WRICEF Type | Priority | Complexity | Reusability | Project | Priority 2
PS | WBS, Network, Activity, Mileston Upload Program | Conversion | Go-Live | Simple | YES | Mecon | Must Have
PS | BPO Upload Program | Conversion | Go-Live | Simple | YES | Sunteck | Must Have
PS | Unit Cost Plan Upload Program | Conversion | Go-Live | Simple | YES | Sunteck | Must Have
PS | Budget Approval Procedure & document attachment compulsary | Workflow | SIT | Complex |  |  | Must Have
PS | Budget Exceed mail trigger | Enhancement | Go-Live | Medium | YES | Sunteck
PS | Milestone Confimation Mail Notification with completion Image & architect certificate attachement | Enhancement | SIT | Complex | YES | Sunteck | Must Have
PS | Project & Work Breakdown Structure sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | WBS & Milestones (Payment milestones plans) sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | Budget sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | Budget Updates / Transfer sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
PS | Link BOQ to WBS in SAP then sync to smartapp | Interface | Go-Live | Complex |  |  | Must Have
DMS | All attached documents in SAP to view in Contentverse DMS | Interface | Go-Live | Complex |  |  | Must Have
FICO | Vendor master upload | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | Asset Cutover upload Program | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | Cutover Template | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | GSTR1 | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | GSTR2 | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | Customer Ageing | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | Vendor Ageing | Report | Go-Live | Simple | YES | Sunteck | Must Have
FICO | Bank Reco Upload Program | Conversion | SIT | Simple | YES | Sunteck | Must Have
FICO | Bank Payment Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Bank Receipt Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Cash Payment Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Cash Receipt Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Journal Voucher | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Customer Tax Invoice (Interest) | Form | SIT | Simple | YES | Sunteck | Must Have
FICO | Customer Receipt Screen | Enhancement | Go-Live | Complex |  |  | Must Have
FICO | Customer Receipt List | Enhancement | Go-Live | Complex |  |  | Must Have
FICO | Project & Plants Mapping table | Enhancement | SIT | Complex |  |  | Must Have
FICO | Interest waiver report | Report | Go-Live | Complex |  |  | Must Have
FICO | Cheque Print | Form | Go-Live | Complex |  |  | Must Have
FICO | Related Party or Intercompany | Report | Post Go-Live | Complex |  |  | Must Have
FICO | Token Amount SFDC-SAP | Interface | SIT | Complex |  |  | Must Have
FICO | Customer Receipts (SFDC) | Interface | SIT | Complex |  |  | Must Have
FICO | Interest Waiver | Interface | SIT | Complex |  |  | Must Have
FICO | GST ASP/GSP | Interface | Go-Live | Complex |  |  | Must Have
FICO | HDFC NEFT Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | HDFC RTGS Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | ICICI NEFT Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | ICICI RTGS Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | INDUSIND RTGS Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | INDUSIND NEFT Format | Form | Go-Live | Medium |  |  | Good to Have
FICO | KOKAT Bulk NEFT Format | Report | Go-Live | Medium |  |  | Good to Have
SD | Unit Upload Program | Conversion | Go-Live | Medium | YES | M3M | Must Have
SD | Other Charges Upload Program | Conversion | Go-Live | Medium | YES | M3M
SD | Customer creation Program | Conversion | Go-Live | Simple | YES | M3M | Must Have
SD | Unit availability report | Report | SIT | Complex | YES | M3M | Must Have
SD | Unit Status (Sold /unsold/reserved) | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Sales Order creation Program | Conversion | Go-Live | Complex | YES | M3M | Must Have
SD | Mass Demand creation Program | Report | Go-Live | Medium | YES | Sunteck | Must Have
SD | Auto Debit /Credit Note Program | Enhancement | Go-Live | Complex
SD | Car Parking program | Enhancement | SIT | Complex | YES | Sunteck | Must Have
SD | Sales order mail trigger at the different approval level | Enhancement | Go-Live | Complex
SD | Additional Custom tab in SO (Additional Field) | Enhancement | SIT | Medium | YES | Sunteck
SD | Price custom routine 1(land abatment) for Unit | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Price custom routine 2(Net of land abatment) for Unit | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Price custom routine for discount calculation for Unit | Enhancement | SIT | Complex |  |  | Must Have
SD | Price custom routine for GST % After OC Receive for Unit | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Price custom routine for GST % After OC Receive for other charges | Enhancement | SIT | Complex | YES | M3M | Must Have
SD | Car Parking status report | Report | SIT | Simple | YES | M3M
SD | Milestone wise demand report(Amout vs actual receipt amount)/MIS Sales | Report | SIT | Medium | YES | M3M | Must Have
SD | Welcome letter | Form | SIT | Medium | YES | M3M | Must Have
SD | Booking Form | Form | SIT | Medium | YES | M3M | Must Have
SD | Reminder letter1 | Form | SIT | Simple | YES | M3M | Must Have
SD | Reminder letter2 | Form | SIT | Simple | YES | M3M | Must Have
SD | Termination Form | Form | SIT | Complex | YES | Sunteck | Must Have
SD | Agreement Form | Form | SIT | Complex | YES | Sunteck | Must Have
SD | Application form | Form | SIT | Complex |  |  | Must Have
SD | Demand form | Form | SIT | Complex | YES | Sunteck | Must Have
SD | Customer ledger | Form | SIT | Complex | YES | M3M
SD | Email trigger demand and 7 days of reminder1 & 7days of reminder 2 | Report | SIT | Complex | YES | Sunteck | Must Have
SD | Unit Transfer Process with Work flow(Approval process) | Report | SIT | Complex | YES | Sunteck | Must Have
SD | Unit Cancallation Process with workflow(Approval process) | Report | SIT | Complex | YES | M3M | Must Have
SD | Unit Cancallation Reports | Report | SIT | Medium | YES | Sunteck | Must Have
SD | Brokerage payout Process | Report | SIT | Complex | YES | Sunteck | Must Have
SD | Brokerage payout Report | Report | SIT | Medium | YES | Sunteck | Must Have
SD | Unit Master sync with SFDC | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Unit master Stauts(Two way) | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Customer master amendment | Interface | SIT | Complex |  |  | Must Have
SD | Broker Creation from SFDC to SAP | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Broker Invoice creation from SAP to SFDC | Interface | SIT | Complex |  |  | Must Have
SD | Broker payment SAP-SFDC | Interface | SIT | Complex |  |  | Must Have
SD | Booking creation SFDC-SAP | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Booking amendment | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Demand information sync to SFDC | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Debit note - wrt Demand no | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Credit note - wrt Demand no | Interface | SIT | Complex | YES | Sunteck | Must Have
SD | Unit Transfer | Interface | SIT | Complex |  |  | Must Have
SD | Unit Cancellation | Interface | SIT | Complex |  |  | Must Have
SD | E invoicing & E Way Bill | Interface | SIT | Complex |  |  | Must Have
SD | Post Possession clearance | Interface | SIT | Complex |  |  | Must Have
SD | Mail intimation during 10 % of agreement amount receipt | Enhancement | SIT | Medium
MM | Material Master Upload Program | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | Service Master Upload Program | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | HSN Master Upload-LSMW | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | Cutover Purchase Order Upload Program | Conversion | Go-Live | Complex | YES | RDPL | Must Have
MM | Cutover Work Order Upload Program | Conversion | Go-Live | Complex | YES | RDPL | Must Have
MM | Initial Stock Upload Program | Conversion | Go-Live | Simple | YES | RDPL | Must Have
MM | Indent Print | Form | Post Go-Live | Simple
MM | Indent Amendment | Form | Post Go-Live | Complex
MM | Store Requistion | Form | Post Go-Live | Simple
MM | Purchase Order Print | Form | SIT | Simple | YES | RDPL | Must Have
MM | Purchase Order Amendment | Form | SIT | Complex |  |  | Must Have
MM | Work Order Print | Form | SIT | Simple | YES | RDPL | Must Have
MM | Work Order Amendment | Form | SIT | Complex |  |  | Must Have
MM | GRN Print Form | Form | Post Go-Live | Simple
MM | GRN Interloc | Form | Post Go-Live | Simple
MM | Workdone Print | Form | SIT | Complex |  |  | Must Have
MM | Goods Issue Slip | Form | Post Go-Live | Simple
MM | Goods Issue Return Slip | Form | Post Go-Live | Simple
MM | Stock Adjustment | Form | Post Go-Live | Simple
MM | Stock Out Form | Form | Post Go-Live | Simple
MM | Transfer(Issue) to Contractor | Form | Post Go-Live | Simple
MM | Purchase (Material) Debit Note | Form | Post Go-Live | Simple
MM | Purchase (Service) Debit Note | Form | Post Go-Live | Simple
MM | Purchase Enquiry | Form | Post Go-Live | Simple
MM | Bill Inward Print | Form | SIT | Simple
MM | RA Bill Certificate of Payment | Form | SIT | Complex |  |  | Must Have
MM | RA Bill Item Rate | Form | SIT | Complex
MM | Purchase Bill | Form | SIT | Simple |  |  | Must Have
MM | Non-Store Puchase Bill | Form | SIT | Simple |  |  | Must Have
MM | Payment Request | Form | SIT | Simple
MM | Vendor Onboading | Form | Post Go-Live | Simple
MM | Purchase Register - Indent to Payment | Report | Post Go-Live | Complex
MM | PR Mandatory for PO | Enhancement | SIT | Simple | YES | RDPL | Must Have
MM | Work Order Amendment Enhancement | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Release Strategy mandatory for PO/WO saving | Enhancement | SIT | Simple | YES | RDPL | Must Have
MM | Release Strategy Reset with Version Management | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Good Receipt Screen Enhacement for Gate Entry | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Transfer Posting 311Q to Contractor w.r.t. WO | Enhancement | SIT | Complex |  |  | Must Have
MM | Types of WO Advance Tagging | Enhancement | SIT | Simple |  |  | Must Have
MM | WO Advance Approval Workflow | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Bill Inward with Workflow | Enhancement | SIT | Complex | YES | RDPL | Must Have
MM | Material Reconcilation | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Price Escalation | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Validation on HSN in PO while creating Docket No. in Bill Inward. | Enhancement | SIT | Simple | YES | RDPL | Must Have
MM | PO/WO Intergration with Smart App for DPR | Interface | SIT | Complex |  |  | Must Have
MM | PR Integration with Smart App | Interface | SIT | Complex |  |  | Must Have
MM | Material and Service Procurement Bidding Intergration with Smart App | Interface | SIT | Complex |  |  | Must Have
QM | ASG_QM01 - Inspection Plan Upload | Conversion | Go-Live | Medium
QM | ASG_QM02 - MIC Quantitative | Conversion | Go-Live | Medium | YES | M3M | Must Have
QM | ASG_QM03 - Sampling Procedure | Conversion | Go-Live | Medium
QM | ASG_QM04 - Catalog | Conversion | Go-Live | Medium
QM | ASG_QM04 - If the material was rejected, Mail alert should be triggered to concern person (Store person/ Construction person) | Enhancement | SIT | Complex | YES | Al - Ali | Must Have
QM | ASG_QM05 - Result Record Report - Smartform | Report | SIT | Simple | YES | M3M | Must Have
QM | ASG_QM06 - After GRN - Quality Material Mail alert should be trigger to corcern person ( 2 Mails - Third party vendor / Store peron, Contracter) | Enhancement | SIT | Complex | YES | Indinfravit | Must Have
QM | ASG_QM07 - Result Record Mail Trigger for all the Inspection Lot Number | Enhancement | SIT | Complex | YES | M3M | Must Have
MM | Cost Plan reference rate in Work Order/Purchase Order and warning message on higher rate than cost plan rate in purchasing | Enhancement | Post Go-Live | Simple | YES | RDPL
MM | Restricting Goods Receipt against Multiple Purchase order in One GRN Document | Enhancement | SIT | Simple |  |  | Must Have
MM | While Transfer Posting to Contractor Storage, debitable materials (Non-FOC) has to be captured for deductions from RA Bill | Enhancement | SIT | Complex |  |  | Must Have
MM | Quantity Validation for Project Material PR (Doc type ZPPR) | Enhancement | SIT | Simple |  |  | Must Have
MM | Restricting final RA Bill against Work order if any surplus material for the WBS is present in stock | Enhancement | Post Go-Live | Simple |  |  | Must Have
MM | Debit head of one contractor to be tagged to work order of other contractor | Enhancement | Post Go-Live | Complex |  |  | Must Have
MM | Custom Table and Validation on ITC and Non-ITC Tax Code in Purchase order. | Enhancement | SIT | Simple |  |  | Must Have

## ABAP Week Target (hidden)
| ABAP Week Target |  | 2023-09-04 | 2023-09-09
Sr No | Module | Development Description | Scope | FRICE Category | Priority | Priority | Complexity | Functional Consultant | Planned Approval | RGS Status | Planned Date | Actual Date | FS Status | Actual ABAP Consultant | Planned Start | Planned Finish | Actual Start | Actual Finish | Development Status
#VALUE!

## Detailed Summary
Project : ASHWIN SHETH GROUP Rise with SAP S/4HANA Implementation | [9 empty] | As On: | 2024-12-31
Status | All
| Module | Reusable | RGS Status | [6 empty] | FS Status | [5 empty] | Development Status | [9 empty] | HBT Testing Status | [8 empty] | CTM Testing Status | [6 empty] | PRD Status
|  | Yes | Total Object | Not Started | Approved | Submitted | WIP | NA | Hold | Completed | Not Started | Hold | WIP | NA | Total | Cancelled | Hold | In Process |  | Functional Correction | CTM Correction | Not Started | Completed |  | Total | Cancelled | Hold | Not Started | In Process | CTM Testing | CTM Correction | Functional Correction | Completed | Total | Cancelled | Hold | Not Started | In Process | In Correction | Approved | Total | Approved, Not Started | Approved, In Process | Completed | Not Started | Not Approved | Total
[18 empty] | Reusable | Fresh |  |  |  | Reusable | Fresh
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PS | 5 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 8 | 0 | 0 | 0 | 2 | 10 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 4 | 4 | 10 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0 | 5 | 0 | 1 | 4 | 10 | 0 | 0 | 0 | 10 | 0 | 10
| SD | 16 | 48 | 0 | 37 | 9 | 0 | 0 | 2 | 42 | 4 | 2 | 0 | 0 | 48 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 15 | 28 | 48 | 0 | 0 | 7 | 3 | 0 | 0 | 2 | 36 | 48 | 0 | 0 | 34 | 0 | 0 | 14 | 48 | 0 | 0 | 0 | 48 | 0 | 48
| MM | 20 | 39 | 0 | 34 | 3 | 0 | 0 | 2 | 31 | 2 | 2 | 0 | 4 | 39 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 19 | 15 | 39 | 0 | 0 | 6 | 1 | 0 | 0 | 1 | 31 | 39 | 0 | 0 | 6 | 2 | 0 | 31 | 39 | 0 | 0 | 0 | 39 | 0 | 39
| DMS | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1
| QM | 3 | 5 | 0 | 0 | 3 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 4 | 1 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 5
| FICO | 7 | 26 | 0 | 23 | 0 | 0 | 3 | 0 | 21 | 2 | 0 | 0 | 3 | 26 | 0 | 1 | 0 | 3 | 0 | 0 | 1 | 6 | 15 | 26 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 16 | 20 | 0 | 0 | 11 | 1 | 2 | 12 | 26 | 0 | 0 | 0 | 26 | 0 | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 51 | 129 | 1 | 102 | 15 | 0 | 7 | 4 | 105 | 9 | 4 | 0 | 11 | 129 | 0 | 6 | 1 | 8 | 0 | 0 | 2 | 47 | 65 | 129 | 0 | 0 | 23 | 4 | 0 | 0 | 3 | 93 | 123 | 0 | 0 | 57 | 7 | 4 | 61 | 129 | 0 | 0 | 0 | 129 | 0 | 129
[18 empty] | 9 |  |  |  |  | 112
Status | SIT
| Module | Reusable | RGS Status | [6 empty] | FS Status | [5 empty] | Development Status | [9 empty] | HBT Testing Status | [8 empty] | CTM Testing Status | [6 empty] | PRD Status
|  | Yes | Total Object | Not Started | Approved | Submitted | WIP | NA | Hold | Completed | Not Started | Hold | WIP | NA | Total | Cancelled | Hold | In Process |  | Functional Correction | CTM Correction | Not Started | Completed |  | Total | Cancelled | Hold | Not Started | In Process | CTM Testing | CTM Correction | Functional Correction | Completed | Total | Cancelled | Hold | Not Started | In Process | In Correction | Approved | Total | Approved, Not Started | Approved, In Process | Completed | Not Started | Not Approved | Total
[18 empty] | Reusable | Fresh |  |  |  | Reusable | Fresh
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PS | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 3 | 0 | 3
| SD | 13 | 39 | 0 | 31 | 8 | 0 | 0 | 0 | 36 | 3 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 13 | 25 | 39 | 0 | 0 | 4 | 3 | 0 | 0 | 1 | 31 | 39 | 0 | 0 | 26 | 0 | 0 | 13 | 39 | 0 | 0 | 0 | 39 | 0 | 39
| MM | 11 | 23 | 0 | 21 | 2 | 0 | 0 | 0 | 20 | 2 | 0 | 0 | 1 | 23 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 12 | 23 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 21 | 23 | 0 | 0 | 1 | 0 | 0 | 22 | 23 | 0 | 0 | 0 | 23 | 0 | 23
| DMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QM | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1
| FICO | 5 | 14 | 0 | 12 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 0 | 2 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 9 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 6 | 0 | 0 | 8 | 14 | 0 | 0 | 0 | 14 | 0 | 14
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 33 | 80 | 0 | 67 | 11 | 0 | 2 | 0 | 72 | 5 | 0 | 0 | 3 | 80 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 30 | 46 | 80 | 0 | 0 | 5 | 4 | 0 | 0 | 1 | 64 | 74 | 0 | 0 | 33 | 0 | 2 | 45 | 80 | 0 | 0 | 0 | 80 | 0 | 80
[18 empty] | 2 |  |  |  |  | 76
Status | Go Live
| Module | Reusable | RGS Status | [6 empty] | FS Status | [5 empty] | Development Status | [9 empty] | HBT Testing Status | [8 empty] | CTM Testing Status | [6 empty] | PRD Status
|  | Yes | Total Object | Not Started | Approved | Submitted | WIP | NA | Hold | Completed | Not Started | Hold | WIP | NA | Total | Cancelled | Hold | In Process |  | Functional Correction | CTM Correction | Not Started | Completed |  | Total | Cancelled | Hold | Not Started | In Process | CTM Testing | CTM Correction | Functional Correction | Completed | Total | Cancelled | Hold | Not Started | In Process | In Correction | Approved | Total | Approved, Not Started | Approved, In Process | Completed | Not Started | Not Approved | Total
[18 empty] | Reusable | Fresh |  |  |  | Reusable | Fresh
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PS | 2 | 7 | 0 | 5 | 0 | 0 | 2 | 0 | 5 | 0 | 0 | 0 | 2 | 7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 4 | 7 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 0 | 5 | 0 | 0 | 2 | 7 | 0 | 0 | 0 | 7 | 0 | 7
| SD | 2 | 5 | 0 | 4 | 1 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 4 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 5 | 0 | 5
| MM | 8 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 3 | 11 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 8 | 1 | 11 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 11 | 0 | 0 | 2 | 2 | 0 | 7 | 11 | 0 | 0 | 0 | 11 | 0 | 11
| DMS | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1
| QM | 2 | 4 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4
| FICO | 2 | 12 | 0 | 11 | 0 | 0 | 1 | 0 | 9 | 2 | 0 | 0 | 1 | 12 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 2 | 6 | 12 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 5 | 1 | 2 | 4 | 12 | 0 | 0 | 0 | 12 | 0 | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 16 | 40 | 1 | 31 | 3 | 0 | 5 | 0 | 28 | 4 | 0 | 0 | 8 | 40 | 0 | 1 | 0 | 6 | 0 | 0 | 0 | 16 | 17 | 40 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 28 | 40 | 0 | 0 | 17 | 7 | 2 | 14 | 40 | 0 | 0 | 0 | 40 | 0 | 40
[18 empty] | 6 |  |  |  |  | 33
Status | Post Go Live
| Module | Reusable | RGS Status | [6 empty] | FS Status | [5 empty] | Development Status | [9 empty] | HBT Testing Status | [8 empty] | CTM Testing Status | [6 empty] | PRD Status
|  | Yes | Total Object | Not Started | Approved | Submitted | WIP | NA | Hold | Completed | Not Started | Hold | WIP | NA | Total | Cancelled | Hold | In Process |  | Functional Correction | CTM Correction | Not Started | Completed |  | Total | Cancelled | Hold | Not Started | In Process | CTM Testing | CTM Correction | Functional Correction | Completed | Total | Cancelled | Hold | Not Started | In Process | In Correction | Approved | Total | Approved, Not Started | Approved, In Process | Completed | Not Started | Not Approved | Total
[18 empty] | Reusable | Fresh |  |  |  | Reusable | Fresh
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 1 | 4 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4
| MM | 1 | 5 | 0 | 2 | 1 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 0 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 5 | 0 | 0 | 3 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 5 | 0 | 5
| DMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FICO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 2 | 9 | 0 | 4 | 1 | 0 | 0 | 4 | 5 | 0 | 4 | 0 | 0 | 9 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 9 | 0 | 0 | 6 | 0 | 0 | 0 | 2 | 1 | 9 | 0 | 0 | 7 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 9 | 0 | 9
[18 empty] | 1 |  |  |  |  | 3

## Pivot
Priority2 | (All)
Planned Finish2 | (All)
Planned Finish | (All)
Planned Preparation Finish | (Multiple Items)
Count of Development Description | Column Labels
Row Labels | Approved | Hold | NA | Not Started | Submitted | Grand Total
FICO | 23 |  | 3 |  |  | 26
MM | 34 | 4 |  |  | 3 | 41
PS | 8 |  | 2 |  |  | 10
SD | 37 | 3 |  |  | 9 | 49
DMS |  |  |  | 1 |  | 1
QM |  |  | 2 |  | 3 | 5
Grand Total | 102 | 7 | 7 | 1 | 15 | 132
Priority2 | (Multiple Items)
Revised Finish | (Multiple Items)
Planned Finish2 | (All)
Planned Finish | (All)
Planned Preparation Finish | (All)
Count of Development Description | Column Labels
Row Labels | Completed | Hold | NA | Not Started | Grand Total
FICO | 21 |  | 3 | 1 | 25
MM | 31 | 4 | 4 | 2 | 41
PS | 8 |  | 2 |  | 10
SD | 42 | 3 |  | 4 | 49
DMS |  |  |  | 1 | 1
QM | 3 |  | 2 |  | 5
Grand Total | 105 | 7 | 11 | 8 | 131
Priority2 | (All)
Revised Finish2 | (All)
FRICE Category | (All)
Planned Finish2 | (All)
Planned Finish | (All)
Planned Preparation Finish | (All)
Count of Development Description | Column Labels
Row Labels | Completed | Hold | In Process | Not Started | Grand Total
FICO | 22 | 1 | 3 |  | 26
MM | 34 | 3 | 3 | 1 | 41
PS | 9 |  | 1 |  | 10
SD | 43 | 4 | 2 |  | 49
DMS | 1 |  |  |  | 1
QM | 5 |  |  |  | 5
Grand Total | 114 | 8 | 9 | 1 | 132
Priority2 | (All)
FS Status | (All)
Development Status | (All)
Revised / Actual Preparation Finish | (All)
Actual Finish | (All)
Count of Development Description | Column Labels
Row Labels | Approved | Hold | NA | Not Started | Submitted | (blank) | Grand Total
FICO | 23 |  | 3 |  |  |  | 26
MM | 34 | 4 |  |  | 3 |  | 41
PS | 8 |  | 2 |  |  |  | 10
SD | 37 | 3 |  |  | 9 |  | 49
DMS |  |  |  | 1 |  |  | 1
QM |  |  | 2 |  | 3 |  | 5
(blank)
Grand Total | 102 | 7 | 7 | 1 | 15 |  | 132
Complexity | (All)
HBT Testing Status | (All)
Priority2 | (All)
Planned Finish | (All)
Actual ABAP Consultant | (All)
FRICE Category | (All)
Reusable Object | (All)
Count of Development Description | Column Labels
Row Labels | (blank) | Approved | Not Started | In Correction | In Process | Hold | Grand Total
FICO |  | 12 | 11 | 2 | 1 |  | 26
MM |  | 31 | 7 |  | 2 | 1 | 41
PS |  | 4 | 5 | 1 |  |  | 10
SD |  | 14 | 34 |  |  | 1 | 49
DMS |  |  | 1 |  |  |  | 1
QM |  |  |  | 1 | 4 |  | 5
(blank)
Grand Total |  | 61 | 58 | 4 | 7 | 2 | 132

## ABAP Target (hidden)
[8 empty] | AS On: | 2024-12-31
This Week Plan
Sr. No. | ABAP Resource | User ID | Module | Object No | Development Description | FRICE-W | Functional | Planned |  | Actual |  |  | Status | Remarks
[8 empty] | Start Date | Finish Date | Start Date | Finish Date | Delay
1 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[16 empty] | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
#NAME?
2 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
3 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
#NAME?
4 | [13 empty] | FIORI issues rasied with BASIS & FIORI Consultant. | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
5 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
#NAME?
6 | [14 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?
[15 empty] | BLANK | #NAME? | #NAME? | #NAME?

## Consultant
Module | Functional Consultant
SD | Karanpal Chouhan
SD | Rao Tella
MM | Izharuddin Quazi
MM | Shantanu Ghodke
PS | Nilesh Patil
FI | Hearshad Mhatre
QM | Parvathineni Srinivasulu
DMS | Nilesh Patil

## Status Value
|  |  | Scope |  |  |  | RGS Status | FS Status | Functional Testing Status | Development Status | CTM Testing Status | UAT Status | PRD Status
| Form | SIT | SOW | Santosh Choudhary | Simple | 0-3 Man Days | Submitted | Not Started | Not Started | Not Started | Not Started | Submitted | Approved, Not Started
Yes | Report | Go Live | System Requirement | ABAP2 | Medium | 3-6 Man Days | Approved | Completed | In Process | In Process | Hold | Approved | Approved, In Process
No | Interface | Post Go Live | Additional | ABAP3 | Complex | 6-8 Man Days | Not Started | Hold | CTM Testing | Hold | Cancelled | Not Approved | Not Started
| Conversion | All | Hold | ABAP4 |  |  | WIP | WIP | CTM Correction | Cancelled | In Process | Not Started | Completed
| Enhancement | Hold | Cancelled |  |  |  | NA | NA | Functional Correction | Functional Testing | In Correction | WIP | Not Approved
| Workflow | [5 empty] | Hold |  | Completed | Functional Correction | Approved | Hold
[9 empty] | Hold | CTM Testing
[9 empty] | Enhancement | CTM Correction
[9 empty] | Cancelled | Enhancement
Completed

## ASG Consolidate Gap List
| Project : ASHWIN SHETH GROUP SAP S-4HANA Implementation | [5 empty] | As On: | 2024-12-31
Complexity |  |  |  | MM | SD | PS | QM | DMS | FICO | [6 empty] | Hold | Grand Total
Complex |  |  |  | 24 | 33 | 7 | 0 | 1 | 14 | [6 empty] | -2 | 77 | 0
Medium |  |  |  | 0 | 13 | 0 | 5 | 0 | 3 | [6 empty] | 0 | 21 | 0
Simple |  |  |  | 17 | 3 | 3 | 0 | 0 | 9 | [6 empty] | 0 | 32 | 0
Grand Total |  |  |  | 41 | 49 | 10 | 5 | 1 | 26 | [6 empty] | -2 | 130 | 0
[10 empty] | RGS | [8 empty] | FS | [6 empty] | Configuration |  |  | ABAP Development | [9 empty] | HBT Testing | [9 empty] | CTM Testing | [10 empty] | UAT Sign Off |  |  |  |  | Go-Live |  |  |  | Reusability
Srno. | Module | Interface | Development Description | Scope | FRICE Category | Priority | Priority | Complexity | Functional Consultant | Planned Preparation Start | Planned Preparation Finish | Planned Submission | Planned Approval | Revised / Actual Preparation Start | Revised / Actual Preparation Finish | Revised / Actual Submission | Revised / Actual Approval | RGS Status | Planned Start | Planned Finish | Revised Start | Revised Finish | Actual Start | Actual Finish | FS Status | Planned Date | Actual Date | Status | Plan ABAP Consultant | Actual ABAP Consultant | Duration | Planned Start | Planned Finish | Revised Start | Revised Finish | Actual Start | Actual Finish | Development Status | UT-SIT Test Scripts Planned Finish | UT-SIT Test Scripts Actual Finish | Planned Start | Planned Finish | Testing Planned Duration | Revised Start | Revised Finish | Actual Start | Actual Finish | HBT Testing Status | CTM Name | Training Start | Training Finish | Duration | Planned Start | Planned Finish | Revised Start | Revised Finish | Actual Start | Actual Finish | CTM Testing Status | Final Test Script Submission Date | Planned Date | Revised Date | Actual Date | UAT Status | PRD Status | Go-Live Planned Date | Go-Live Revised Date | Go-Live Actual Date | Reusable Object | Reusable Client Name | Remarks | Additional Efforts | % | Remarks / Details | Custom Tcode
1 | PS |  | WBS, Network, Activity, Mileston Upload Program | SOW | Conversion | 1 | SIT | Simple | Nilesh | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | Approved | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | Completed |  |  |  | Mayur Joshi | Mohanreddy | 2 | 2024-03-14 | 2024-03-15 | 2024-03-22 | 2024-03-22 | 2024-03-13 | 2024-03-26 | Completed | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-14 |  | 2024-03-22 | 2024-03-22 | 2024-03-13 | 2024-03-26 | Completed | Ketan | [8 empty] | 2024-05-13 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Mecon, Sunteck | Copied | 1 | 33.33% | Muliple Plant & Profit center in Project, User fields | ZPS_CJ20n, ZPS_Activity, ZPS_MLST
2 | PS |  | BPO Upload Program | SOW | Conversion | 1 | Go Live | Simple | Nilesh | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | Completed | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 | 2024-03-14 | Completed | Aanas | [8 empty] | 2024-05-17 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Mecon | Copied | 0.5 | 16.67% | Material, Service price not mandatory | ZPS_BPO
3 | PS |  | Unit Cost Plan Upload Program | SOW | Conversion | 2 | Go Live | Simple | Nilesh | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | Completed | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 | 2024-03-14 | Completed | Aanas | [8 empty] | 2024-05-17 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Mecon | Copied |  | 16.67% |  | ZPS_CJ40
4 | PS |  | Budget Approval Procedure & document attachment compulsary | SOW | Enhancement | 2 | SIT | Complex | Nilesh | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | Approved | 2024-03-16 | 2024-03-16 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-20 | Completed |  |  |  | Mayur Joshi | Sumant Bharti | 5 | 2024-03-26 | 2024-03-30 | 2024-03-22 | 2024-04-01 | 2024-03-22 | 2024-04-01 | Completed |  |  | 2024-03-30 | 2024-03-31 |  | 2024-04-01 | 2024-04-02 | 2024-04-01 | 2024-04-03 | Completed | Aanas | [8 empty] | 2024-05-03 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | INDINFRAVIT | Copied | 4 | 57.14% | Approval levels, Approvers project as well as depart. wise, Budgeting overall as well as annual basis. | ZPS_BUDG_AMEND, ZPS_BUDG_APPROVAL, ZPS_CMD_APPROV
5 | PS |  | Milestone Confimation Mail Notification with completion Image & architect certificate attachement | SOW | Enhancement | 1 | SIT | Complex | Nilesh | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | Approved | 2024-03-15 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-15 | 2024-03-16 | Completed |  |  |  | Mayur Joshi | Mohanreddy | 3 | 2024-03-19 | 2024-03-21 | 2024-04-04 | 2024-04-06 | 2024-03-14 | 2024-03-15 | Not Started |  |  | 2024-03-21 | 2024-03-22 |  |  |  | 2024-03-22 | 2024-03-23 | Completed | Ketan | [8 empty] | 2024-05-02 | In Correction |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 1 | 14.29% | Certificate attachment in DMS, Mail trigger with attachment | ZPS_CONFIRM
6 | PS | Smart app | Project & Work Breakdown Structure sync to smartapp | SOW | Integration | 1 | Go Live | Complex | Nilesh | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-22 |  | Approved | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | 2024-03-16 | 2024-03-22 | Completed |  |  |  |  | Mayur Joshi | 16 | 2024-04-08 | 2024-04-23 | 2024-04-12 | 2024-05-10 | 2024-04-15 |  | Completed |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
7 | PS | Smart app | WBS & Milestones (Payment milestones plans) sync to smartapp | SOW | Integration | 2 | Go Live | Complex | Nilesh | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-22 |  | Approved | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | 2024-03-16 | 2024-03-22 | Completed |  |  |  |  | Mayur Joshi | 16 | 2024-04-08 | 2024-04-23 | 2024-04-12 | 2024-05-10 | 2024-04-15 |  | Completed |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
8 | PS | Smart app | Network Sync to Smartapp | SOW | Integration | 4 | Go Live | Complex | Nilesh | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-22 |  | Approved | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-05 | 2024-03-16 | 2024-03-22 | Completed |  |  |  |  | Mayur Joshi | 16 | 2024-04-08 | 2024-04-23 | 2024-04-12 | 2024-05-10 |  |  | Completed |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
9 | PS | Smart app | Activities Sync from Smartapp to SAP | SOW | Integration | 5 | Go Live | Complex | Nilesh | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-22 |  | Approved | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-05 | 2024-03-16 | 2024-03-22 | Completed |  |  |  |  | Mayur Joshi | 16 | 2024-04-08 | 2024-04-23 | 2024-04-12 | 2024-05-10 |  |  | Completed |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
10 | PS | Smart app | Link BOQ to WBS in SAP then sync to smartapp | SOW | Integration | 3 | Go Live | Complex | Nilesh | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-22 |  | Approved | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-04-05 | 2024-03-16 | 2024-03-22 | Completed |  |  |  |  | Mayur Joshi | 16 | 2024-04-08 | 2024-04-23 | 2024-04-12 | 2024-05-10 | 2024-04-17 |  | In Process |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
11 | DMS |  | All attached documents in SAP to view in Contentverse DMS | SOW | Integration | 1 | Go Live | Complex | Nilesh | 2024-03-26 | 2024-03-28 | 2024-03-28 | 2024-03-30 |  |  |  |  | Not Started | 2024-04-06 | 2024-04-08 | 2024-04-06 | 2024-04-08 |  |  | Not Started |  |  |  |  | Mayur Joshi | 16 | 2024-04-08 | 2024-04-23 | 2024-05-15 | 2024-05-30 | 2024-05-15 | 2024-06-30 | Completed |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
12 | FICO |  | Vendor master upload | SOW | Conversion | 1 | SIT | Simple | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Not Started | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-04-03 | 2024-04-04 | 2024-04-22 | 2024-04-23 | Completed |  | 2024-04-15 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 16.67% | Column to be add - ESIC No/PF No./ GSTN Effective Date /PAN Operative / Inoperative/Vendor Turn Over /MSME NUMBER/MSME Category type/RERA NUMBER/RERA VALID FROM/RERA NUMBER TO/Contact Person/Favouring Name /Website | ZFI_VENDOR_UP
13 | FICO |  | Asset Cutover upload Program | SOW | Conversion | 1 | SIT | Simple | Harshad | NA | NA | NA | NA | NA | NA | NA |  | NA |  | NA |  | NA |  |  | NA |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Completed | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Completed |  | 2024-04-15 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 16.67% | NA | ZFI_ASSET_UPD
14 | FICO |  | Cutover Template | SOW | Conversion | 1 | SIT | Simple | Harshad | NA | NA | NA | NA | NA | NA | NA |  | NA |  | NA |  | NA |  |  | NA |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-04-16 | 2024-04-19 | Completed | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Completed |  | 2024-04-15 | 2024-04-15 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 16.67% | NA | ZFI_GLBAL_UPD
15 | FICO |  | GSTR1 | SOW | Report | 1 | Go Live | Simple | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | Completed |  |  |  | Sumant | Sumant | 2 | 2024-03-13 | 2024-03-14 | 2024-04-05 | 2024-04-06 | 2024-04-12 | 2024-04-16 | Completed | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-04-05 | 2024-04-06 | 2024-04-16 | 2024-04-19 | Completed |  | 2024-04-19 | 2024-04-19 |  | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | In Correction |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 16.67% | Column to be add- Period/GSTIN Status/Eligibility/HSN Nature/Adj DocumentNo/Adj TransactionTypeId/Adj Document Date | ZGSTN1
16 | FICO |  | GSTR2 | SOW | Report | 1 | Go Live | Simple | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | Completed |  |  |  | Sumant | Sumant | 2 | 2024-03-13 | 2024-03-14 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-16 | Completed | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-04-08 | 2024-04-10 | 2024-04-16 | 2024-04-19 | Completed |  | 2024-04-19 | 2024-04-19 |  | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | In Correction |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 16.67% | Column to be add- Period/GSTIN Status/Eligibility/HSN Nature/Adj DocumentNo/Adj TransactionTypeId/Adj Document Date | ZGSTR2
17 | FICO |  | Bank Reco Upload Program | SOW | Conversion | 2 | SIT | Simple | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | 2024-03-14 | 2024-03-15 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-14 | 2024-03-14 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | Completed | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | Completed |  | 2024-04-20 | 2024-04-20 |  | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 1 | 33.33% | Excel upload template as per bank | ZFI_BRS
18 | FICO |  | Customer Tax Invoice (Interest) | SOW | Form | 2 | Go Live | Simple | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 3 | 2024-03-20 | 2024-03-22 | 2024-03-29 | 2024-03-27 | 2024-03-30 | 2024-03-30 | Completed |  |  | 2024-03-22 | 2024-03-23 |  | 2024-03-29 | 2024-03-27 | 2024-03-30 | 2024-03-30 | Completed |  | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_RECEIPT_POST
19 | FICO |  | Customer Receipt Screen | SOW | Enhancement | 2 | SIT | Complex | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 3 | 2024-03-18 | 2024-03-20 | 2024-03-21 | 2024-03-30 | 2024-03-21 | 2024-03-30 | Completed | 2024-03-19 | 2024-03-20 | 2024-03-13 | 2024-03-13 |  | 2024-03-21 | 2024-03-30 | 2024-03-30 | 2024-03-30 | Completed |  | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_RECEIPT_PARK
20 | FICO |  | Customer Receipt List | SOW | Enhancement | 1 | SIT | Complex | Harshad | 2024-03-08 | 2024-03-10 | 2024-03-10 | 2024-03-11 | 2024-03-08 | 2024-03-10 | 2024-03-11 |  | Approved | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-03-23 | Completed | 2024-03-23 | 2024-03-23 | 2024-03-23 | 2024-03-23 |  | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Completed |  | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 4 | 28.57% | 1. On account entry adjustment & GST Calculation 2. 1% TDS line item to be add as per demand basic closed 3. Simple Interest calulation | ZFI_RECEIPT_POST
21 | FICO |  | Project & Plants Mapping table | SOW | Enhancement | 1 | SIT | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 1 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-17 | Completed | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 |  | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-17 | Completed |  | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_PROJ_MAP
22 | FICO | SFDC | Token Amount SFDC-SAP | SOW | Integration | 2 | SIT | Complex | Harshad | NA | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 |  | Approved | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 18 | 2024-04-10 | 2024-04-27 | 2024-04-16 | 2024-04-16 | 2024-04-16 |  | Completed |  |  | 2024-04-27 | 2024-04-28 | [5 empty] | Functional Testing | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_CUST_ADV
23 | FICO | SFDC | Customer Receipts (SFDC) | SOW | Integration | 1 | SIT | Complex | Harshad | NA | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 18 | 2024-04-10 | 2024-04-27 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 25-04-2024 | Completed |  |  | 2024-04-27 | 2024-04-28 |  | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | Functional Testing | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
24 | FICO | SFDC | Interest Waiver | SOW | Integration | 3 | SIT | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 18 | 2024-04-10 | 2024-04-27 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 25-04-2024 | Completed |  |  | 2024-04-27 | 2024-04-28 |  | 2024-04-20 | 2024-04-20 |  |  | Functional Testing | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_RECEIPT_PARK
25 | FICO | Clear tax | Invoice wise Match & Mismatch Report showing Revenue as per in P&L & as per GST Outward Register | SOW | Integration | 3 | SIT | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 18 | 2024-04-10 | 2024-04-27 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 25-04-2024 | Completed |  |  | 2024-04-27 | 2024-04-28 |  | 2024-04-20 | 2024-04-20 |  |  | Functional Testing | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_RECEIPT_PARK
26 | FICO | Clear tax | GSTR 1 | SOW | Integration | 3 | SIT | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 18 | 2024-04-10 | 2024-04-27 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 25-04-2024 | Completed |  |  | 2024-04-27 | 2024-04-28 |  | 2024-04-20 | 2024-04-20 |  |  | Functional Testing | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_RECEIPT_PARK
27 | FICO | Clear tax | GSTR 2 | SOW | Integration | 3 | SIT | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 18 | 2024-04-10 | 2024-04-27 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 25-04-2024 | Completed |  |  | 2024-04-27 | 2024-04-28 |  | 2024-04-20 | 2024-04-20 |  |  | Functional Testing | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_RECEIPT_PARK
28 | FICO | Clear tax | GSTN , Address & Pan Validation | SOW | Integration | 2 | Go Live | Complex | Harshad | 2024-03-14 | 2024-03-14 |  |  | 2024-03-14 | 2024-03-14 | 2024-03-14 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 18 | 2024-04-10 | 2024-04-27 | 2024-05-21 | 2024-05-31 |  |  | In Process |  |  | 2024-04-27 | 2024-04-28 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFIT_INT_WAVIER
29 | FICO |  | GSTN , Address & Pan Validation | SOW | Report | 1 | Go Live | Medium | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-18 | 2024-03-19 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Completed |  |  |  | Sriniwas Moturi | Sriniwas Moturi | 3 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-04-02 | 2024-03-30 | 2024-04-08 | Completed |  |  | 2024-03-28 | 2024-03-29 |  | 2024-04-08 | 2024-04-10 | 2024-03-30 | 2024-04-08 | Completed |  | 2024-04-19 | 2024-04-19 |  | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_TDS_RECON
30 | FICO |  | Expense Head wise TDS deduction required | SOW | Report | 2 | Go Live | Medium | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Completed |  |  |  | Mohanreddy Mogili | Mohanreddy Mogili | 3 | 2024-03-28 | 2024-03-30 | 2024-03-29 | 2024-04-02 | 2024-03-30 | 2024-04-03 | Completed |  |  | 2024-03-30 | 2024-03-31 |  | 2024-03-29 | 2024-04-02 | 2024-03-30 | 2024-04-03 | Completed |  | 2024-04-19 | 2024-04-19 |  | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_EXP_TDS
31 | FICO |  | ITC utilization project wise | SOW | Report | 2 | Go Live | Medium | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Completed |  |  |  | Mayur Joshi | Mayur Joshi | 3 | 2024-04-08 | 2024-04-10 | 2024-05-25 | 2024-06-01 |  |  | Hold |  |  | 2024-04-10 | 2024-04-11 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [7 empty] | Logic Pending from Client
32 | FICO |  | Cash Flow Report | Additional | Report | 2 | Go Live | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-21 | 2024-03-21 | 2024-03-21 | Completed |  |  |  | Veeru | Veeru | 5 | 2024-03-31 | 2024-04-04 | 2024-04-11 | 2024-04-13 | 2024-04-16 | 2024-04-24 | Completed |  |  | 2024-04-04 | 2024-04-05 |  | 2024-04-11 | 2024-04-13 | 2024-04-24 | 2024-04-24 | Completed | [10 empty] | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_CASHFLOW
33 | FICO |  | Invoice wise Match & Mismatch Report showing Revenue as per in P&L & as per GST Outward Register | Additional | Report | 2 | Go Live | Complex | Harshad | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-10 | 2024-03-11 | 2024-03-11 |  | Approved | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-26 |  |  | NA |  |  |  | Mayur Joshi | Mayur Joshi | 3 | 2024-04-05 | 2024-04-07 | 2024-04-05 | 2024-06-27 |  |  | In Process |  |  | 2024-04-07 | 2024-04-08 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [7 empty] | It will get from Clear Tax /API Logic given
34 | SD |  | Unit Upload Program | SOW | Conversion | 2 | SIT | Medium | Bhaskar | 2024-03-10 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-13 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-18 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 2 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-08 | 2024-04-10 | Completed |  |  | 2024-04-04 | 2024-04-05 |  | 2024-04-07 | 2024-04-08 | 2024-04-10 | 12.04.2024 | Completed | Avinash/Bhavesh | 2024-04-29 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | Approved |  | 2024-04-30 | 2024-04-29 | 2024-04-29 | WIP | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 20% | Additional custom field & Material characteristic need to map | ZMM_MAT_UPD
35 | SD |  | Other Charges Upload Program | SOW | Conversion | 2 | SIT | Medium | Bhaskar | 2024-03-10 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-13 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-18 | Completed |  |  |  | Srinivas | Srinivas | 2 | 2024-04-05 | 2024-04-06 | 2024-04-08 | 2024-04-10 | 2024-04-08 | 2024-04-10 | Completed |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-07 | 2024-04-08 | 2024-04-10 | 12.04.2024 | Completed | Avinash/Bhavesh | 2024-04-29 | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | Approved |  | 2024-04-30 | 2024-04-29 | 2024-04-29 | WIP | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 10% | Additional custom field & Material characteristic need to map | ZSD_SO_UPLOAD
36 | SD |  | Customer creation Program | SOW | Conversion | 2 | SIT | Simple | Bhaskar | 2024-03-10 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-13 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-18 | Completed |  |  |  | Mohan Reddy | Mohan Reddy | 1 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-04-06 | 2024-04-10 | Completed |  |  | 2024-03-18 | 2024-03-19 |  | 2024-04-07 | 2024-04-08 | 2024-04-10 | 2024-04-14 | Completed | Avinash/Bhavesh | 2024-04-29 | [8 empty] | Approved |  | 2024-04-30 | 2024-04-29 | 2024-04-29 | WIP | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 1 | 33.33% | Customer Parmanent add also need to upload with correspondence add | ZSD_CUST_UPD
37 | SD |  | Unit Status Auto Update | SOW | Enhancement | 1 | SIT | Medium | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-15 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-18 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 1 | 2024-03-19 | 2024-03-19 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-19 | Completed | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 | Completed | Avinash/Bhavesh |  | 2024-04-18 |  | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | Approved |  | 2024-04-30 | 2024-04-29 | 2024-04-29 | WIP | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 10%
38 | SD |  | Sales Order creation Program | SOW | Conversion | 2 | Go Live | Complex | Bharat Nagda | 2024-03-10 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | 2024-04-01 | 2024-04-02 | Completed |  |  |  | Srinivas | Srinivas | 3 | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-06 | 2024-05-01 | 2024-05-03 | Completed |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-07 | 2024-04-08 | 2024-04-30 |  | Completed | Avinash/Bhavesh | [7 empty] | 2024-06-04 | 2024-06-05 | Approved |  | 2024-04-30 | 2024-04-29 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 2 | 28.57% | Dring upload we need to update complete billing for those milestone which demand already generated in lagecy system,but its pending from ABAP Side Need to check with @Ravi.M (Runwal) | ZSD_SO_UPLOAD
39 | SD |  | Mass Demand creation Program | SOW | Enhancement | 1 | SIT | Medium | Karanpal | 2024-03-11 | 2024-03-12 | 2024-03-12 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-13 | 2024-03-13 | 2024-03-18 | 2024-03-18 | 2024-03-19 | 2024-03-20 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 1 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-25 | Completed |  |  | 2024-03-21 | 2024-03-22 |  | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-04-03 | Completed | Avinash/Bhavesh | 2024-04-29 | 2024-04-30 | [5 empty] | 2024-05-07 | 2024-05-08 | Approved |  | 2024-04-30 | 2024-04-29 | 2024-05-07 | WIP | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 20% | Additional Check & control required | ZSD_MASSDEMAND
40 | SD |  | Auto Debit /Credit Note Program | Hold | Enhancement | 1 | Hold | Complex | Karanpal |  | NA |  |  |  |  | Hold |  | Hold |  | NA |  | NA |  |  | Hold | [12 empty] | Hold | [9 empty] | Hold | [10 empty] | Hold |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07
41 | SD |  | Additional Custom tab in SO (Additional Field) | SOW | Enhancement | 2 | SIT | Medium | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-15 | 2024-03-19 | 2024-03-19 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 2 | 2024-04-03 | 2024-04-04 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-26 | Completed |  |  | 2024-04-04 | 2024-04-05 |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Completed | Avinash/Bhavesh | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-08 | Approved |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck |  | 1 | 20% | Custom field required to capture additional information
42 | SD |  | Price custom routine 1(land abatment) for Unit | SOW | Enhancement | 2 | SIT | Complex | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-05-10 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 2 | 2024-03-22 | 2024-03-23 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Completed |  |  | 2024-03-23 | 2024-03-24 |  | 2024-03-22 | 2024-03-22 | 2024-03-23 | 2024-03-23 | Completed | Avinash/Bhavesh | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-17 | Approved |  | 2024-04-30 | 2024-05-16 |  | Submitted | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 7.143% | Need to Check with all type of scnaerios(SO/Invoice/debit/credit process)
43 | SD |  | Price custom routine 2(Net of land abatment) for Unit | SOW | Enhancement | 2 | SIT | Complex | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-05-10 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 4 | 2024-03-23 | 2024-03-26 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | Completed |  |  | 2024-03-26 | 2024-03-27 |  | 2024-03-22 | 2024-03-22 | 2024-03-23 | 2024-03-23 | Completed | Avinash/Bhavesh | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-17 | Approved |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 7.143% | Need to Check with all type of scnaerios(SO/Invoice/debit/credit process)
44 | SD |  | Price custom routine for discount calculation for Unit | SOW | Enhancement | 2 | SIT | Complex | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-05-10 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-19 | 2024-03-19 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 2 | 2024-03-27 | 2024-03-28 | 2024-03-18 | 2024-03-18 | 2024-03-19 | 2024-03-20 | Completed | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  | 2024-03-20 | 2024-03-20 | 2024-03-21 | 2024-03-28 | Completed | Avinash/Bhavesh/Harendra/Devenra | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-17 | Approved |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07
45 | SD |  | Price custom routine for GST % After OC Receive for Unit | SOW | Enhancement | 1 | SIT | Complex | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-05-10 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-16 | 2024-03-17 | 2024-03-20 | 2024-03-20 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 4 | 2024-03-29 | 2024-04-01 | 2024-03-18 | 2024-03-18 | 2024-03-20 | 2024-03-21 | Completed |  |  | 2024-04-01 | 2024-04-02 |  | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-22 | Completed | Avinash/Bhavesh/Harendra/Devenra | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-17 | Approved |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 14.29% | Extra Enhancement required to get GST % record for affordable housing scheme
46 | SD |  | Price custom routine for GST % After OC Receive for other charges | SOW | Enhancement | 1 | SIT | Complex | Karanpal | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-05-10 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-23 | 2024-03-23 | 2024-03-20 | 2024-03-20 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 3 | 2024-04-01 | 2024-04-03 | 2024-03-17 | 2024-03-19 | 2024-03-20 | 2024-03-22 | Completed |  |  | 2024-04-03 | 2024-04-04 |  | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-26 | Completed | Avinash/Bhavesh/Harendra/Devenra | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-17 | Approved |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 14.29% | Extra Enhancement required to get GST % record for composite charge
47 | SD |  | Milestone wise demand report(Amout vs actual receipt amount)/MIS Sales | SOW | Report | 1 | SIT | Medium | Karanpal | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-29 | Approved | 2024-03-14 | 2024-03-14 | 2024-04-02 | 2024-03-03 | 2024-04-02 | 2024-04-03 | Completed |  |  |  | Mohan Reddy | Mohan Reddy | 4 | 2024-04-05 | 2024-04-08 | 2024-04-05 | 2024-04-08 | 2024-04-08 | 2024-04-16 | Completed |  |  | 2024-04-08 | 2024-04-09 |  | 2024-04-09 | 2024-04-10 | 2024-04-17 | 2024-05-02 | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-16 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_MIS
48 | SD |  | Booking Form | SOW | Form | 2 | SIT | Medium | Bhaskar | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-15 | 2024-03-15 | 2024-03-26 | 2024-03-26 | 2024-03-27 | 2024-03-27 | Completed |  |  |  | Sridhar | Satish Bhakth | 3 | 2024-04-09 | 2024-04-11 | 2024-04-01 | 2024-04-05 | 2024-04-04 | 2024-04-09 | Completed |  |  | 2024-04-11 | 2024-04-12 |  | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-15 | Completed | Avinash/Bhavesh | 2024-05-07 | 2024-05-08 | [5 empty] | 2024-05-07 | 2024-05-08 | Approved |  | 2024-04-30 | 2024-05-17 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_BOOKING / ZSD_PRINT
49 | SD |  | Reminder letter1 | SOW | Form | 2 | SIT | Simple | Karanpal | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | Completed |  |  |  | Viru | Viru | 4 | 2024-04-12 | 2024-04-15 | 2024-03-31 | 2024-04-04 | 2024-04-07 | 2024-04-15 | Completed |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-09 | 2024-04-10 | 2024-04-11 |  | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-17 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 3 | 66.67% | Form structure changed,additional field also need to add Changes from ABAP side Pedning, Printout not showing, Final correction Sent to abaper. | ZSD01
50 | SD |  | Reminder letter2 | SOW | Form | 2 | SIT | Simple | Bhaskar | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | Completed |  |  |  | Viru | Viru | 4 | 2024-04-12 | 2024-04-15 | 2024-04-02 | 2024-04-04 | 2024-04-07 | 2024-04-15 | Completed |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-13 | 2024-04-14 | 2024-04-11 |  | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-17 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 66.67% | Invoice type & condition type replaced with newly created Changes from ABAP side Pedning, Printout not showing, Final correction Sent to abaper. | ZSD02
51 | SD |  | Termination Form | SOW | Form | 1 | Post Go Live | Complex | Bhaskar | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | Completed |  |  |  | Sridhar | Veeru | 4 | 2024-04-12 | 2024-04-15 | 2024-04-02 | 2024-04-04 | 2024-04-05 | 2024-04-16 | Hold |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-13 | 2024-04-14 | 2024-04-11 |  | Functional Correction | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-17 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 0.5 | 14.29% | Invoice type & condition type need to replaced with newly created
52 | SD |  | Demand form | SOW | Form | 1 | SIT | Complex | Karanpal | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-28 | 2024-03-28 | 2024-03-25 | 2024-03-27 | Completed |  |  |  | Sridhar | Sridhar | 3 | 2024-04-16 | 2024-04-18 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-04-04 | Completed |  |  | 2024-04-18 | 2024-04-19 |  | 2024-04-04 | 2024-04-05 | 2024-04-05 |  | Functional Correction | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-17 |  | Not Started | Not Started | 2024-06-07 | [6 empty] | 57.14% | FS Shared with Abaper and Checking with Multiple test case scenario to make sure the final changes. | ZSD_DEMAND / ZSD_PRINT
53 | SD |  | Unit Cancellation Process with workflow(Approval process) | SOW | Enhancement | 1 | SIT | Complex | Karanpal | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-04-29 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-04 | 2024-03-06 | 2024-04-05 | 2024-04-14 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 3 | 2024-04-19 | 2024-04-21 | 2024-04-14 | 2024-04-24 | 2024-04-14 | 2024-04-28 | Completed |  |  | 2024-04-21 | 2024-04-22 |  | 2024-04-28 | 2024-05-02 | 2024-04-28 | 2024-05-01 | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-17 |  | Not Started | Not Started | 2024-06-07 |  |  |  |  | Copied |  |  |  | ZSD_GST_REV
54 | SD |  | Brokerage payout Process | SOW | Enhancement | 1 | SIT | Complex | Yousuf | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-14 | 2024-03-19 | 2024-03-20 | 2024-03-20 | 2024-04-29 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-06 | 2024-03-07 | 2024-04-29 | 2024-04-30 | Completed |  |  |  | Mohan Reddy | Mohan Reddy | 4 | 2024-04-13 | 2024-04-16 | 2024-04-14 | 2024-04-24 | 2024-04-30 |  | Completed |  |  | 2024-04-16 | 2024-04-17 | [5 empty] | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 4 | 57.14% | Check & control ,increase level of approval | ZSD_BROK
55 | SD |  | Brokerage payout Report | SOW | Report | 1 | Go Live | Medium | Bhaskar | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-19 | 2024-03-20 | 2024-03-20 | 2024-04-29 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-06 | 2024-03-07 |  |  | Not Started |  |  |  | Satish Bhakth | ABAP5 | 2 | 2024-04-17 | 2024-04-18 | 2024-04-14 | 2024-04-24 | 2024-04-30 |  | Completed |  |  | 2024-04-18 | 2024-04-19 | [5 empty] | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | Sunteck | Copied | 2 | 40% | Additional information required
56 | SD | SFDC | Unit Master sync with SFDC | SOW | Integration | 1 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-04-25 | Approved | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 2024-04-17 | 2024-04-18 | Completed |  |  |  | Sridhar | Sridhar | 4 | 2024-04-09 | 2024-04-12 | 2024-05-19 | 2024-04-22 | 2024-05-01 | 2024-05-15 | Completed |  |  | 2024-04-12 | 2024-04-13 |  | 2024-05-08 | 2024-05-09 | 2024-05-09 | 2024-05-20 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-17 | 2024-05-18 |  |  | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
57 | SD | SFDC | Unit master Stauts (SAP-SFDC) | SOW | Integration | 2 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-04-25 | Approved | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-05-01 | 2024-05-02 | Completed |  |  |  | Satish | Satish | 3 | 2024-04-13 | 2024-04-15 | 2024-04-23 | 2024-04-25 | 2024-05-02 | 2024-05-15 | Completed |  |  | 2024-04-15 | 2024-04-16 |  | 2024-05-08 | 2024-05-09 | 2024-05-15 | 2024-05-15 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-17 | 2024-05-18 |  |  | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
58 | SD | SFDC | Unit master Stauts (SFDC-SAP) | SOW | Integration | 2 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-04-25 | Approved | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-05-01 | 2024-05-02 | Completed |  |  |  | Satish | Satish | 3 | 2024-04-13 | 2024-04-15 | 2024-04-23 | 2024-04-25 | 2024-05-02 | 2024-05-15 | Completed |  |  | 2024-04-15 | 2024-04-16 |  | 2024-05-08 | 2024-05-09 | 2024-05-15 | 2024-05-15 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-17 | 2024-05-18 |  |  | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
59 | SD | SFDC | Customer master Creation | SOW | Integration | 3 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-04-25 | Approved | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-04-21 | 2024-04-22 | Completed |  |  |  | Satish | Satish | 3 | 2024-04-12 | 2024-04-14 | 2024-04-26 | 2024-04-30 | 2024-04-29 | 2024-05-17 | Completed |  |  | 2024-04-14 | 2024-04-15 |  | 2024-04-14 | 2024-04-26 | 2024-04-30 | 2024-05-17 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-17 | 2024-05-18 |  |  | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
60 | SD | SFDC | Broker Creation from SFDC to SAP | SOW | Integration | 4 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-05-08 | Approved | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-04-23 | 2024-04-24 | Completed |  |  |  | Satish | Satish | 5 | 2024-04-16 | 2024-04-20 | 2024-05-01 | 2024-05-04 | 2024-05-04 |  | Completed |  |  | 2024-04-20 | 2024-04-21 |  | 2024-05-04 | 2024-05-05 | 2024-05-05 | 2024-05-20 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-17 | 2024-05-18 |  |  | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
61 | SD | SFDC | Broker Invoice creation from SAP to SFDC | SOW | Integration | 10 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-25 | 2024-04-26 | Not Started |  |  |  | Sumant Bharti | Sumant Bharti | 5 | 2024-05-05 | 2024-05-09 | 2024-05-05 | 2024-05-08 |  |  | Completed |  |  | 2024-05-09 | 2024-05-10 |  | 2024-05-05 | 2024-05-06 | 2024-05-12 |  | Not Started | Avinash/Bhavesh/Haredra/Devendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
62 | SD | SFDC | Broker payment SAP-SFDC | SOW | Integration | 11 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-28 | 2024-04-28 | 2024-04-28 | 2024-04-28 | 2024-04-27 | 2024-04-28 | Not Started |  |  |  | Sumant Bharti | Sumant Bharti | 5 | 2024-05-10 | 2024-05-14 | 2024-05-09 | 2024-05-11 |  |  | Completed |  |  | 2024-05-14 | 2024-05-15 |  | 2024-05-05 | 2024-05-06 |  |  | Not Started | Avinash/Bhavesh/Haredra/Devendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
63 | SD | SFDC | Booking creation SFDC-SAP | SOW | Integration | 5 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-04-25 | Approved | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2024-04-22 | 2024-04-23 | 2024-04-23 | Completed |  |  |  | Sridhar | Sridhar | 5 | 2024-04-21 | 2024-04-25 | 2024-05-12 | 2024-05-16 | 2024-04-25 | 2024-05-20 | Completed |  |  | 2024-04-25 | 2024-04-26 |  | 2024-04-25 | 2024-04-26 | 2024-04-28 | 2024-05-20 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
64 | SD | SFDC | Booking amendment | SOW | Integration | 6 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-05-01 | Approved | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-05-02 | 2024-05-06 | Completed |  |  |  | Sumant Bharti | Sumant Bharti | 5 | 2024-04-26 | 2024-04-30 | 2024-05-17 | 2024-05-20 | 2024-05-07 | 2024-05-18 | Completed |  |  | 2024-04-30 | 2024-05-01 |  | 2024-05-08 | 2024-05-12 | 2024-05-20 | 2024-05-20 | Completed | Avinash/Bhavesh | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
65 | SD | SFDC | Demand information sync to SFDC | SOW | Integration | 7 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-05-04 | 2024-05-06 | Completed |  |  |  | Sumant Bharti | Sumant Bharti | 4 | 2024-05-01 | 2024-05-04 | 2024-05-21 | 2024-05-25 | 2024-05-10 | 2024-05-25 | Completed |  |  | 2024-05-04 | 2024-05-05 |  | 2024-05-08 | 2024-05-12 | 2024-06-03 | 2024-06-04 | Completed | Avinash/Bhavesh/Haredra/Devendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
66 | SD | SFDC | Debit note - wrt Demand no | SOW | Integration | 8 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-05-07 | 2024-05-10 | Completed |  |  |  | Veeru | Veeru | 4 | 2024-05-05 | 2024-05-08 | 2024-05-26 | 2024-05-28 | 2024-05-14 |  | Completed |  |  | 2024-05-08 | 2024-05-09 |  | 2024-05-08 | 2024-05-12 |  |  | Not Started | Avinash/Bhavesh/Haredra/Devendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
67 | SD | SFDC | Credit note - wrt Demand no | SOW | Integration | 9 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-05-07 | 2024-05-10 | Completed |  |  |  | Veeru | Veeru | 1 | 2024-05-09 | 2024-05-09 | 2024-05-29 | 2024-05-31 | 2024-05-14 |  | Completed |  |  | 2024-05-09 | 2024-05-10 |  | 2024-05-08 | 2024-05-12 | 2024-05-20 |  | In Process | Avinash/Bhavesh/Haredra/Devendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
68 | SD | SFDC | Unit Transfer | SOW | Integration | 12 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-05-09 |  | Completed |  |  |  | Sumant Bharti | Sumant Bharti | 4 | 2024-05-09 | 2024-05-12 | 2024-06-01 | 2024-06-02 | 2024-06-04 | 2024-06-05 | Completed |  |  | 2024-05-12 | 2024-05-13 |  | 2024-05-08 | 2024-05-12 | 2024-06-06 | 2024-06-06 | Completed | [6 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
69 | SD | SFDC | Unit Cancellation | SOW | Integration | 13 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  | Submitted | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-12 |  | Completed |  |  |  | Sumant Bharti | Sumant Bharti | 4 | 2024-05-13 | 2024-05-16 | 2024-06-03 | 2024-06-04 | 2024-06-04 | 2024-06-05 | Completed |  |  | 2024-05-16 | 2024-05-17 |  | 2024-05-08 | 2024-05-12 | 2024-06-06 | 2024-06-06 | Completed | [6 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
70 | SD | Clear tax | E invoicing/IRN Creation SAP-CT | SOW | Integration | 15 | SIT | Complex | Bharat Nagda | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-05-01 | Approved | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-02 | 2024-05-02 | Completed |  |  |  | Pavan | Pavan | 6 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-06-02 | 2024-05-04 | 2024-05-15 | Completed |  |  | 2024-05-22 | 2024-05-23 |  | 2024-05-08 | 2024-05-12 | 2024-05-23 | 2024-05-23 | Completed | Harendra / Devendra / Surendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_INV
71 | SD | Clear tax | E invoicing/IRN Cancellation SAP-CT | SOW | Integration | 15 | SIT | Complex | Bharat Nagda | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-05-01 | Approved | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-02 | 2024-05-02 | Completed |  |  |  | Pavan | Pavan | 6 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-06-02 | 2024-05-18 | 2024-05-15 | Completed |  |  | 2024-05-22 | 2024-05-23 |  | 2024-05-08 | 2024-05-12 | 2024-05-23 | 2024-05-23 | Completed | Harendra / Devendra / Surendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_INV
72 | SD | Clear tax | Eway Bill Generation SAP-CT | SOW | Integration | 15 | SIT | Complex | Bharat Nagda | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-05-01 | Approved | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-02 | 2024-05-02 | Completed |  |  |  | Pavan | Pavan | 6 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-06-02 | 2024-05-18 | 2024-05-20 | Completed |  |  | 2024-05-22 | 2024-05-23 |  | 2024-05-08 | 2024-05-12 | 2024-05-23 | 2024-05-23 | In Process | Harendra / Devendra / Surendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_INV
73 | SD | Clear tax | Eway Bill Cancellation SAP-CT | SOW | Integration | 15 | SIT | Complex | Bharat Nagda | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-05-01 | Approved | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-02 | 2024-05-02 | Completed |  |  |  | Pavan | Pavan | 6 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-06-02 | 2024-05-18 | 2024-05-20 | Completed |  |  | 2024-05-22 | 2024-05-23 |  | 2024-05-08 | 2024-05-12 | 2024-05-23 | 2024-05-23 | In Process | Harendra / Devendra / Surendra | [5 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_INV
74 | SD | Clear tax | Get Eway Bill PDF | SOW | Integration | 15 | SIT | Complex | Bharat Nagda | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-05-01 | Approved | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-02 | 2024-05-02 | Completed |  |  |  | Pavan | Pavan | 6 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-06-02 | 2024-06-02 | 2024-05-25 | Completed |  |  | 2024-05-22 | 2024-05-23 |  | 2024-05-08 | 2024-05-12 | 2024-05-31 | 2024-05-31 | Completed | [6 empty] | 2024-05-25 | 2024-05-28 |  |  | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_INV
75 | SD | SFDC | Post Possession clearance | SOW | Integration | 14 | SIT | Complex | Karanpal | 2024-03-01 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | Submitted | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-04-15 | 2024-04-16 | Not Started |  |  |  | Sumant Bharti | Sumant Bharti | 5 | 2024-05-23 | 2024-05-27 | 2024-06-05 | 2024-06-07 |  |  | In Process |  |  | 2024-05-27 | 2024-05-28 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-28 |  | Not Started | Not Started | 2024-06-07
76 | SD |  | Future Demand & Cash flow report | SOW | Report | 2 | Go Live | Complex | Karanpal | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-04-29 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-02 | Completed |  |  |  | Srinivas | Srinivas | 3 | 2024-04-19 | 2024-04-21 | 2024-04-01 | 2024-04-05 | 2024-04-04 | 2024-04-19 | Completed |  |  | 2024-04-21 | 2024-04-22 |  | 2024-04-23 | 2024-04-24 | 2024-04-19 | 2024-04-20 | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_CASH_FLOW
77 | SD |  | Demand will not create if customer blocked | SOW | Enhancement | 1 | SIT | Complex | Karanpal | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-30 | 2024-03-30 | 2024-03-26 | 2024-03-28 | Completed |  |  |  | Satish Bhakth | Satish Bhakth | 1 | 2024-04-22 | 2024-04-22 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | Completed |  |  | 2024-04-22 | 2024-04-23 |  | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | Completed | Avinash / Bhavesh | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | Approved |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
78 | SD |  | Delay In Process Report to identify the demand(Milestone trigger But due for billing) | SOW | Report | 1 | Post Go Live | Medium | Karanpal | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-04-15 | Approved | 2024-03-19 | 2024-03-19 | 2024-03-30 | 2024-03-30 | 2024-03-22 | 2024-03-23 | Completed |  |  |  | Satish Bhakth | ABAP5 | 2 | 2024-04-22 | 2024-04-23 | 2024-06-26 | 2024-06-29 |  |  | In Process |  |  | 2024-04-23 | 2024-04-24 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07
79 | SD |  | RERA Form-3 | SOW | Form | 2 | Post Go Live | Medium | Karanpal |  | NA | NA | NA |  |  |  |  | Hold | 2024-03-19 | 2024-03-19 | 2024-03-31 | 2024-03-31 |  |  | Hold |  |  |  | Satish Bhakth | ABAP5 | 3 | 2024-04-24 | 2024-04-26 |  |  |  |  | Hold |  |  | 2024-04-26 | 2024-04-27 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [7 empty] | Requirement not cleared from @Sandeep sir
80 | SD |  | RERA Form-5 | SOW | Form | 2 | Post Go Live | Medium | Karanpal |  | NA | NA | NA |  |  |  |  | Hold | 2024-03-19 | 2024-03-19 | 2024-03-31 | 2024-03-31 |  |  | Hold |  |  |  | Satish Bhakth | ABAP5 | 4 | 2024-04-27 | 2024-04-30 |  |  |  |  | Hold |  |  | 2024-04-30 | 2024-05-01 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [7 empty] | Requirement not cleared from @Sandeep sir
81 | SD |  | Scrap Invoice | SOW | Form | 2 | Go Live | Medium | Bharat Nagda | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-23 |  | Submitted | 2024-03-19 | 2024-03-19 | 2024-03-31 | 2024-03-31 | 2024-04-02 | 2024-05-03 | Completed |  |  |  | MOhan Reddy | MOhan Reddy | 3 | 2024-05-01 | 2024-05-03 | 2024-04-01 | 2024-04-05 | 2024-05-04 | 2024-05-25 | Completed |  |  | 2024-05-03 | 2024-05-04 |  | 2024-05-20 | 2024-05-23 | 2024-05-24 | 2024-05-25 | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07 | [7 empty] | Scrap invoice tested and found ok. | ZSD_PRINT
82 | SD |  | Legacy Data Table & Upload Program | SOW | Report | 2 | Go Live | Medium | Bharat Nagda | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-23 | 2024-03-23 | Approved | 2024-03-19 | 2024-03-19 | 2024-03-31 | 2024-03-31 | 2024-04-02 | 2024-05-03 | Completed |  |  |  | Srinivas Moturi | Srinivas Moturi | 3 | 2024-05-01 | 2024-05-03 | 2024-04-01 | 2024-04-05 | 2024-05-04 | 2024-05-14 | Completed |  |  | 2024-05-03 | 2024-05-04 |  | 2024-05-08 | 2024-05-09 | 2024-05-11 | 2024-05-14 | Completed | [10 empty] | Not Started |  | 2024-04-30 | 2024-05-18 |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZSD_LEGACY
83 | MM |  | Material Master Upload Program | SOW | Conversion | 1 | Go Live | Simple | Izharuddin | 2024-03-08 | 2024-03-09 | 2024-03-11 | 2024-03-12 | 2024-03-08 | 2024-03-09 | 2024-03-13 | 2024-04-23 | Approved | NA | NA | NA | NA | NA | NA | NA |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-18 | 2024-03-31 | Completed |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | 2024-03-14 | 2024-03-31 | 2024-03-31 | Completed | Rajan | 2024-05-01 | 2024-05-01 |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-21 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | Copied | 1 | 33.33% | Development | ZMM_MATMAST_UPLOAD
84 | MM |  | Service Master Upload Program | SOW | Conversion | 1 | Go Live | Simple | Izharuddin | 2024-03-08 | 2024-03-09 | 2024-03-11 | 2024-03-12 | 2024-03-08 | 2024-03-09 | 2024-03-13 | 2024-04-23 | Approved | NA | NA | NA | NA | NA | NA | NA |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-18 | 2024-03-18 | Completed |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | 2024-03-14 | 2024-03-31 | 2024-03-31 | Completed | Anas | 2024-05-15 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-21 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | Copied | 1 | 33.33% |  | ZMM_AC01
85 | MM |  | HSN Master Upload-LSMW | SOW | Conversion | 1 | Go Live | Simple | Shantanu | 2024-03-08 | 2024-03-09 | 2024-03-11 | 2024-03-12 | 2024-03-08 | 2024-03-09 | 2024-03-13 | 2024-04-23 | Approved | NA | NA | NA | NA | NA | NA | NA |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | Completed |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | 2024-03-14 | 2024-03-12 | 2024-03-13 | Completed | Sandeep Sir | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-21 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL |  | 1 | 33.33% |  | _
86 | MM |  | Cutover Purchase Order Upload Program | SOW | Conversion | 1 | Go Live | Complex | Shantanu | 2024-03-09 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-09 | 2024-03-11 | 2024-03-19 | 2024-04-23 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-18 | 2024-04-26 | Completed |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-05-01 | Completed | Rajan | [8 empty] | 2024-05-21 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | Copied | 1 | 14.29% |  | ZMM_PO_UPL
87 | MM |  | Cutover Work Order Upload Program | SOW | Conversion | 2 | Go Live | Complex | Shantanu | 2024-03-09 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-09 | 2024-03-11 | 2024-03-19 | 2024-04-15 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-18 |  | Completed |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-05-13 | Completed | Shreya Deolekar | [8 empty] | 2024-05-21 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | Copied | 1 | 14.29% |  | ZMM_POWO_UPD
88 | MM |  | Initial Stock Upload Program | SOW | Conversion | 2 | Go Live | Simple | Shantanu | 2024-03-09 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-09 | 2024-03-11 | 2024-03-19 | 2024-04-06 | Approved | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-18 | 2024-04-23 | Completed |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | 2024-03-14 | 2024-04-23 | 2024-04-23 | Completed | Pramod/Somnath | 2024-05-04 | 2024-05-04 |  | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-20 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | Copied | 1 | 14.29% |  | ZMM_INSTSKT2
89 | MM |  | Purchase Order Print | SOW | Form | 1 | SIT | Complex | Shantanu | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-04-23 | Approved | 2024-03-15 | 2024-03-18 | 2024-03-15 | 2024-03-19 | 2024-03-20 | 2024-03-21 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 6 | 2024-03-15 | 2024-03-20 | 2024-03-21 | 2024-03-27 | 2024-03-22 | 2024-03-30 | Completed |  |  | 2024-03-20 | 2024-03-21 |  | 2024-03-29 | 2024-03-29 | 2024-03-31 | 2024-04-02 | Completed | Rajan | 2024-05-12 | 2024-05-12 |  | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [5 empty] | 1 |  |  | _
90 | MM |  | Purchase Order Amendment | SOW | Form | 2 | SIT | Complex | Shantanu | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-04-23 | Approved | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-19 | 2024-03-19 | 2024-03-27 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 6 | 2024-03-15 | 2024-03-20 | 2024-03-15 | 2024-03-20 | 2024-04-20 | 2024-04-27 | Completed |  |  | 2024-03-20 | 2024-03-21 |  | 2024-04-20 | 2024-03-21 | 2024-04-27 | 2024-04-28 | Completed | Rajan | 2024-05-12 | 2024-05-12 | 2024-05-11 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZMM_POAMEND
91 | MM |  | Work Order Print | SOW | Form | 1 | SIT | Complex | Shantanu | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-03-15 | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-03-18 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-19 | 2024-03-20 | 2024-03-21 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 5 | 2024-03-16 | 2024-03-20 | 2024-03-30 | 2024-04-04 | 2024-03-30 | 2024-04-04 | Completed |  |  | 2024-03-20 | 2024-03-21 |  | 2024-03-30 | 2024-03-21 | 2024-04-04 | 2024-04-26 | Completed | Shreya Deolekar | 2024-05-12 | 2024-05-12 | 45423 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
92 | MM |  | Work Order Amendment Form | SOW | Form | 2 | SIT | Complex | Shantanu | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-03-15 | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-03-18 | Approved | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-19 | 2024-03-26 | 2024-03-27 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 5 | 2024-03-16 | 2024-03-20 | 2024-03-16 | 2024-03-20 | 2024-04-20 | 2024-04-27 | Completed |  |  | 2024-03-20 | 2024-03-21 |  | 2024-03-20 | 2024-03-21 | 2024-04-27 | 2024-04-28 | Completed | Shreya Deolekar | 2024-05-12 | 2024-05-12 | 2024-05-11 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZMM_WOAMEND
93 | MM |  | Purchase (Material) Debit Note | SOW | Form | 2 | Post Go Live | Simple | Harshad | 2024-03-16 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  | Hold | 2024-03-18 | 2024-03-18 | 2024-03-22 | 2024-03-23 |  |  | Hold |  |  |  | V. Veeranajan | Sumant Bharti | 3 | 2024-04-08 | 2024-04-10 | 2024-07-01 | 2024-07-04 |  |  | Hold |  |  | 2024-04-10 | 2024-04-11 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
94 | MM |  | Purchase (Service) Debit Note | SOW | Form | 1 | Post Go Live | Simple | Harshad | 2024-03-16 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  | Hold | 2024-03-18 | 2024-03-18 | 2024-03-22 | 2024-03-23 |  |  | Hold |  |  |  | V. Veeranajan | Sumant Bharti | 3 | 2024-04-11 | 2024-04-13 | 2024-07-04 | 2024-07-08 |  |  | Hold |  |  | 2024-04-13 | 2024-04-14 | [5 empty] | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
95 | FICO |  | Payment Request (Advance) | SOW | Form | 1 | SIT | Simple | Harshad | 2024-03-16 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  | Approved | 2024-03-18 | 2024-03-18 | 2024-03-22 | 2024-03-23 | 2024-04-01 | 2024-04-01 | Completed |  |  |  | Sumant | Sumant | 2 | 2024-04-14 | 2024-04-15 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-03 | Completed |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-03 | Completed |  | 2024-04-18 | 2024-04-19 |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-19 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_ADV_REQ
96 | FICO |  | Vendor Onboading | SOW | Form | 2 | Go Live | Simple | Harshad | 2024-03-16 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2024-03-20 | 2024-03-21 | 2024-03-21 |  | Approved | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-19 | Completed |  |  |  | Srinivas Moturi | Srinivas Moturi | 1 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-30 | 2024-03-27 | 2024-03-30 | Completed |  |  | 2024-03-27 | 2024-03-28 |  | 2024-03-27 | 2024-03-30 | 2024-03-27 | 2024-03-30 | Completed |  | 2024-04-18 | 2024-04-19 |  | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-19 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_VENDOR_FORM
97 | MM |  | Purchase Register - Indent to Payment | SOW | Report | 1 | Go Live | Complex | Izharuddin | 2024-03-12 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-12 | 2024-03-14 | 2024-03-19 | 2024-04-23 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | Srinivas Moturi | Srinivas Moturi | 1 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | Completed |  |  | 2024-03-18 | 2024-03-19 |  | 2024-03-18 | 2024-03-19 | 2024-03-29 | 2024-05-23 | Completed | Rajan/Shreya | 2024-05-20 | 2024-05-20 |  | 2024-05-20 | 2024-05-20 | 2024-05-23 | 2024-05-23 | 2024-05-23 |  | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | Copied | 3 | 42.86% |  | ZMM_PR_TO_PAY
98 | MM |  | Work Order Amendment Enhancement | SOW | Enhancement | 1 | SIT | Complex | Shantanu | 2024-03-12 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-12 | 2024-03-14 | 2024-03-18 | 2024-04-15 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | Satish Bhakt | Satish/Mayur | 4 | 2024-04-01 | 2024-04-04 | 2024-04-08 | 2024-04-15 | 2024-04-08 | 2024-04-17 | Completed |  |  | 2024-04-04 | 2024-04-05 |  | 2024-04-15 | 2024-04-16 | 2024-04-18 | 2024-04-22 | Completed | Shreya Deolekar | 2024-05-12 | 2024-05-12 | 45423 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL |  | 1 | 14.29% |  | _
99 | MM |  | Release Strategy mandatory for PO/WO saving | SOW | Enhancement | 1 | SIT | Simple | Shantanu | 2024-03-12 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-12 | 2024-03-14 | 2024-03-19 | 2024-04-23 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 2 | 2024-04-05 | 2024-04-06 | 2024-04-18 | 2024-04-19 | 2024-04-18 | 2024-04-19 | Completed |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2024-04-20 | Completed | Rajan Arekar/Shreya Deolekar | 2024-05-12 | 2024-05-12 | 45423 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL |  | 3 | 100% |  | _
100 | MM |  | Release Strategy Reset with Version Management | SOW | Enhancement | 2 | SIT | Complex | Shantanu | 2024-03-12 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-12 | 2024-03-14 | 2024-03-19 | 2024-04-15 | Approved | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 2 | 2024-04-06 | 2024-04-07 | 2024-04-19 | 2024-04-20 | 2024-04-19 | 2024-04-20 | Completed |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-20 | 2024-04-21 | 2024-04-20 | 2024-04-21 | Completed | Rajan/Shreya Deolekar | 2024-05-12 | 2024-05-12 | 45423 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2024-05-12 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL |  | 4 | 57.14% |  | _
101 | MM |  | Transfer Posting 311Q to Contractor w.r.t. WO | SOW | Enhancement | 2 | SIT | Complex | Izharuddin | 2024-03-14 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-12 | 2024-03-14 | 2024-03-14 | 2024-04-23 | Approved | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-23 | 2024-03-21 | 2024-03-27 | Completed |  |  |  | V. Veeranajan | Sridhar Yamala | 3 | 2024-04-07 | 2024-04-09 | 2024-04-21 | 2024-04-22 | 2024-04-17 | 2024-04-27 | Completed |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-22 | 2024-04-23 | 2024-04-27 | 2024-05-01 | Completed | Pramod Mishra | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-20 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
102 | MM |  | Maintain WO Terms & Conditions – Header | SOW | Enhancement | 1 | SIT | Simple | Izharuddin | 2024-03-14 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-14 | 2024-03-16 | 2024-03-19 | 2024-04-23 | Approved | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | NA | NA | NA |  |  |  | V. Veeranajan | Satish Bhakt | 2 | 2024-03-18 | 2024-03-19 | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-30 | Completed |  |  | 2024-03-19 | 2024-03-20 |  | 2024-03-19 | 2024-03-20 | 2024-03-19 | 2024-03-21 | Completed | Shreya Deolekar | 2024-04-20 | 2024-04-20 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-23 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 16.67% |  | ZMM_WO_HTC
103 | MM |  | Bill Inward with Workflow | SOW | Enhancement | 1 | SIT | Complex | Izharuddin | 2024-03-14 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-14 | 2024-03-16 | 2024-03-19 | 2024-04-22 | Approved | 2024-03-20 | 2024-03-21 | 2024-03-20 | 2024-03-22 | 2024-03-18 | 2024-03-19 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 10 | 2024-03-21 | 2024-03-30 | 2024-03-19 | 2024-03-30 | 2024-03-19 | 2024-03-30 | Completed |  |  | 2024-03-30 | 2024-03-31 |  | 2024-03-29 | 2024-04-22 | 2024-03-29 | 2024-04-22 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 | 2024-04-20 | 2024-05-04 | 2024-05-04 | 2024-05-16 | 2024-05-28 | 2024-05-16 | 2024-05-28 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | WIP | 2 | 28.57% |  | ZMM_BD
104 | MM | Smart app | PO/WO Intergration with Smart App for DPR | SOW | Integration | 2 | Hold | Complex | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-16 | 2024-03-17 |  |  | Hold | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  |  | Hold |  |  |  | V. Veeranajan | V. Veeranajan | 5 | 2024-04-08 | 2024-04-12 | 2024-04-20 | 2024-04-22 |  |  | Not Started |  |  | 2024-04-12 | 2024-04-13 |  | 2024-04-22 | 2024-04-23 |  |  | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
105 | MM | Smart app | PR Integration with Smart App | SOW | Integration | 2 | Go Live | Complex | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-16 | 2024-03-17 | 2024-03-19 | 2024-04-23 | Approved | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  | Completed |  |  |  | Srinivas Moturi | Srinivas Moturi | 6 | 2024-04-08 | 2024-04-13 | 2024-07-01 | 2024-07-08 |  |  | In Process |  |  | 2024-04-13 | 2024-04-14 |  | 2024-07-08 | 2024-07-09 |  |  | Not Started | Rajan Arekar/Shreya Deolekar | [9 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
106 | MM | Smart app | Material and Service Procurement Bidding Intergration with Smart App | SOW | Integration | 2 | Go Live | Complex | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-16 | 2024-03-17 | 2024-03-19 | 2024-04-23 | Approved | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 |  |  | Completed |  |  |  | Srinivas Moturi | Srinivas Moturi | 8 | 2024-04-08 | 2024-04-15 | 2024-07-01 | 2024-07-08 |  |  | In Process |  |  | 2024-04-15 | 2024-04-16 |  | 2024-07-08 | 2024-07-09 |  |  | Not Started | Rajan Arekar/Shreya Deolekar | [9 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
107 | QM |  | Inspection Plan Upload | SOW | Conversion | 2 | Go Live | Medium | P. Srinivasulu | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | NA | 2024-03-16 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-28 | 2024-03-28 | NA |  |  |  | V. Veeranajan | Sridhar Yamala | 2 | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-18 | Completed |  |  | 2024-03-16 | 2024-03-17 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | Completed | Amol Deshpandy / Mahesh | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | [5 empty] | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 10% |  | ZQP01_Upload
108 | QM |  | MIC Quantitative | SOW | Conversion | 2 | Go Live | Medium | P. Srinivasulu | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | NA | 2024-03-16 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-28 | 2024-03-28 | NA |  |  |  | V. Veeranajan | V. Veeranajan | 2 | 2024-03-18 | 2024-03-19 | 2024-03-16 | 2024-03-16 | 2024-03-17 | 2024-03-18 | Completed |  |  | 2024-03-19 | 2024-03-20 |  | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | Completed | Amol Deshpandy / Mahesh | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | [5 empty] | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 0.5 | 10% |  | ZQS21_Upload
109 | QM |  | Sampling Procedure | SOW | Conversion | 2 | Go Live | Medium | P. Srinivasulu | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Submitted | 2024-03-16 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-28 | 2024-03-28 | Completed |  |  |  | V. Veeranajan | Srinivas M | 5 | 2024-04-11 | 2024-04-15 | 2024-04-17 | 2024-04-18 | 2024-04-20 | 2024-04-23 | Completed |  |  | 2024-04-22 | 2024-04-23 |  | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | Completed | Amol Deshpandy / Mahesh | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | [5 empty] | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZQDV1_Upload
110 | QM |  | Catalog | SOW | Conversion | 2 | Go Live | Medium | P. Srinivasulu | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Submitted | 2024-03-16 | 2024-03-16 | 2024-03-20 | 2024-03-22 | 2024-03-28 | 2024-03-28 | Completed |  |  |  | V. Veeranajan | Srinivas M | 5 | 2024-04-11 | 2024-04-15 | 2024-04-17 | 2024-04-18 | 2024-04-20 | 2024-04-23 | Completed |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-20 | 2024-04-20 | 2024-04-22 | 2024-04-23 | Completed | Amol Deshpandy / Mahesh | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | [5 empty] | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZQS41_Upload
111 | QM |  | Result Record Report - Smartform | SOW | Form | 2 | SIT | Medium | P. Srinivasulu | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 | Submitted | 2024-03-18 | 2024-03-18 | 2024-03-22 | 2024-03-20 | 2024-03-20 | 2024-03-20 | Completed |  |  |  | V. Veeranajan | Mohan Reddy | 2 | 2024-04-09 | 2024-04-10 | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-28 | Completed |  |  | 2024-04-10 | 2024-04-11 |  | 2024-03-27 | 2024-03-28 | 2024-03-28 | 2024-03-28 | Completed | Amol Deshpandy / Mahesh | 2024-05-13 | 2024-05-13 |  | 2024-05-13 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-17 | In Correction |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 2 | 40% |  | ZQM_LAB_REPORT
112 | MM |  | Cost Plan reference rate in Work Order/Purchase Order and warning message on higher rate than cost plan rate in purchasing | SOW | Enhancement | 2 | Go Live | Simple | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-16 | 2024-03-17 | 2024-03-19 | 2024-04-23 | Approved | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | Sridhar Yamala | Sridhar Yamala | 2 | 2024-04-08 | 2024-04-09 | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-05-03 | Completed |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-24 | 2024-04-25 | 2024-05-04 | 2024-05-04 | Completed | Rajan Arekar | 2024-05-04 | 2024-05-04 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-23 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL |  | 1 | 33.33% |  | _
113 | MM |  | Restricting Goods Receipt against Multiple Purchase order in One GRN Document | SOW | Enhancement | 2 | SIT | Simple | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-16 | 2024-03-17 | 2024-03-19 | 2024-04-23 | Approved | 2024-03-27 | 2024-03-28 | 2024-03-27 | 2024-03-28 | 2024-03-22 | 2024-03-24 | Completed |  |  |  | V. Veeranajan | Sridhar Yamala | 3 | 2024-04-09 | 2024-04-11 | 2024-04-09 | 2024-04-11 | 2024-04-09 | 2024-04-11 | Completed |  |  | 2024-04-11 | 2024-04-12 |  | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2024-04-12 | Completed | Pramod Mishra | 2024-05-15 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-20 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
114 | MM |  | While Transfer Posting to Contractor Storage, debitable materials (Non-FOC) has to be captured for deductions from RA Bill | SOW | Enhancement | 2 | SIT | Complex | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-04-23 | Approved | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-03-30 | 2024-03-28 | Hold for A/c | Not Started |  |  |  | V. Veeranajan | Sridhar Yamala | 5 | 2024-04-11 | 2024-04-15 | 2024-07-01 | 2024-07-08 |  |  | Completed |  |  | 2024-04-15 | 2024-04-16 |  | 2024-07-08 | 2024-07-09 |  |  | Not Started | Pratik Gour | [9 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [7 empty] | In-Process (Izhar) (Configuration part done. Email enhancement In-Process) | _
115 | MM |  | Quantity Validation for Project Material PR (Doc type ZPPR) | SOW | Enhancement | 2 | SIT | Simple | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-17 | 2024-03-18 | 2024-03-16 | 2024-03-17 | 2024-03-21 | 2024-04-23 | Approved | 2024-03-29 | 2024-03-30 | 2024-03-29 | 2024-03-30 | 2024-03-27 | 2024-03-28 | Completed |  |  |  | V. Veeranajan | Sridhar Yamala | 2 | 2024-04-15 | 2024-04-16 | 2024-04-12 | 2024-04-15 | 2024-04-12 | 2024-04-17 | Completed |  |  | 2024-04-16 | 2024-04-17 |  | 2024-04-15 | 2024-04-16 | 2024-04-18 | 2024-04-20 | Completed | Ketan Sawant | 2024-05-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-20 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
116 | MM |  | Restricting final RA Bill against Work order if any surplus material for the Work Order (Contractor Godown) is present in stock | SOW | Enhancement | 2 | Go Live | Simple | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-19 | 2024-03-20 | 2024-03-16 | 2024-03-17 | 2024-03-31 | 2024-04-08 | Approved | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-02 | 2024-03-31 | 2024-04-02 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 3 | 2024-04-18 | 2024-04-20 | 2024-04-30 | 2024-05-01 | 2024-05-01 | 2024-05-04 | Completed |  |  | 2024-04-20 | 2024-04-21 |  | 2024-05-01 | 2024-05-02 | 2024-05-04 | 2024-05-04 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-28 | 2024-05-16 |  | In Process |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZMM_BD
117 | MM |  | Debit head of one contractor to be tagged to work order of other contractor | SOW | Enhancement | 2 | SIT | Complex | Izharuddin | 2024-03-16 | 2024-03-17 | 2024-03-19 | 2024-03-20 | 2024-03-16 | 2024-03-17 | 2024-03-31 | 2024-04-08 | Approved | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-03-31 | 2024-04-01 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 2 | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-20 | Completed |  |  | 2024-04-03 | 2024-04-04 |  | 2024-04-08 | 2024-04-09 | 2024-04-20 | 2024-04-22 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-24 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
118 | MM |  | Custom Table and Validation on ITC and Non-ITC Tax Code in Purchase Document. | SOW | Enhancement | 2 | SIT | Simple | Izharuddin | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-20 | 2024-03-13 | 2024-03-14 | 2024-03-15 |  | Submitted | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-27 | Completed |  |  |  | V. Veeranajan | Mayur/Sridhar | 1 | 2024-04-21 | 2024-04-21 | 2024-04-21 | 2024-04-21 | 2024-04-11 | 2024-04-12 | Completed |  |  | 2024-04-21 | 2024-04-22 |  | 2024-04-11 | 2024-04-12 | 2024-04-11 | 2024-04-12 | Completed | Sandeep Pimpalkar | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _ | TABLE: ZMM_ITC_PLANTS
119 | MM |  | For Manufacturing Material require Barcode system . Which is Check after Delivery (Test / Performance Report) | Hold | Integration | 2 | Hold | Complex | Izharuddin | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-03-22 | 2024-03-18 | 2024-03-19 | Hold |  | Hold | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  | Hold |  |  |  | V. Veeranajan | Mayur Joshi | [7 empty] | Hold | [9 empty] | Hold | [10 empty] | Hold |  | 2024-04-30 |  |  | Hold | Not Started | 2024-06-07 | [8 empty] | _
120 | MM |  | Email trigger as per TAT for Bill Inward | SOW | Enhancement | 2 | SIT | Simple | Izharuddin | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-03-22 | 2024-03-18 | 2024-03-19 | 2024-03-21 |  | Submitted | 2024-03-22 | 2024-03-23 | 2024-03-22 | 2024-03-23 | 2024-03-22 | 2024-03-26 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 2 | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | 2024-04-02 | 2024-04-03 | Completed |  |  | 2024-04-03 | 2024-04-04 |  | 2024-04-06 | 2024-04-08 | 2024-04-06 | 2024-04-08 | Completed | Sandeep Pimpalkar | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 |  | Approved | ep | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
121 | MM |  | Bill Inward TAT report | SOW | Report | 2 | Post Go Live | Simple | Shantanu/Izharuddin | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-18 | 2024-03-19 | 2024-03-21 |  | Submitted | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-29 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 3 | 2024-04-11 | 2024-04-13 | 2024-03-29 | 2024-03-30 | 2024-03-29 | 2024-03-30 | Completed |  |  | 2024-04-13 | 2024-04-14 |  | 2024-04-13 | 2024-04-14 | 2024-04-13 |  | Functional Correction | Sandeep Pimpalkar | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 |  | Approved | ep | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZMM_BD_TAT
122 | MM |  | Email trigger as per TAT for Project service indent | SOW | Enhancement | 2 | SIT | Simple | Shantanu | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-04-23 | Approved | 2024-03-29 | 2024-03-30 | 2024-03-29 | 2024-03-30 |  |  | Not Started |  |  |  | V. Veeranajan | Madhu | 4 | 2024-04-06 | 2024-04-09 | 2024-04-17 | 2024-04-19 | 2024-04-17 |  | Completed |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-19 | 2024-04-20 | 2024-05-08 | 2024-05-13 | Completed | Ketan Sawant | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-21 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | _
123 | MM |  | Process payment abstract Print/COP | SOW | Form | 3 | SIT | Complex | Izharuddin | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-03-22 | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-04-22 | Approved | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 5 | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-29 | Completed |  |  | 2024-03-29 | 2024-03-30 |  | 2024-03-28 | 2024-03-29 | 2024-03-28 | 2024-03-29 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 |  | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M |  |  | 0% |  | _
124 | MM |  | SLA Report | SOW | Report | 3 | Post Go Live | Complex | Shantanu/Izharuddin | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-19 | 2024-03-20 | 2024-03-20 | 2024-04-22 | Approved | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 7 | 2024-03-20 | 2024-03-26 | 2024-03-20 | 2024-03-26 | 2024-03-20 | 2024-03-30 | Completed |  |  | 2024-03-26 | 2024-03-27 |  | 2024-03-29 | 2024-03-30 | 2024-03-29 | 2024-03-30 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 |  | 2024-05-16 | 2024-05-16 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-23 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | RDPL | WIP | 3 | 42.86% |  | ZMM_BD
125 | MM |  | Escalation / Price variation calculation in RA Bill | SOW | Enhancement | 3 | SIT | Complex | Izharuddin | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-19 | 2024-03-20 | 2024-03-22 | 2024-04-29 | Approved | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 3 | 2024-03-26 | 2024-03-28 | 2024-07-08 | 2024-07-10 |  |  | In Process |  |  | 2024-03-28 | 2024-03-29 |  | 2024-07-10 | 2024-07-11 | 2024-04-27 |  | In Process | Pratik Gour | 2024-05-04 | 2024-05-04 |  | 2024-05-04 | 2024-05-04 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 14.29% | Price Variance In-Process (Izhar) (50%) | ZMM_WO_GIE | ZMM_WO_RABILL_ESC1 | ZMM_WO_PVM_1 | ZMM_WO_RABILL_PVC_1
126 | MM |  | Material reconciliation & material recovery | SOW | Enhancement | 3 | SIT | Complex | Izharuddin | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-19 | 2024-03-20 | 2024-03-22 | 2024-04-29 | Approved | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-18 | 2024-03-18 | Completed |  |  |  | V. Veeranajan | Satish/Mayur | 2 | 2024-03-28 | 2024-03-29 | 2024-04-19 | 2024-04-23 | 2024-04-30 | 2024-05-12 | Completed |  |  | 2024-03-29 | 2024-03-30 |  | 2024-04-23 | 2024-04-24 | 2024-05-03 | 2024-05-12 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 | 45416 | 2024-05-04 | 2024-05-16 | 2024-05-16 | 2024-05-28 | 2024-05-16 | 2024-05-04 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 14.29% |  | ZMM_WO_FOC_MTAG | ZMM_WO_RAB_RECO
127 | MM |  | Recovery of advances in RA Bill | SOW | Enhancement | 3 | SIT | Complex | Izharuddin | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-19 | 2024-03-20 | 2024-03-22 | 2024-04-29 | Approved | 2024-04-01 | 2024-04-02 | 2024-04-01 | 2024-04-03 | 2024-04-01 | 2024-04-03 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 4 | 2024-04-03 | 2024-04-06 | 2024-04-26 | 2024-04-30 | 2024-04-26 | 2024-04-29 | Completed |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-30 | 2024-05-01 | 2024-04-30 | 2024-05-01 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 | 45416 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-23 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 1 | 14.29% |  | ZMM_WOADV_RABRECO
128 | MM |  | Maintain materials to be issued against the Work Order (Free Supply / Debitable) | SOW | Enhancement | 3 | SIT | Complex | Izharuddin | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-19 | 2024-03-20 | 2024-03-27 | 2024-04-29 | Approved | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | Completed |  |  |  | V. Veeranajan | Mayur Joshi | 5 | 2024-03-22 | 2024-03-26 | 2024-03-22 | 2024-03-26 | 2024-03-22 | 2024-03-29 | Completed |  |  | 2024-03-26 | 2024-03-27 |  | 2024-03-26 | 2024-03-29 | 2024-03-26 | 2024-03-29 | Completed | Anas Shaikh | 2024-04-20 | 2024-04-20 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-28 | 2024-05-14 | 2024-05-31 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 2 | 28.57% |  | ZMM_WO_BOM
129 | MM |  | Creation of advance request RA Bill against the Work Order | SOW | Enhancement | 3 | SIT | Complex | Izharuddin | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-19 | 2024-03-20 | 2024-03-22 | 2024-04-29 | Approved | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-28 | 2024-03-28 | Completed |  |  |  | V. Veeranajan | Satish Bhakt | 7 | 2024-03-27 | 2024-04-02 | 2024-03-27 | 2024-04-02 | 2024-03-27 | 2024-04-09 | Completed |  |  | 2024-04-02 | 2024-04-03 |  | 2024-04-03 | 2024-04-09 | 2024-04-03 | 2024-04-09 | Completed | Pratik Gour | 2024-05-04 | 2024-05-04 |  | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 |  |  | Yes | M3M | Copied | 3 | 42.86% |  | ZMM_WO_ADV
130 | MM |  | Project service indent TAT report | SOW | Report | 2 | Post Go Live | Simple | Shantanu | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-04-23 | Approved | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-04-26 | 2024-04-27 | Completed |  |  |  | V. Veeranajan | V. Veeranajan | 1 | 2024-04-25 | 2024-04-25 | 2024-07-01 | 2024-07-08 | 2024-07-01 |  | Completed |  |  | 2024-04-25 | 2024-04-26 |  | 2024-07-08 | 2024-07-09 |  |  | Not Started | Ketan Sawant | [9 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
131 | FICO | HDFC/ICICI | Bank Interface | SOW | Integration | 2 | Go Live | Complex | Harshad | 2024-04-20 | 2024-04-22 | 2024-04-20 | 2024-04-22 | 2024-04-20 | 2024-04-22 |  |  | NA | 2024-04-20 | 2024-04-22 |  |  |  |  | Not Started |  |  |  | Mayur Joshi | Mayur Joshi | 3 | 2024-04-20 | 2024-04-22 | 2024-05-15 | 2024-05-31 | 2024-05-15 |  | In Process |  |  | 2024-04-20 | 2024-04-22 | 45402 |  |  |  |  | Not Started | [10 empty] | Not Started |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07
132 | FICO |  | Cheque Back Print | SOW | Form | 2 | Go Live | Complex | Harshad | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | Approved | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-04-23 | Not Started |  |  |  | Mohan | Mohan | 2 | 2024-04-22 | 2024-04-23 | 2024-04-22 | 2024-04-23 | 2024-04-20 | 26-04-2024 | Completed |  |  | 2024-04-22 | 2024-04-23 | 45402 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 26-04-2024 | Completed |  | 2024-04-18 | 2024-04-19 | [7 empty] | Approved |  | 2024-04-30 |  |  | Not Started | Not Started | 2024-06-07 | [8 empty] | ZFI_CHQ_PRINT
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
Formulas:
Planned Start = [Planned Finish]
Planned Finish = [Planned Start]+1
Planned Finish = [Planned Start]
Revised Start = [Actual Start]
Revised Start = [Revised Finish]
Revised Finish = [Actual Finish]
Revised Finish = [Revised Start]+1
Actual Start = [Revised Finish]+1
Actual Start = [Actual Finish]
Actual Finish = [Actual Start]+1

## Config & User Manual
|  | Configuration |  |  | UT |  | Configuration Manual
Module | Functional Consultant | Planned Date | Revised Date | Actual Date | Planned Date | Actual Date | Planned Date | Actual Date
SD | Karanpal Chouhan | 2024-03-11 |  | 2024-03-12 | 2024-03-14 | 2024-03-16
MM | Izharuddin Quazi | 2024-03-12 | 2024-03-13 |  | 2024-03-14 | 2024-03-16
PS | Nilesh Patil | 2024-03-11 |  | 2024-03-11 | 2024-03-14 | 2024-03-15
FI | Harshad Mhatre | 2024-03-11 | 2024-03-13 |  | 2024-03-14 | 2024-03-16
QM | Parvathineni Srinivasulu | 2024-03-11 |  | 2024-03-12 | 2024-03-14 | 2024-03-16
DMS | Nilesh Patil | -